## DDR#256
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 256
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-03
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 39.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-02 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 225
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 713.62
DEPTH, MD (M) |  | 4412 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 817
MW IN (SG) |  | 1.8 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1755.62
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 616
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 500
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2871.62
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 108000
GEL ST. |  | 13/27 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 14800
WL (ml/30 min.) |  | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 122800
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 30000
KCl (mg/l) |  | 50718.2 | JAR |  | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 30000
CHLORIDES |  | 23500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 390000
CALCIUM |  | 180 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 18
SOLIDS % |  | 28.09 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 37775 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 16258791 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 90.08% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4385 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4385 |  | 1025/1025 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4385 |  | 1225/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43345 | 43345.0521 | 1.25 | DRL | NPT-UP | DP | CONT'D RIH FROM 124M TO 285M, MEANWHILE P/UP 3 1/2'' DP'S SINGLE BY SINGLE FROM CATWALK. DRIFTED EACH JOINT. (TOTAL 3 1/2'' JTS = 30)
43345.0521 | 43345.0625 | 0.25 | DRL | NPT-UP | CIR | CIRCULATED TO FLUSH STRING. CIRCULATED 2 TIMES STRING VOLUME.
43345.0625 | 43345.4375 | 9 | DRL | NPT-UP | RIH | CONT'D RIH FROM 285M ON 5'' DP'S TO 4268M.
43345.4375 | 43345.4479 | 0.25 | DRL | NPT-UP | CIR | M/UP TDS. RESUMED CIRCULATION. WASHED DOWN TO 4295M.
43345.4479 | 43345.4792 | 0.75 | DRL | NPT-UP | FC | PUMPED & SPOTTED 20 BBL HV PILL @ 4295M
43345.4792 | 43345.6458 | 4 | DRL | NPT-UP | POOH | P/UP TO 4280 M CIRCULATED FOR COOLING BHT PRIOR TO CEMENT JOB. PREPARED FLUID MIX DURING CIRCULATION.
43345.6458 | 43345.6667 | 0.5 | DRL | NPT-UP | RU | PJSM. R/UP CIRCULATING HEAD FOR CMT PLUG JOB. HOOKED UP DWS PUMPER & RIG PUMP TO CIRCULATING HEAD
43345.6667 | 43345.6875 | 0.5 | DRL | NPT-UP | P/T | FLUSHED LINES & PRESSURE TESTED HOOK UP @ 500 PSI & @ 3000 PSI. PRESSURE TEST OK.
43345.6875 | 43345.75 | 1.5 | DRL | NPT-UP | CIR | SWITCHED OVER TO RIG PUMP & CIRCULATED, MEANWHILE DWS WEIGHTED UP CEMENT SLURRY.
43345.75 | 43345.7708 | 0.5 | DRL | NPT-UP | CMT | STOPPED CIRCULATION. PUMPED 60 BBLS SPACER OF 1.95 SP.GR WITH RIG PUMP. R/DOWN CIRCULATING HEAD. SQUEEZED & PUSHED FOAM BALL INSIDE STRING & R/UP CIR HEAD. SWITCHED OVER TO DWS PUMP.
43345.7708 | 43345.8125 | 1 | DRL | NPT-UP | CMT | PUMPED 60 BBLS OF BATCH MIXED CEMENT SLURRY HAVING SP.GR 2.10 S.G; FOLLOWED BY 20 BBLS OF SPACER HAVING 1.95 SP.GR. DISPLACED WITH 200 BBLS OF MUD WITH DWS PUMPER. BLED OFF PRESSURE TO CHECK BACK FLOW, OBSERVED NO BACK FLOW.
43345.8125 | 43345.8646 | 1.25 | DRL | NPT-UP | POOH | R/DOWN CIRCULATING HEAD & POOH FROM 4280M TO 4000M AT SLOW SPEED.
43345.8646 | 43345.9375 | 1.75 | DRL | NPT-UP | WOC | WOC, M/UP CIRCULATING HEAD, CLOSED BOP, REVERSE CIRCULATED OUT 2 TIMES STRING VOLUME. DUMPED 80 BBL CONTAMINATED MUD + SPACER (1.92 S.G).
43345.9375 | 43345.9792 | 1 | DRL | NPT-UP | WOC | WOC, OPENED BOP, M/UP TDS & PULLED UPTO 3982M. DIRECT CIRCULATED BTM UP PRIOR POOH.
43345.9792 | 43346 | 0.5 | DRL | NPT-UP | WOC | WOC, POOH FROM 3982M TO 3935M, MEANWHILE GREASED/DOPED EACH 5'' DP JOINT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43346 | 43346.2083 | 5 | DRL | NPT-UP | WOC | WOC, CONT'D POOH FROM 3935M TO 3298M. MEANWHILE GREASED/DOPED EACH 5'' DP JOINT CONNECTION.
43346.2083 | 43346.25 | 1 | DRL | NPT-UP | WOC | WOC, REPLACING IBOP IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | REPLACING IBOP IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 4295M, SPOTTED 20 BBL HV PILL, P/UP TO 4280M, PERFORMED CMT PLUG JOB, POOH TO 4000M, REVERSE CIRCULATED 2XSTRING VOLUMES, P/UP TO 3982M, DIRECT CIRCULATION, POOH UPTO 3935M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WOC, MEANWHILE POOH TO SURFACE, P/UP & M/UP TC BIT, RIH TO TAG / DRESS CMT, POOH.
REMARKS |  |  | BACKLOADED W.FORD USED D. JAR + SCREW IN SUB (UNUSED) ON 02-09-18.
Formulas:
DHARIAN-1-ST-1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14