## DDR#257
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 257
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-01-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/ MUHAMMAD MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 256.9792
RIG REP.: |  | JAVED MUGHAL / KHALID M GILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | TESTING DAYS: | [6 empty] | 14.0792
2020-01-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 79.9
CHECK TIME |  | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 975
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | Bottom Nose | [7 empty] | 0.264 |  |  | PITS (BBL) | 730
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 4-1/2" 5 SPF Power Jet Omega (201.5 m loaded) | [7 empty] | 66 |  |  | ACT. SYS (BBL) | 1784.9
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | Safety Spacer | [7 empty] | 5.22 |  |  | RESV. SYS (BBL) | 1019
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | eFire / TCF Redundant Firing Head | [7 empty] | 3.792 |  |  | KILL MUD (BBL) | 340
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 02 x 2 7/8" EUE Tubing Joints | [7 empty] | 19.178 |  |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) |  | 79 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | Debris Sub - 01 | [7 empty] | 0.538 |  |  | TOTAL | 3143.9
PV |  | 36 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 01 x 2 7/8" EUE Tubing Joints | [7 empty] | 9.614 |  |  | DIESEL (LTR)
YIELD POINT |  | 29 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | Debris Sub - 02 | [7 empty] | 0.535 |  |  | RIG TANK | 87240
GEL ST. |  | 11/19 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 02 x 2 7/8" EUE Tubing Joints | [7 empty] | 19.058 |  |  | CAMP TANK | 20051
WL (ml/30 min) |  | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | RA MARKER | [7 empty] | 0.566 |  |  | CONSUMED | 4182
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | X-over: 2-7/8" EUE Pin X 3-1/2" PH-6 Box | [7 empty] | 0.413 |  |  | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | Tubing : 3-1/2" | [10 empty] | TOTAL | 107291
ALK (FILT.) |  | 0.3/0.9 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 612004
MAX SHIELD % |  | 1.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) |  | 3 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 35948
KCl (mg/l) |  | 33367.3 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 41500
CHLORIDES (mg/l) |  | 18000 | 3.5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 340 | 4.75" DCS |  | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % |  | 0.8 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 125.178 | 0 |  | MPCL | 6
MAX GUARD % |  | 0.7 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 48
SOLIDS % |  | 23.69 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 7 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 139
DAILY WELL COST (US$) |  | 150652.1449 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 18906812.5404 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 94.98% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-02 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43845 | 43846 | 24 | TEST | PT-P | DST | WELL UNDER PRODUCTION TESTING. FIRED TCP GUNS BY ACTIVATING MECHANICAL FIRING HEAD BY SLICK LINE TOOL. POOH TCP GUNS ON 3.5"-12.95 PPF-PH-6 TUBING IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43846 | 43846.25 | 6 | TEST | PT-P | DST | WELL UNDER PRODUCTION TESTING. POOH TCP GUNS ON 3.5"-12.95 PPF-PH-6 TUBING IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WELL UNDER PRODUCTION TESTING.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WELL UNDER PRODUCTION TESTING. FIRED TCP GUNS BY ACTIVATING MECHANICAL FIRING HEAD BY SLICK LINE TOOL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WELL UNDER PRODUCTION TESTING.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21