## DDR#258
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 258
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 41.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 15RR1 |  | BHA No. |  |  | 37 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 224
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 705.28
DEPTH, MD (M) | 4412 | 4412 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRI-CONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 | 0.034239 |  | PITS (BBL) | 839
MW IN (SG) | 1.8 | 1.84 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137 |  | BIT SUB (F.V) |  |  | 6.5 | 3.5 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1768.28
MW OUT (SG) | 1.8 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RJ2167 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.24 | 1.2655 |  | RESV. SYS (BBL) | 700
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.69 | 0.23146 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 136 | 137 | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 X OPEN |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 62 | 61 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.88 | 0.25748 |  | TOTAL | 2968.28
PV | 36 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 4 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.03 | 5.0715 |  | DIESEL (LTR)
YIELD POINT | 26 | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 9 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.86 | 6.1171 |  | RIG TANK | 96000
GEL ST. | 15/27 | 15/29 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CAMP TANK | 13500
WL (ml/30 min.) | 3.6 | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 3 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 28.12 | 2.0512 |  | CONSUMED | 7650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 109500
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 105000
KCl (mg/l) | 50908.9 | 50870.8 | JAR |  | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 105000
CHLORIDES | 23500 | 23500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 390000
CALCIUM | 200 | 200 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 182.16 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  |  |  | BIT NO. 15RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 13 |  |  | MPCL SERV | 17
SOLIDS % | 28.09 | 28.39 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | TOTAL | 111
DAILY WELL COST (US$) |  | 39794 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 16364172 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 90.67% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4385 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4385 |  | 1025/1025 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4385 |  | 1225/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43347 | 43347.2396 | 5.75 | DRL | NPT-UP | RIH | CONT'D RIH DOWN TO 3309M. FILLED UP STRING EVERY 15 STANDS.
43347.2396 | 43347.2604 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED @ 9 5/8'' CSG WINDOW.
43347.2604 | 43347.2708 | 0.25 | DRL | NPT-UP | RIH | RIH FROM 3312M TO 3399 M. OBSERVED COMPRESSION.
43347.2708 | 43347.2812 | 0.25 | DRL | NPT-UP | RW | M/UP TDS WASHED DOWN TO 3422M.
43347.2812 | 43347.3021 | 0.5 | DRL | NPT-UP | RIH | RIH FROM 3422 M TO 3538M.
43347.3021 | 43347.3125 | 0.25 | DRL | NPT-UP | RW | REAMED DOWN TO 3566M
43347.3125 | 43347.3333 | 0.5 | DRL | NPT-UP | RIH | RIH FROM 3566 M TO 3656 M.
43347.3333 | 43348 | 16 | DRL | NPT-UP | RW | REAMED DOWN FROM 3656 TO 3900M. HARD REAMING BELOW 3680M. OBSERVED FREQUENT ROTARY STALLING (TORQUE LIMIT SET AT 15KFP). MEANWHILE GRADUALLY INCREASED MUD SP. GRAVITY FROM 1.80 TO 1.84.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43348 | 43348.1979 | 4.75 | DRL | NPT-UP | RW | CONT'D REAMING DOWN FROM 3900M TO 3970M. GRADUALLY INCREASED MUD SP. GR. FROM 1.84 TO 1.85. WHILE REAMING DOWN OBSERVED LEAKAGE IN WASHPIPE.
43348.1979 | 43348.2396 | 1 | DRL | NPT-UP | RR | RACK BACK STAND. R/UP CIRCULATING HEAD AND RESUMED CIRCULATION, REPLACED WASHPIPE. P/TESTED SAME, OK.
43348.2396 | 43348.25 | 0.25 | DRL | NPT-UP | RW | CONT'D REAMING DOWN FROM 3970 TO 3975M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | REAMING DOWN TO TAG/DRESS CMT IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 3309M, FILLED UP STRING EVERY 15 STANDS, CIRCULATED AT 9 5/8'' CSG WINDOW, RIH FROM 3312M TO 3399M, OBSERVED COMPRESSION, WASHED DOWN TO 3422M, RIH FROM 3422M TO 3538M, REAMED DOWN TO 3566M, RIH FROM 3566M TO 3656M, REAMED DOWN FROM 3656M TO 3900M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE REAM DOWN TO TAG CMT, DRESS/ CLEAN OUT CMT TO +/- 4150M , POOH TO SURFACE FOR KICK OFF.
REMARKS |  |  | INCREASED MUD SP. GR FROM 1.80 TO 1.85 S.G., RECEIVED 1 X 8 1/2'' PDC BIT (MDSi616)
Formulas:
DHARIAN-1-ST-1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14