## DDR#259
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 259
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-06
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT RAO /SAIFULLAH TURK / S. HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 42.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-05 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 15RR1 |  | BHA No. |  |  | 37 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 226
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 698.26
DEPTH, MD (M) | 4412 | 4412 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRI-CONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 | 0.034239 |  | PITS (BBL) | 887
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137 |  | BIT SUB (F.V) |  |  | 6.5 | 3.5 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1811.26
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RJ2167 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.24 | 1.2655 |  | RESV. SYS (BBL) | 611.25
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.69 | 0.23146 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 140 | 139 | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 X OPEN |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 63 | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.88 | 0.25748 |  | TOTAL | 2922.51
PV | 38 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 4 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.03 | 5.0715 |  | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 9 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.86 | 6.1171 |  | RIG TANK | 88000
GEL ST. | 15/29 | 16/31 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CAMP TANK | 12850
WL (ml/30 min.) | 3.6 | 3.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 3 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 28.12 | 2.0512 |  | CONSUMED | 8650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 100850
ALK (FILT.) | 0.6 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 205000
KCl (mg/l) | 50146.2 | 50336.9 | JAR | 36.6 | STAB - 1 | 36.6 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 215000
CHLORIDES | 23000 | 23200 | 5" HWDPS | 36.6 | STAB - 2 | 36.6 | TFA (IN²) | [14 empty] | TOTAL | 400000
CALCIUM | 200 | 220 | 6 1/2" DCS | 36.6 | NMDC |  | HSI | [14 empty] | POB
OIL % | 5 | 5.5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 182.16 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 36.6 |  | BIT NO. 15RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 13 |  |  | MPCL SERV | 18
SOLIDS % | 28.51 | 28.31 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 39.9 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 43922 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 16398229 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 90.85% | MUD CLEANER | 2 x 140 + 1 x 140 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4385 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4385 |  | 1025/1025 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4385 |  | 1225/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43348 | 43348.1979 | 4.75 | DRL | NPT-UP | RW | CONT'D REAMING DOWN FROM 3900M TO 3970M. GRADUALLY INCREASED MUD SP. GR. FROM 1.84 TO 1.85. WHILE REAMING DOWN OBSERVED LEAKAGE IN WASHPIPE.
43348.1979 | 43348.2396 | 1 | DRL | NPT-UP | RR | RACK BACK STAND. R/UP CIRCULATING HEAD AND RESUMED CIRCULATION, REPLACED WASHPIPE. P/TESTED SAME, OK.
43348.2396 | 43348.4583 | 5.25 | DRL | NPT-UP | RW | CONT'D REAMING DOWN FROM 3970 TO 4020M.
43348.4583 | 43348.8958 | 10.5 | DRL | NPT-UP | DC | DRILLED CMT FROM 4020M TO 4136M. FOUND FIRM TO MODERATELY HARD CMT BELOW 4100M.
43348.8958 | 43348.9375 | 1 | DRL | NPT-UP | CIR | CIRCULATED TO CONDITION MUD.
43348.9375 | 43349 | 1.5 | DRL | NPT-UP | CIR | PUMPED 20 BBL HI VIS PILL AND CIRCULATED OUT TILL SHAKERS CLEAN.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43349 | 43349.0104 | 0.25 | DRL | NPT-UP | FC | CHECKED FLOW, WELL STATIC.
43349.0104 | 43349.125 | 2.75 | DRL | NPT-UP | POOH | POOH FROM 4136M TO 3296M. OBSERVED TIGHT SPOTS, CLEARED SAME BY RECIPROCATION OF STRING. ( FROM 4099M TO 4067, 4048M TO 4020M)
43349.125 | 43349.1354 | 0.25 | DRL | NPT-UP | FC | CHECKED FLOW, WELL STATIC.
43349.1354 | 43349.25 | 2.75 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3296M TO 2107M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D REAMING DOWN TO 4020M, MEANWHILE INCREASED MUD SP. GR FROM 1.84 TO 1.85 SG, DRILLED CMT FROM 4020M TO 4136M, CIRCULATED TO CONDITION MUD, PUMPED 20 BBL HI-VIS AND CIRCULATED OUT TILL SHAKERS CLEAN
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN JAR + BIT, P/UP SCHL KICK OFF ASSY AND BHA, RIH TO 4136M FOR SIDE TRACK.
REMARKS
Formulas:
DHARIAN-1-ST-1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14