## DDR#260
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 260
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4136 / 4002.12 METER (PBTD) | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 43.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4136 /4002.12 METER (PBTD) | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8 1/2'' |  | BIT NO. |  | 15RR1 |  | 16RR1 | BHA No. |  |  | 38 | IN (M) |  | 4136 |  | OUT (M) |  |  | STRING (BBL) | 180
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4136 |  | SIZE (IN) |  | 8.5 |  | 8.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 704.35
DEPTH, MD (M) |  | 4136 | TVD @ 00:00HR (M) |  | 4002.12 |  | MANUFACTURER |  | SMITH |  | HLB | TRI-CONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 887
MW IN (SG) |  | 1.85 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137 |  | QH30R | XP MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.68 | 1.0518 |  | ACT. SYS (BBL) | 1786.35
MW OUT (SG) |  | 1.85 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RJ2167 |  | 12235652 | FLOAT SUB |  |  | 6.1875 | 2.8125 |  | 4 1/2 IF |  | 0.49 | 0.067109 |  | RESV. SYS (BBL) | 705
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | 537 | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | 139 | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 X OPEN |  | 3 X 24 | SPSA |  |  | 6.75 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 4136 | NMDC |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | TOTAL | 2991.35
PV |  | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | DRESSED CMT |  |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 1.2696 |  | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  |  | 18 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.97 | 12.2524 |  | RIG TANK | 80000
GEL ST. |  | 16/32 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CAMP TANK | 12200
WL (ml/30 min.) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 15 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.11 | 10.2202 |  | CONSUMED | 8650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [15 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [15 empty] | TOTAL | 92200
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [15 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [15 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 41000
KCl (mg/l) |  | 50527.6 | JAR | 36.6 | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 81000
CHLORIDES |  | 23400 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) |  |  |  | 1.33 | [11 empty] | TOTAL | 440000
CALCIUM |  | 220 | 6 1/2" DCS |  | NMDC | 0 | HSI | [15 empty] | POB
OIL % |  | 5.5 | MUD MOTOR |  | SPSA | 0 | DULL CODE |  | I-O-D-L-B-G-O-R |  |  | TOTAL LENGTH (M) | [7 empty] | 349.91 |  |  | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT NO. 15RR1 |  | 2-3-FC-C3-E-I-NO-BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 18
SOLIDS % |  | 28.3 | ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 11 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [12 empty] | TOTAL | 108
DAILY WELL COST (US$) |  | 37524 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [12 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 16435753 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [12 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 91.06% | MUD CLEANER | 2 x 140 + 1 x 140 |  |  | 7" LINER | [15 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" |  | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" |  | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" |  | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43349 | 43349.0104 | 0.25 | DRL | NPT-UP | FC | CHECKED FLOW, WELL STATIC.
43349.0104 | 43349.125 | 2.75 | DRL | NPT-UP | POOH | POOH FROM 4136M TO 3296M. OBSERVED TIGHT SPOTS, CLEARED SAME BY RECIPROCATION OF STRING. ( FROM 4099M TO 4067, 4048M TO 4020M)
43349.125 | 43349.1354 | 0.25 | DRL | NPT-UP | FC | CHECKED FLOW, WELL STATIC.
43349.1354 | 43349.5 | 8.75 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3296M TO SURFACE. B/OUT AND L/DOWN BIT.
43349.5 | 43349.5833 | 2 | DRL | NPT-UP | BHA | P/UP AND M/UP TC BIT ( SR # 12235652, HLB, IADC: 537, 3 X 24/32'' NOZZLES) + SCHL XP MOTOR AND MWD TOOLS.
43349.5833 | 43349.6042 | 0.5 | DRL | NPT-UP | E/C | SHALLOW TESTED SCHL TOOLS WITH 400 GPM + 950 PSI - OK
43349.6042 | 43349.7083 | 2.5 | DRL | NPT-UP | BHA | RIH KICK OFF BHA TO 349M (P/UP 21 JNTS OF 5" HWDP FROM CATWALK). FLUSHED SAME.
43349.7083 | 43349.9479 | 5.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 349M TO 2792M ON 5'' DP. FILLED UP STRING EVERY 15 STANDS.
43349.9479 | 43349.9896 | 1 | DRL | NPT-UP | RS | CUT & SLIPPED 25M D.LINE.
43349.9896 | 43350 | 0.25 | DRL | NPT-UP | RIH | CONT'D RIH FROM 2792M TO 2963M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43350 | 43350.1042 | 2.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 2963M TO 3710M. OBSERVED COMPRESSION.
43350.1042 | 43350.125 | 0.5 | DRL | NPT-UP | RW | WASHED DOWN FROM 3710M TO 3761M.
43350.125 | 43350.1667 | 1 | DRL | NPT-UP | RIH | CONT'D RIH FROM 3761M TO 4016M. OBSERVED COMPRESSION.
43350.1667 | 43350.2083 | 1 | DRL | NPT-UP | RW | WASHED DOWN FROM 4016M TO 4045M.
43350.2083 | 43350.2188 | 0.25 | DRL | NPT-UP | RIH | CONT'D RIH FROM 4045M TO 4096M.
43350.2188 | 43350.25 | 0.75 | DRL | NPT-UP | RW | REAMED DOWN FROM 4096M TO 4132M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | REAMING IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CHECKED FLOW, WELL STATIC, POOH FROM 4136M TO SURFACE, L/DOWN BIT. P/UP AND M/UP TC BIT + SCHL K/OFF TOOLS, SHALLOW TESTED SAME, OK, RIH TO 2792M, FILLED UP STRING EVERY 15 STANDS, CUT AND SLIPPED D. LINE, CONT'D RIH TO 2963M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO BTM AT 4136M, SIDE TRACK.
REMARKS |  |  | RECEIVED W.FORD BACKUP 6 1/2'' D. JAR ON 06-09-18.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14