## DDR#261
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 261
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4141 / 4006.24 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 44.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4143 /4007.52 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 5
2018-09-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8 1/2'' |  | BIT NO. |  | 16RR1 |  | BHA No. |  |  | 38 | IN (M) |  | 4136 |  | OUT (M) |  |  | STRING (BBL) | 231
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4141 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 628.6
DEPTH, MD (M) | 4136.5 | 4141 | TVD @ 00:00HR (M) |  | 4006.24 |  | MANUFACTURER |  | HLB |  | TRI-CONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 951
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 5 |  | TYPE |  | QH30R |  | XP MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.68 | 1.0518 |  | ACT. SYS (BBL) | 1810.62
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  | 0.5 |  | SERIAL NO. |  | 1223562 |  | FLOAT SUB |  |  | 6.1875 | 2.8125 |  | 4 1/2 IF |  | 0.49 | 0.067109 |  | RESV. SYS (BBL) | 646
ECD (SG) | 1.92 | 1.92 | AVG. ROP (M/HR) |  | 0.44 |  | IADC CODE |  | 537 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 138 | 139 | AVG. WOB (TON) |  | 3.89 |  | NOZZLES |  | 3 X 24 |  | SPSA |  |  | 6.75 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 65 | 65 | AVG. RPM SURFACE |  | 0 |  | DEPTH IN (M) |  | 4136 |  | NMDC |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | TOTAL | 2956.62
PV | 39 | 38 | AVG. RPM DOWNHOLE |  | 119 |  | DEPTH OUT (M) |  |  |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 1.2696 |  | DIESEL (LTR)
YIELD POINT | 27 | 28 | FLOWRATE (GPM) |  | 424 |  | METERAGE (M) |  | 5 |  | 18 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.97 | 12.2524 |  | RIG TANK | 74000
GEL ST. | 15/30 | 16/32 | PRESSURE (PSI) |  | 3120 |  | RPM SURF. |  | 0 |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CAMP TANK | 11550
WL (ml/30 min.) | 3.8 | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 120 |  | 15 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.11 | 10.2202 |  | CONSUMED | 7650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 4-6 | [12 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 127 |  | AVG. ROP (M/HR) |  | 0.44092 | [12 empty] | TOTAL | 85550
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  | 155 |  | BIT ROT HRS. |  | 11.34 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 80.97 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 80.97 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 76.63 | [12 empty] | CONSUMED | 77000
KCl (mg/l) | 50718.2 | 50870.8 | JAR | 40.61 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 31.4 | [12 empty] | RECEIVED | 77000
CHLORIDES | 23400 | 23400 | 5" HWDPS | 4.01 | STAB - 2 |  | TFA (IN²) |  | 1.33 | [12 empty] | TOTAL | 440000
CALCIUM | 200 | 200 | 6 1/2" DCS | 4.01 | NMDC | 4.01 | HSI |  | 0.6 | [12 empty] | POB
OIL % | 5.5 | 5.5 | MUD MOTOR | 4.01 | SPSA | 4.01 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 349.91 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 4.01 |  | BIT NO. 16RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 17
SOLIDS % | 28.51 | 28.4 | ON BOTTOM HRS |  | 11.34 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 11 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 19.43 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 107
DAILY WELL COST (US$) |  | 42593 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 16478346 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 91.3% | MUD CLEANER | 2 x 140 + 1 x 140 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4130 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4130 |  | 1050/1040 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4130 |  | 1250/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43350 | 43350.1042 | 2.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 2963M TO 3710M. OBSERVED COMPRESSION.
43350.1042 | 43350.125 | 0.5 | DRL | NPT-UP | RW | WASHED DOWN FROM 3710M TO 3761M.
43350.125 | 43350.1667 | 1 | DRL | NPT-UP | RIH | CONT'D RIH FROM 3761M TO 4016M. OBSERVED COMPRESSION.
43350.1667 | 43350.2083 | 1 | DRL | NPT-UP | RW | WASHED DOWN FROM 4016M TO 4045M.
43350.2083 | 43350.25 | 1 | DRL | NPT-UP | RIH | CONT'D RIH FROM 4045M TO 4096M.
43350.25 | 43350.375 | 3 | DRL | NPT-UP | RW | HARD REAMED DOWN FROM 4096M TO BOTTOM AT 4136M. RECORDED CHECKSHOT AND SCR AT CONNECTION.
43350.375 | 43350.4062 | 0.75 | DRL | NPT-UP | DM | DRILLED 8 1/2'' HOLE FROM 4136M TO 4136.5M IN ROTARY MODE. OBSERVED FREQUENT ROTARY STALLING.
43350.4062 | 43351 | 14.25 | DRL | NPT-UP | DM | P/UP STRING, SWITCHED OVER TO SLIDE MODE. ATTEMPTED TO KICK OFF WELL FROM 4136.5M. OBSERVED MOTOR STALLING FOLLOWED BY STRING STUCK, WORKED ON STRING AND RELEASED SAME. PUMPED HI-VIS AND CONT'D KICK OFF WELL FROM 4136.5M TO 4141M. OBSERVED 100 % FORMATION SAMPLE IN SPOT OF 4141M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43351 | 43351.25 | 6 | DRL | NPT-UP | DM | CONT'D DRILLING 8 1/2'' DIRECTIONAL HOLE FROM 4141M TO 4143M IN SLIDE MODE.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' DIRECTIONAL HOLE IN SLIDE MODE IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH DOWN TO 4096M, WASHED DOWN FROM 3710-3761M & 4016-4045M, REAMED DOWN FROM 4096M TO BTM AT 4136M, DRILLED 8 1/2'' HOLE FROM 4136M TO 4136.5M IN ROTARY MODE, SWITCHED OVER TO SLIDE MODE, KICKED OFF WELL FROM 4136.5M TO 4141M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE DRILLING 8 1/2'' DIRECTIONAL HOLE IN SLIDE MODE, POOH TO CHANGE THE BIT/BHA.
REMARKS |  |  | RECEIVED B/UP 2 X ST. STABS ON 06-09-18.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14