## DDR#261
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 261
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-01-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/MUHAMMAD MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 260.9792
RIG REP.: |  | TARIQ BUTT / KHALID M GILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | TESTING DAYS: | [6 empty] | 18.0792
2020-01-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 929.6
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | MULE SHOE + PERF JOINT | [7 empty] | 3.7 |  |  | PITS (BBL) | 857.4
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | X-OVER | [7 empty] | 0.32 | 0.006169 |  | ACT. SYS (BBL) | 1787
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | CHAMP PACKER | [7 empty] | 3.615 | 0.25078 |  | RESV. SYS (BBL) | 1017
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | SAFETY JOINT | [7 empty] | 1.175 | 0.081511 |  | KILL MUD (BBL) | 340
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | HYD JAR | [7 empty] | 1.59 | 0.1103 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) |  | 80 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | X-OVER | [7 empty] | 0.355 | 0.024627 |  | TOTAL | 3144
PV |  | 36 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | GAUGE CARRIER | [7 empty] | 2.65 | 0.18383 |  | DIESEL (LTR)
YIELD POINT |  | 29 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | X-OVER | [7 empty] | 0.53 | 0.036767 |  | RIG TANK | 119915
GEL ST. |  | 10/17 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | SELECTOR TESTER VALVE | [7 empty] | 4.84 | 0.33576 |  | CAMP TANK | 17545
WL (ml/30 min) |  | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | X-OVER | [7 empty] | 0.255 | 0.01769 |  | CONSUMED | 3404
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 3 X 4.75 DCS | [7 empty] | 27.52 | 1.9091 |  | RECEIVED
ALK (MUD) |  | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | X-OVER | [7 empty] | 0.254 | 0.01762 |  | TOTAL | 137460
ALK (FILT.) |  | 0.3/1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) |  |  |  |  | 5" RD CIR VALVE | [7 empty] | 1.34 | 0.092958 |  | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  |  | X-OVER | [7 empty] | 0.265 | 0.018383 |  | RIG STORAGE | 610343
MAX SHIELD % |  | 1.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  |  |  | 21 X 4.75" DCS | [7 empty] | 191.83 | 13.3075 |  | CAMP STORAGE | 72000
KCl (%) |  | 3 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  |  |  | X-OVER | [7 empty] | 0.27 | 0.01873 |  | CONSUMED | 65971
KCl (mg/l) |  | 33367.3 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  |  |  | 2 X SLIP JOINTS | [7 empty] | 10.98 | 0.49036 |  | RECEIVED | 106100
CHLORIDES (mg/l) |  | 18000 | 3.5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) |  |  |  |  | 2 X-OVERS | [7 empty] | 1.025 | 0.01976 |  | DRL WASTE
HARDNESS (mg/l) |  | 340 | 4.75" DCS |  | STAB - 3 |  | TFA (IN²) |  |  |  |  | 3.5" TUBING JOINTS | [10 empty] | POB
PENETREX % |  | 0.8 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 252.514 | 16.9219 |  | MPCL | 6
MAX GUARD % |  | 0.7 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 37
SOLIDS % |  | 23.69 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 7 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 127
DAILY WELL COST (US$) |  | 38215 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19116473.734 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 96.03% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-02 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43848 | 43849 | 24 | TEST | PT-P | DST | WELL UNDER PRODUCTION TESTING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43849 | 43849.25 | 6 | TEST | PT-P | DST | WELL UNDER PRODUCTION TESTING.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WELL UNDER PRODUCTION TESTING.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WELL UNDER PRODUCTION TESTING.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WELL UNDER PRODUCTION TESTING.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21