## DDR#262
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 262
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-09
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4150 / 4012.57 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 45.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4150 /4012.57 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 9
2018-09-08 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8 1/2'' |  | BIT NO. |  | 16RR1 |  | BHA No. |  |  | 38 | IN (M) |  | 4136 |  | OUT (M) | 4150 |  | STRING (BBL) | 231
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4150 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 630.48
DEPTH, MD (M) | 4146 | 4150 | TVD @ 00:00HR (M) |  | 4012.57 |  | MANUFACTURER |  | HLB |  | TRI-CONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 956
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 9 |  | TYPE |  | QH30R |  | XP MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.68 | 1.0518 |  | ACT. SYS (BBL) | 1817.48
MW OUT (SG) | 1.85 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 1223562 |  | FLOAT SUB |  |  | 6.1875 | 2.8125 |  | 4 1/2 IF |  | 0.49 | 0.067109 |  | RESV. SYS (BBL) | 624
ECD (SG) | 1.92 |  | AVG. ROP (M/HR) |  | 0.48 |  | IADC CODE |  | 537 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 141 |  | AVG. WOB (TON) |  | 8 |  | NOZZLES |  | 3 X 24 |  | SPSA |  |  | 6.75 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 65 | 64 | AVG. RPM SURFACE |  | 40 |  | DEPTH IN (M) |  | 4136 |  | NMDC |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | TOTAL | 2941.48
PV | 40 | 39 | AVG. RPM DOWNHOLE |  | 119 |  | DEPTH OUT (M) |  | 4150 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 1.2696 |  | DIESEL (LTR)
YIELD POINT | 29 | 28 | FLOWRATE (GPM) |  | 424 |  | METERAGE (M) |  | 14 |  | 18 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.97 | 12.2524 |  | RIG TANK | 65000
GEL ST. | 12/30 | 15/29 | PRESSURE (PSI) |  | 3200 |  | RPM SURF. |  | 40 |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CAMP TANK | 10900
WL (ml/30 min.) | 3.8 | 3.9 | TORQ. ON-BTM (KLB-FT) |  | 6-7 |  | RPM BTM. |  | 120 |  | 15 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.11 | 10.2202 |  | CONSUMED | 9650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 4-8 | [12 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 127 |  | AVG. ROP (M/HR) |  | 0.46589 | [12 empty] | TOTAL | 75900
ALK (FILT.) | 0.5 | 0.6 | PICK-UP WT. (TON) |  | 155 |  | BIT ROT HRS. |  | 30.05 | [12 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 143.57 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 224.54 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 76.63 | [12 empty] | CONSUMED | 80000
KCl (mg/l) | 52815.6 | 53196.9 | JAR | 45.04 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 31.4 | [12 empty] | RECEIVED | 80000
CHLORIDES | 23800 | 24000 | 5" HWDPS | 8.43 | STAB - 2 |  | TFA (IN²) |  | 1.33 | [12 empty] | TOTAL | 440000
CALCIUM | 220 | 220 | 6 1/2" DCS | 8.43 | NMDC | 8.43 | HSI |  | 0.6 | [12 empty] | POB
OIL % | 5.5 | 5.5 | MUD MOTOR | 8.43 | SPSA | 8.43 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 349.91 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 8.44 |  | BIT NO. 16RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 17
SOLIDS % | 28.39 | 28.48 | ON BOTTOM HRS |  | 18.71 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 11 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 42.09 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 104
DAILY WELL COST (US$) |  | 48113 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 16526458 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 91.56% | MUD CLEANER | 2 x 140 + 1 x 140 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4130 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4130 |  | 1050/1040 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4130 |  | 1250/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43351 | 43351.75 | 18 | DRL | NPT-UP | DM | CONT'D DRILLING 8 1/2'' DIRECTIONAL HOLE FROM 4141M TO 4148M IN SLIDE MODE.
43351.75 | 43351.7708 | 0.5 | DRL | NPT-UP | RW | PICK UP DRILL STRING AND P/OUT OF NEW SIDE TRACK HOLE. RIH BACK TO BTM AT 4148M.
43351.7708 | 43351.8542 | 2 | DRL | NPT-UP | DM | DRILL 8 1/2" HOLE F/4148M TO 4150M IN ROTATION MODE.
43351.8542 | 43351.9479 | 2.25 | DRL | NPT-UP | CIR | SWEPT OUT 25 BBL HI-VIS PILL & CIRCULATED TILL SHAKERS CLEAN.
43351.9479 | 43351.9583 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43351.9583 | 43352 | 1 | DRL | NPT-UP | POOH | POOH F/ 4150M TO 3912M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43352 | 43352.25 | 6 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3912M TO 1016M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D DRILLING 8 1/2'' DIRECTIONAL HOLE FROM 4141M TO 4150M IN SLIDE/ROTARY MODE, SWEPT OUT 25BBL HI-VIS, FLOW CHECKED, OK, POOH FROM 4150M TO 3912M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN BIT, P/UP & M/UP NEW PDC BIT + DIRECTIONAL BHA AND RIH TO BTM AT 4150M, RESUME DRILLING 8 1/2'' HOLE.
REMARKS |  |  | RECEIVED 1 X TRI-CONE BIT FROM SLB.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14