## DDR#263
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 263
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4151 / 4012.93 METER | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 46.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4159.5 /4019.57 METER | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 1
2018-09-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8 1/2'' |  | BIT NO. |  | 16RR1 |  | 17 | BHA No. |  |  | 39 | IN (M) |  | 4150 |  | OUT (M) |  |  | STRING (BBL) | 234
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4151 |  | SIZE (IN) |  | 8.5 |  | 8.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 624.78
DEPTH, MD (M) |  | 4151 | TVD @ 00:00HR (M) |  | 4012.93 |  | MANUFACTURER |  | HLB |  | SMITH | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.22 | 0.03013 |  | PITS (BBL) | 822
MW IN (SG) |  | 1.85 | DAILY PROGRESS (M) |  | 1 |  | TYPE |  | QH30R |  | MDSi616 | XP MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.94 | 1.0874 |  | ACT. SYS (BBL) | 1817.48
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 1.5 |  | SERIAL NO. |  | 1223562 |  | JP0206 | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.68 | 0.09313 |  | RESV. SYS (BBL) | 624
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 537 |  |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.63 | 0.22324 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | 137 | AVG. WOB (TON) |  | 4 |  | NOZZLES |  | 3 X 24 |  | 6 x 14 | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 65 | AVG. RPM SURFACE |  | 40 |  | DEPTH IN (M) |  | 4136 |  | 4150 | SPSA |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | TOTAL | 2941.48
PV |  | 39 | AVG. RPM DOWNHOLE |  | 160 |  | DEPTH OUT (M) |  | 4150 |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | DIESEL (LTR)
YIELD POINT |  | 27 | FLOWRATE (GPM) |  | 425 |  | METERAGE (M) |  | 14 |  | 1 | 1X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 0.67619 |  | RIG TANK | 89000
GEL ST. |  | 16/32 | PRESSURE (PSI) |  | 3200-3400 |  | RPM SURF. |  | 40 |  | 50 | 18 XHWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.91 | 12.2481 |  | CAMP TANK | 30250
WL (ml/30 min.) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  | 8-10 |  | RPM BTM. |  | 120 |  | 170 | D.JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CONSUMED | 6650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  | 5-6 |  | WOB (TON) |  | 4-8 |  | 2-4 | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2IF |  | 140.11 | 10.2202 |  | RECEIVED | 50000
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  | 140 |  | AVG. ROP (M/HR) |  | 0.46589 |  | 1.5152 | [11 empty] | TOTAL | 119250
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  | 155 |  | BIT ROT HRS. |  | 30.05 |  | 0.66 | [11 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 143.57 | [13 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 224.54 | [13 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 76.63 | [13 empty] | CONSUMED | 40000
KCl (mg/l) |  | 52243.6 | JAR | 0.66 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 31.4 | [13 empty] | RECEIVED | 40000
CHLORIDES |  | 24300 | 5" HWDPS | 9.09 | STAB - 2 |  | TFA (IN²) |  | 1.33 |  | 0.902 | [11 empty] | TOTAL | 440000
CALCIUM |  | 220 | 6 1/2" DCS | 9.09 | NMDC | 9.09 | HSI |  | 0.6 | [13 empty] | POB
OIL % |  | 5.5 | MUD MOTOR | 0.66 | SPSA | 9.09 | DULL CODE |  | I-O-D-L-B-G-O-R |  |  | TOTAL LENGTH (M) | [7 empty] | 351.89 |  |  | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  | 0.66 |  | BIT NO. 16RR1 |  | 2-3-FC-A-E-1-WT-BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 17
SOLIDS % |  | 28.37 | ON BOTTOM HRS |  | 0.66 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 43.75 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [12 empty] | TOTAL | 104
DAILY WELL COST (US$) |  | 59058 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [12 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 16585516 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [12 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 91.89% | MUD CLEANER | 2 x 140 + 1 x 140 |  |  | 7" LINER | [15 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" |  | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4151 |  | 800/810 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" |  | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4151 |  | 1000/1020 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" |  | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4151 |  | 1260/1270 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43352 | 43352.3021 | 7.25 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3912M TO 349M.
43352.3021 | 43352.3125 | 0.25 | DRL | NPT-UP | RW | FLOW CHECKED, WELL STATIC.
43352.3125 | 43352.4167 | 2.5 | DRL | NPT-UP | BHA | POOH FROM 349M TO SURFACE. MEANWHILE L/DOWN JAR + BIT + MUD MOTOR.
43352.4167 | 43352.5312 | 2.75 | DRL | NPT-UP | BHA | P/UP & M/UP NEW 8 1/2'' PDC BIT (SR # JP0260, 6 X 14/32'' NOZZLES)+MUD MOTOR+ S.STAB+ SPSA. ADJUSTED ABH TO 1.5°. SCRIBED TOOL FACE. SET SLIM PULSE INTO SPSA. FUNCTION TESTED MWD TOOL-OK. RECORDED SPP: 860-900 PSI @ 400 GPM. RIH AS PER BHA DOWN TO 351M.
43352.5312 | 43352.8125 | 6.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 351M TO 3299M. FILLED UP STRING EVERY 15 STANDS.
43352.8125 | 43352.8438 | 0.75 | DRL | NPT-UP | RS | SERVICED TDS.
43352.8438 | 43352.9583 | 2.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 3299M TO 4122M. WHILE RIH OBSERVED COMPRESSION AT 3930M, 3942M, 4017M, 4068M & 4082M. CLEARED ALL BY RECIPROCATION.
43352.9583 | 43352.9792 | 0.5 | DRL | NPT-UP | RW | WASHED DOWN FROM 4122M TO BTM AT 4150M.
43352.9792 | 43353 | 0.5 | DRL | NPT-UP | DM | BROKE IN THE BIT & RESUMED DRILLING, DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4150M TO 4151M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43353 | 43353.0104 | 0.25 | DRL | NPT-UP | DM | WHILE DRILLING 8 1/2'' HOLE OBSERVED DROPPING TREND IN SPP. CHECKED SURFACE SYSTEM AND FOUND PUMP # 1 MALFUNCTIONING, SWITCHED FROM MP # 1 TO MP #3.
43353.0104 | 43353.0729 | 1.5 | DRL | NPT-UP | RR | OBSERVED SAFETY VALVE POPPED OFF AT PUMP # 3, REPLACED SAME MEANWHILE CIRCULATED WITH MP # 2.
43353.0729 | 43353.1667 | 2.25 | DRL | NPT-UP | DM | CONT'D DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4151M TO 4158M IN ROTARY MODE. OBSERVED FREQUENT ROTARY STALLING.
43353.1667 | 43353.25 | 2 | DRL | NPT-UP | DM | SWITCHED OVER TO SLIDE MODE, DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4158M TO 4159.5M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' DIRECTIONAL HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH TO SURFACE, L/DOWN BIT, P/UP & M/UP NEW PDC BIT + DIRECTIONAL BHA AND RIH TO BTM AT 4150M, OBSERVED FEW COMPRESSIONS WHILE RIH, RECIPROCATED AND CLEARED SAME, RESUME DRILLING 8 1/2'' HOLE DOWN TO 4151M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE DRILLING AHEAD 8 1/2'' HOLE IN ROTARY/SLIDE MODE.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14