## DDR#264
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 264
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4183 / 4038.6 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 47.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4196.5 / 4049.1 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 32
2018-09-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 17 |  | BHA No. |  |  | 39 | IN (M) |  | 4150 |  | OUT (M) |  |  | STRING (BBL) | 234
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4183 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 632
DEPTH, MD (M) | 4169 | 4183 | TVD @ 00:00HR (M) |  | 4038.6 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.22 | 0.03013 |  | PITS (BBL) | 831
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 32 |  | TYPE |  | MDSi616 |  | XP MUD MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.94 | 1.0874 |  | ACT. SYS (BBL) | 1697
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  | 3.5 |  | SERIAL NO. |  | JP0206 |  | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.68 | 0.09313 |  | RESV. SYS (BBL) | 659
ECD (SG) | 1.92 | 1.92 | AVG. ROP (M/HR) |  | 1.716 |  | IADC CODE |  | - |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.63 | 0.22324 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 144 | 143 | AVG. WOB (TON) |  | 3 - 5 |  | NOZZLES (1/32") |  | 6 x 14 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 65 | 65 | AVG. RPM SURFACE |  | 0 - 70 |  | DEPTH IN (M) |  | 4150 |  | SPSA |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | TOTAL | 2856
PV | 40 | 38 | AVG. RPM DOWNHOLE |  | 115 - 190 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | DIESEL (LTR)
YIELD POINT | 28 | 28 | FLOWRATE (GPM) |  | 415 - 435 |  | METERAGE (M) |  | 33 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 0.67619 |  | RIG TANK | 81000
GEL ST. | 15/29 | 16/32 | PRESSURE (PSI) |  | 3000 - 3450 |  | RPM SURF. |  | 0 - 70 |  | 18 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.91 | 12.2481 |  | CAMP TANK | 29600
WL (ml/30 min.) | 3.7 | 3.9 | TORQ. ON-BTM (KLB-FT) |  | 7 - 12 |  | RPM BTM. |  | 115 - 190 |  | DRILLING JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CONSUMED | 8650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 7 - 9 |  | WOB (TON) |  | 2 - 5 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2IF |  | 140.11 | 10.2202 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 142 |  | AVG. ROP (M/HR) |  | 1.709 | [12 empty] | TOTAL | 110600
ALK (FILT.) | 0.6 | 0.5 | PICK-UP WT. (TON) |  | 155 |  | BIT ROT HRS. |  | 19.31 | [12 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 180.4 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 180.4 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 65.7 | [12 empty] | CONSUMED | 80580
KCl (mg/l) | 52434.3 | 52243.6 | JAR | 54.58 | STAB - 1 | 9.54 | JET VELOCITY (M/SEC) |  | 45.7 | [12 empty] | RECEIVED | 80580
CHLORIDES | 24200 | 24000 | 5" HWDPS | 17.97 | STAB - 2 |  | TFA (IN²) |  | 0.902 | [12 empty] | TOTAL | 440000
CALCIUM | 200 | 200 | 6 1/2" DCS | 17.97 | NMDC | 17.97 | HSI |  | 1.3 | [12 empty] | POB
OIL % | 5.5 | 5.5 | MUD MOTOR | 9.54 | SPSA | 17.97 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 351.89 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 17.97 |  | BIT NO. 17 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 19
SOLIDS % | 28.27 | 28.58 | ON BOTTOM HRS |  | 19.31 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 25.29 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 45
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4174 / 4031.5 |  | 38.51 |  | 81.92 |  |  | 4.15 |  | MWD |  | TOTAL | 103
DAILY WELL COST (US$) |  | 44508.2236 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 16630024.2957 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 92.14% | MUD CLEANER | 2 x 140 + 1 x 140 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4151 |  | 800/810 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4151 |  | 1000/1020 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4151 |  | 1260/1270 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-09-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43353 | 43353.0104 | 0.25 | DRL | NPT-UP | RR | WHILE DRILLING 8 1/2" HOLE OBSERVED DROPPING TREND IN SPP. CHECKED SURFACE SYSTEM AND FOUND PUMP # 1 MALFUNCTIONING, SWITCHED FROM MP # 1 TO MP # 3.
43353.0104 | 43353.0729 | 1.5 | DRL | NPT-UP | RR | OBSERVED SAFETY VALVE POPPED OFF AT MP # 3, REPLACED SAME MEANWHILE CIRCULATED WITH MP # 2.
43353.0729 | 43353.1667 | 2.25 | DRL | PT-UP | DM | DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4151M TO 4158M IN ROTARY MODE. OBSERVED FREQUENT ROTARY STALLING DURING DRILLING.
43353.1667 | 43353.2917 | 3 | DRL | PT-UP | DM | SWITCHED OVER TO SLIDE MODE, DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4158M TO 4160M.
43353.2917 | 43353.3958 | 2.5 | DRL | PT-UP | DM | DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4160M TO 4167M IN ROTARY MODE. OBSERVED OCCASIONAL ROTARY STALLING DURING DRILLING.
43353.3958 | 43353.8958 | 12 | DRL | PT-UP | DM | SWITCHED OVER TO SLIDE MODE, DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4167M TO 4175M.
43353.8958 | 43354 | 2.5 | DRL | PT-UP | DM | DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4175M TO 4183M IN ROTARY MODE. OBSERVED OCCASIONAL ROTARY STALLING DURING DRILLING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43354 | 43354.1875 | 4.5 | DRL | PT-UP | DM | CONT'D DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4183M TO 4195M IN ROTARY MODE. OBSERVED OCCASIONAL ROTARY STALLING DURING DRILLING. CIRCULATED FOR 10 MIN, REAMED DRILLED SECTION & RECORDED MWD SURVEY PRIOR CONNECTION.
43354.1875 | 43354.25 | 1.5 | DRL | PT-UP | DM | SWITCHED OVER TO SLIDE MODE, DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4195M TO 4196.5M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA / SANDSTONE, CLAYSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" DIRECTIONAL HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | REPLACED POPPED OFF SAFETY VALVE AT MP # 3. DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 4151M TO 4183M IN ROTARY & SLIDE MODES.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" DIRECTIONAL HOLE IN ROTARY & SLIDE MODES.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14