## DDR#267
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 266.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-01-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 266.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | TESTING DAYS: | [6 empty] | 24.0792
2020-01-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 47 |  | BHA NO. |  |  | 60 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 83.8
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 19RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 946.6
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | TC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 |  |  | PITS (BBL) | 506
MW IN (SG) | 1.58 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | SCRAPPER |  |  | 8.5 | 2.1875 |  | 4 1/2 REG |  | 1.22 |  |  | ACT. SYS (BBL) | 1536.4
MW OUT (SG) | 1.58 | 1.85 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MFDGH |  | BIT SUB |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 |  |  | RESV. SYS (BBL) | 1382
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | RL0945 |  | 15 X DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 137.89 |  |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 137 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 140 |  |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 59 | 67 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18 | [12 empty] | TOTAL | 3158.4
PV | 35 | 40 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 24 | 28 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 117108
GEL ST. | 8/14 | 9/13 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 13655
WL (ml/30 min) | 4.7 | 4.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4666
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 130763
ALK (FILT.) | 0.3/0.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 619267
MAX SHIELD % | 1.5 | 2.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 68000
KCl (%) | 3 | 3 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 89386
KCl (mg/l) | 32413.9 | 52434.3 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 163800
CHLORIDES (mg/l) | 17000 | 28000 | 3.5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 360 | 320 | 4.75" DCS |  | STAB - 3 |  | TFA (IN²) |  |  | 0.745 | [12 empty] | POB
PENETREX % | 0.8 | 1.5 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 280.42 |  |  | MPCL | 3
MAX GUARD % | 0.7 | 1.5 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 21
SOLIDS % | 27.57 | 39.8 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 19RR1 |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 7 | 5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 60213.5417 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19367356.9666 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 97.29% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43855 | 43855.1562 | 3.75 | DRL | PT-P | BHA | P/U & M/U RR 8.5" TC AND 9 5/8" CASING SCRAPPER & RIH BHA FROM SURFACE TO 280M. WHILE RIH P/U 15 X 6.5" DC & 15 X 5" HWDP.
43855.1562 | 43855.5521 | 9.5 | DRL | PT-P | RIH | RIH FROM 280M TO 4407M. WASH DOWN LAST STAND.
43855.5521 | 43855.5938 | 1 | DRL | PT-P | DC | DRILLED OUT CEMENT FROM 4407M TO 4429M. OBSERVED SOFT CEMENT @ 4407M AND HARD CEMENT @ 4426M.
43855.5938 | 43855.6875 | 2.25 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN.
43855.6875 | 43855.7083 | 0.5 | DRL | PT-P | P/T | CLOSED RAM AND P/T CEMENT PLUG @ 4000 PSI - OK.
43855.7083 | 43855.7292 | 0.5 | DRL | PT-P | CIR | CIRCULATED MEANWHILE PREPARED 1.85 SG MUD.
43855.7292 | 43855.8542 | 3 | DRL | PT-P | DISP | DISPLACED HOLE WITH 1.85 SG MUD.
43855.8542 | 43855.8646 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - OK.
43855.8646 | 43856 | 3.25 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 4429M TO 3130M. WHILE POOH SCRAPPED FROM 4400M TO 4370M INTERVAL.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43855 | 43855.2188 | 5.25 | DRL | PT-P | POOH | CONT'D POOH FROM 3130M TO 280M.
43855.2188 | 43855.2396 | 0.5 | DRL | PT-P | BHA | POOH BHA FROM 280M TO 140M.
43855.2396 | 43855.25 | 0.25 | DRL | PT-P | RS | SLIP & CUT DRILLING LINE IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | SLIP & CUT DRILLING LINE IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH WITH 8.5" TC BIT & 9 5/8" SCRAPPER. DRIILED OUT CEMENT FROM 4407M TO 4429M. CIRCULATED TO CLEAN HOLE. P/T CEMENT PLUG @ 4000 PSI. DISPLACED HOLE WITH 1.85 SG MUD. POOH FROM 4429M TO 3130M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WHIPSTOCK. SET WHIPSTOCK AND CUT WINDOW IN 9 5/8" CASING FOR SIDETRACK.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14