## DDR#269
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 269
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-01-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4391 | 4390.35 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 268.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4394.6 | 4393.95 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-01-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 61 | IN (M) |  | 4387 |  | OUT (M) |  |  | STRING (BBL) | 245
CHECK TIME | 15:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 661
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | EXPANDABLE WHIPSTOCK |  |  | 8.5 |  |  | SHEAR PIN |  | 7.39 |  |  | PITS (BBL) | 812
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | TRI-MILL |  |  | 8.5 | 2 |  | 4 1/2 IF |  | 4.19 |  |  | ACT. SYS (BBL) | 1718
MW OUT (SG) |  | 1.85 | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | HYDRAULIC RUNNING TOOL |  |  | 6.5 | 2.5 |  | 4 1/2 IF |  | 1.78 |  |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 1 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 9.29 |  |  | KILL MUD (BBL) | 240
FL TEMP. °F |  | 122 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | MULTICYCLE BYPASS VALVE |  |  | 6.75 |  |  | 4 1/2 IF |  | 1.86 |  |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 67 | 64 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | UBHO |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 0.95 |  |  | TOTAL | 3158
PV | 39 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 18 X DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 165.67 |  |  | DIESEL (LTR)
YIELD POINT | 30 | 33 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 140 |  |  | RIG TANK | 108929
GEL ST. | 9/12 | 10/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 12420
WL (ml/30 min) | 4.4 | 4.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5296
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 121349
ALK (FILT.) | 0.3/0.9 | 0.3/1.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 659971
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 85000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 49519
KCl (mg/l) | 46714.2 | 46714.2 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 139500
CHLORIDES (mg/l) | 26000 | 26000 | 5" HWDPS | 8.4 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 340 | 360 | 6.5" DCS | 8.4 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 1.5 | 1.5 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 331.13 |  |  | MPCL | 3
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 8.4 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 27
SOLIDS % | 39.88 | 39.88 | DAILY ON BOTTOM HRS |  | 6.12 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 17.26 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 115
DAILY WELL COST (US$) |  | 146051 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19551236 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 98.22% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43857 | 43857.3021 | 7.25 | DRL | PT-P | RIH | CONT'D RIH FROM 2488M TO 4386M.
43857.3021 | 43857.3854 | 2 | DRL | PT-P | RU | HELD PJSM, R/UP SLB W.LINE GEARS & TOOLS.
43857.3854 | 43857.5833 | 4.75 | DRL | PT-P | W/L | RIH GYRO TOOLS ON W.LINE. ORIENTED WHIPSTOCK TOOL FACE. POOH W.LINE TO SURFACE.
43857.5833 | 43857.6146 | 0.75 | DRL | PT-P | RD | R/DOWN GYRO TOOLS AND W.LINE GEARS.
43857.6146 | 43857.6667 | 1.25 | DRL | PT-P | OTH | M/UP TDS, OPERATED MULTI CYCLE VALVE & SET WHIPSTOCK ANCHOR @ 3800 PSI. SHEARED BREAK BOLT WITH 20 TON COMPRESSION, P/UP STRING & BROKE CONTROL LINE HOSE (PRESSURE DROPPED TO ZERO).
43857.6667 | 43858 | 8 | DRL | PT-P | MIL | MILLED 9 5/8" CASING WINDOW FROM 4387M TO ESTABLISH KICK OFF AT 4391M. PUMPED 10 BBL HV PILL INTERMITTENTLY WHILE MILLING 9 5/8'' CSG WINDOW.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43858 | 43858.25 | 6 | DRL | PT-P | MIL | CONT'D MILL DOWN 8 1/2'' RAT HOLE FROM 4391M TO 4394.6M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | MILLING DOWN 8 1/2'' RAT HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH WHIPSTOCK ASSEMBLY TO 4387M. ORIENTED AND SET WHIPSTOCK. MILLED 9 5/8'' CSG WINDOW FROM 4387M TO 4391M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE MILLING 8 1/2'' HOLE TO +/- 4395M, SWEEP OUT HI-VIS PILL TO CLEAN HOLE, FLOW CHECK, POOH TO SURFACE, CHECK & L/DOWN MILLING ASSEMBLY, P/UP NEW TC BIT + DIRECTIONAL ASSEMBLY TO RIH AND RESUME DRILLING.
REMARKS
Formulas:
MIRAJ-1 ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14