## DDR#27
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 27
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR / MOHSIN / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2082 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 26.5833
RIG REP.: |  | SARDAR NAEEM / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 2101 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 67
2018-01-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3RR1 | 3RR1 | BHA No. |  |  | 5 | IN (M) |  | 1654 |  | OUT (M) |  |  | STRING (BBL) | 116
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2082 |  | SIZE (IN) |  | 17.5 | 17.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1928
DEPTH, MD (M) | 2052 | 2082 | TVD @ 00:00HR (M) |  | 2082 |  | MANUFACTURER |  | NOV | NOV | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 848
MW IN (SG) | 1.42 | 1.45 | DAILY PROGRESS (M) |  | 67 |  | TYPE |  | TFH519 | TFH519 | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.82 | 2.9 |  | ACT. SYS (BBL) | 2892
MW OUT (SG) | 1.42 | 1.45 | INST. ROP (M/HR) |  | 3.93 |  | SERIAL NO. |  | E244694 | E244694 | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.79 | 0.2 |  | RESV. SYS (BBL) | 826
ECD (SG) | 1.4283 | 1.4583 | AVG. ROP (M/HR) |  | 3.17 |  | IADC CODE |  | S422 | S422 | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.42 | 0.8 |  | KILL MUD (BBL) | 400
FL TEMP. °F | 145.4 | 145.4 | AVG. WOB (TON) |  | 4 - 9 |  | NOZZLES |  | 5X18/32" | 5X18/32" | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) | 57 | 60 | AVG. RPM SURFACE |  | 95 - 105 |  | DEPTH IN (M) |  | 1654 | 1654 | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.43 | 2.7 |  | TOTAL | 4118
PV | 34 | 33 | AVG. RPM DOWNHOLE |  | 195 - 205 |  | DEPTH OUT (M) |  | - |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.8 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 27 | 30 | FLOWRATE (GPM) |  | 850 - 900 |  | METERAGE (M) |  | 428 |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 9.43 | 2.4 |  | RIG TANK | 108000
GEL ST. | 10/29 | 9/28 | PRESSURE (PSI) |  | 3000 - 3300 |  | RPM SURF. |  | 90 - 105 |  | 9 1/2" FILTER SUB |  |  | 9.5 | 3.875 |  | 7 5/8 REG |  | 2.45 | 0.79144 |  | CAMP TANK | 16200
WL (ml/30 min.) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  | 5 - 7 |  | RPM BTM. |  | 190 - 205 |  | 3 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.63 | 8.9256 |  | CONSUMED | 11500
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2 - 3 |  | WOB (TON) |  | 3 - 9 |  | X/OVER |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.93 | 0.30043 |  | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 117 |  | AVG. ROP (M/HR) |  | 3.2197 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.47 | 4.1243 |  | TOTAL | 124200
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 119 |  | BIT ROT HRS. |  | 132.93 |  | DRILLING JAR |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.65 | 1.2616 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 116 |  | K-REVS IN 24 HRS |  | 238 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.46 | 4.1221 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1499 |  | X/OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.95 | 0.21213 |  | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 23.51 |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.17 | 4.1809 |  | CONSUMED | 175770
KCl (mg/l) | 53387.6 | 53387.6 | JAR | 130.37 | NMDC | 130.37 | JET VELOCITY (M/SEC) |  | 65.5 | [12 empty] | RECEIVED | 125770
CHLORIDES | 25000 | 25000 | 5" HWDPS | 130.37 | STAB - 1 | 130.37 | TFA (IN²) |  | 1.24 | [12 empty] | TOTAL | 445000
CALCIUM | 160 | 120 | 8" DCS | 130.37 | STAB - 2 |  | HSI |  | 1 | [12 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS | 130.37 | SPSA | 130.37 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 164.38 |  |  | MPCL | 4
SAND % |  |  | BHA ROT. HRS |  | 130.37 |  | BIT No. 3RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 17
SOLIDS % | 13.23 | 14.76 | ON BOTTOM HRS |  | 132.93 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 149.01 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 13
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 80 | 2 X 80 |  | 20" SURFACE CASING |  |  | 594 | 1994 |  | 0.34 |  | 116.49 |  |  | 0.02 |  | MWD |  | TOTAL | 115
DAILY WELL COST (US$) |  | 63915.9692 | SHAKER-2 | 2 X 120 | 1 X 80 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 2023 |  | 0.49 |  | 85.12 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3112949.5002 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2051 |  | 0.53 |  | 99.71 |  |  | 0.15 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 17.25% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2080 |  | 0.89 |  | 89.99 |  |  | 0.39 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 295
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 2075 |  | 320 / 390 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 2075 |  | 320 / 390 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2017-12-31 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 10 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43116 | 43116.3854 | 9.25 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 2015M TO 2043M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M AND INCREASED MUD WEIGHT FROM 1.34 S.G TO 1.40 S.G.
43116.3854 | 43116.3958 | 0.25 | DRL | NPT-P | RS | SERVICED TDS.
43116.3958 | 43116.4792 | 2 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 2043M TO 2048M IN ROTARY MODE. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M. OBSERVED DRILLING BREAK.
43116.4792 | 43116.4896 | 0.25 | DRL | PT-UP | FC | P/U DRILL STRING & FLOW CHECKED - WELL STATIC.
43116.4896 | 43116.7083 | 5.25 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 2048M TO 2065M IN ROTARY MODE. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M AND INCREASED MUD WEIGHT FROM 1.40 S.G TO 1.45 S.G. OBSERVED WASH PIPE LEAKED.
43116.7083 | 43116.7188 | 0.25 | DRL | NPT-UP | POOH | POOH FROM 2065M TO 2014M. INSTALLED CIRCULATION HEAD.
43116.7188 | 43116.75 | 0.75 | DRL | NPT-UP | RR | REPLACED TDS WASH PIPE. MEANWHILE CIRCULATED THROUGH CIRCULATION HEAD.
43116.75 | 43116.7604 | 0.25 | DRL | NPT-UP | RIH | R/D CIRCULATION HEAD. RIH FROM 2014M AT 2065M.
43116.7604 | 43117 | 5.75 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 2065M TO 2082M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43117 | 43117.25 | 6 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 2082M TO 2101M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (70% CLAYSTONE & 30% SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 17 1/2" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2" HOLE SECTION FROM 2015M TO 2082M IN ROTARY MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2" HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21