## DDR#270
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 269.5833
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4382 / 4188.5 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 52.7133
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4385 / 4190.6 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 31
2018-09-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 17 |  | BHA No. |  |  | 39 | IN (M) |  | 4150 |  | OUT (M) |  |  | STRING (BBL) | 245.37
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4383 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 661.66
DEPTH, MD (M) | 4364 | 4382 | TVD @ 00:00HR (M) |  | 4166.3 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.22 | 0.03013 |  | PITS (BBL) | 903
MW IN (SG) | 1.9 | 1.9 | DAILY PROGRESS (M) |  | 31 |  | TYPE |  | MDSi616 |  | XP MUD MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.94 | 1.0874 |  | ACT. SYS (BBL) | 1810.03
MW OUT (SG) | 1.9 | 1.9 | INST. ROP (M/HR) |  | 0.53 |  | SERIAL NO. |  | JP0206 |  | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.68 | 0.09313 |  | RESV. SYS (BBL) | 700
ECD (SG) | 2.0544 | 2.0544 | AVG. ROP (M/HR) |  | 1.98 |  | IADC CODE |  | - |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.63 | 0.22324 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 150.8 | 150.8 | AVG. WOB (TON) |  | 4 - 9 |  | NOZZLES (1/32") |  | 6 x 14 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 68 | 66 | AVG. RPM SURFACE |  | 0 - 90 |  | DEPTH IN (M) |  | 4150 |  | SPSA |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | TOTAL | 3010.03
PV | 44 | 42 | AVG. RPM DOWNHOLE |  | 128 - 219 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | DIESEL (LTR)
YIELD POINT | 30 | 28 | FLOWRATE (GPM) |  | 460 |  | METERAGE (M) |  | 233 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 0.67619 |  | RIG TANK | 130000
GEL ST. | 15/33 | 14/33 | PRESSURE (PSI) |  | 3500 - 3750 |  | RPM SURF. |  | 0 - 90 |  | 18 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.91 | 12.2481 |  | CAMP TANK | 25700
WL (ml/30 min.) | 3.6 | 3.6 | TORQ. ON-BTM (KLB-FT) |  | 0 - 12 |  | RPM BTM. |  | 115 - 219 |  | DRILLING JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CONSUMED | 12650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 0 - 10 |  | WOB (TON) |  | 2 - 10 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2IF |  | 140.11 | 10.2202 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 144 |  | AVG. ROP (M/HR) |  | 1.7759 | [12 empty] | TOTAL | 155700
ALK (FILT.) | 0.7 | 0.6 | PICK-UP WT. (TON) |  | 160 |  | BIT ROT HRS. |  | 131.2 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 191.73 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 1332.02 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 82.41 | [12 empty] | CONSUMED | 91370
KCl (mg/l) | 53387.6 | 53387.6 | JAR | 133.62 | STAB - 1 | 88.58 | JET VELOCITY (M/SEC) |  | 49.6 | [12 empty] | RECEIVED | 91370
CHLORIDES | 24500 | 24800 | 5" HWDPS | 97.01 | STAB - 2 |  | TFA (IN²) |  | 0.902 | [12 empty] | TOTAL | 440000
CALCIUM | 180 | 180 | 6 1/2" DCS | 97.01 | NMDC | 97.01 | HSI |  | 1.8 | [12 empty] | POB
OIL % | 7 | 7 | MUD MOTOR | 88.58 | SPSA | 97.01 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 351.89 |  |  | MPCL | 3
LUBE % |  |  | BHA ROT. HRS |  | 97.01 |  | BIT NO. 17 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 18
SOLIDS % | 29.88 | 29.87 | ON BOTTOM HRS |  | 131.22 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 162.56 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 44
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4258 / 4097.2 |  | 39.72 |  | 77.66 |  |  | 1.34 |  | MWD |  | TOTAL | 101
DAILY WELL COST (US$) |  | 52817.39 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4285 / 4117.7 |  | 41.07 |  | 77.87 |  |  | 1.51 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 16941792.7428 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4315 / 4140.1 |  | 42.47 |  | 77.42 |  |  | 1.24 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 93.87% | MUD CLEANER | 1 x 200 + 2 x 140 |  |  | 7" LINER |  |  |  | 4342 / 4159.8 |  | 44.18 |  | 77.4 |  |  | 2.26 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4361 |  | 700/690 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4361 |  | 900/880 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4361 |  | 1050/1050 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-09-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43359 | 43359.2083 | 5 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 4351M TO 4361M IN ROTARY MODE.
43359.2083 | 43359.2917 | 2 | DRL | PT-UP | CIR | SWEPT OUT 15 BBL EACH LOW-VIS + HI-VIS TANDEM PILL. RECORDED MWD SURVEY AND CIRCULATED TILL SHAKERS CLEANED.
43359.2917 | 43359.3021 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - WELL STATIC.
43359.3021 | 43359.375 | 1.75 | DRL | PT-UP | WT | PERFORMED WIPER TRIP. POOH FROM 4361 M TO 4134M. REAM UP/DOWN SEVERAL TIMES TO CLEAR KICK-OFF POINT.
43359.375 | 43359.3958 | 0.5 | DRL | NPT-P | RS | SERVICED TDS
43359.3958 | 43359.4583 | 1.5 | DRL | PT-UP | WT | RIH TO BOTTOM AT 4361M. PRECAUTIONARY REAMED DOWN LAST STAND.
43359.4583 | 43359.875 | 10 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 4361M TO 4381M IN ROTARY MODE.
43359.875 | 43359.9167 | 1 | DRL | PT-UP | CIR | CIRCULATED & SWEPT OUT 15 BBL EACH LOW-VIS + HI-VIS TANDEM PILL.
43359.9167 | 43360 | 2 | DRL | PT-UP | DM | ADJUSTED MWD TOOL FACE & DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 4381M TO 4382M IN SLIDE MODE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43360 | 43360.2083 | 5 | DRL | PT-UP | DM | CONTINUED DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4382M TO 4385M IN SLIDE MODE.
43360.2083 | 43360.25 | 1 | DRL | PT-UP | RW | REAMED DRILLED SECTION. OBSERVED HIGH TORQUE, ROTARY STALLING AND PRESSURE CAVINGS IN TRACES.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA / SANDSTONE, CLAYSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" DIRECTIONAL HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4351M TO 4361M IN ROTARY MODE. PERFROMED WIPER TRIP TO KICK OFF POINT. DRILL AHEAD DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4361M TO 4382M IN ROTARY & SLIDE MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" DIRECTIONAL HOLE IN ROTARY & SLIDE MODES.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21