## DDR#271
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 271
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-01-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4398.4 | 4397.75 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 270.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4402 | 4401.33 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 3.8
2020-01-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 48 |  | BHA NO. |  |  | 62 | IN (M) |  | 4394.6 |  | OUT (M) |  |  | STRING (BBL) | 249
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4398.4 |  | BIT NO. |  |  | 21 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 665.5
DEPTH, MD (M) | 4394.6 | 4398.4 | TVD @ 00:00HR (M) |  | 4397.75 |  | SIZE (IN) |  |  | 8 1/2'' |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 847
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 3.8 |  | MANUFACTURER |  |  | SMITH |  | 675XP MUD MOTOR |  |  | 8.375 | 5.5 |  | 4 1/2 IF |  | 8.24 | 1.0834 |  | ACT. SYS (BBL) | 1761.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 0.58 |  | TYPE |  |  | GFS15PS |  | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.078887 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.72 |  | SERIAL NO. |  |  | RJ4606 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.53 | 0.069683 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 9 |  | IADC CODE |  |  | 447 |  | SLIM PULSE |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 9.43 | 1.2398 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 61 | 58 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18 |  | UBHO |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.1249 |  | TOTAL | 3201.5
PV | 39 | 39 | AVG. RPM DOWNHOLE |  | 112 |  | DEPTH IN (M) |  |  | 4394.6 |  | NMDC |  |  | 6.875 | 2.875 |  | 4 1/2 IF |  | 9.46 | 1.2438 |  | DIESEL (LTR)
YIELD POINT | 33 | 31 | FLOWRATE (GPM) |  | 402 |  | DEPTH OUT (M) |  |  |  |  | 3 X 6 1/2'' DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.29 | 3.588 |  | RIG TANK | 126653
GEL ST. | 10/14 | 9/12 | PRESSURE (PSI) |  | 3350 |  | METERAGE (M) |  |  | 3.8 |  | 18 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.96 | 12.3267 |  | CAMP TANK | 27000
WL (ml/30 min) | 4.8 | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.79 | 1.2872 |  | CONSUMED | 5191
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 112 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 139.95 | 10.271 |  | RECEIVED
ALK (MUD) | 0.5 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  | 4-10 | [12 empty] | TOTAL | 153653
ALK (FILT.) | 0.3/0.9 | 0.3/1.1 | PICK-UP WT. (TON) |  | 165 |  | AVG. ROP (M/HR) |  |  | 0.71563 | [12 empty] | WATER (LTR)
pH | 9.5 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | BIT ROT HRS. |  |  | 5.31 | [12 empty] | RIG STORAGE | 616388
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 35.92 | [12 empty] | CAMP STORAGE | 85000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 35.92 | [12 empty] | CONSUMED | 59480
KCl (mg/l) | 46714.2 | 49574 | JAR | 7.23 | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  | 74.6 | [12 empty] | RECEIVED | 40500
CHLORIDES (mg/l) | 26000 | 33000 | 5" HWDPS | 22.78 | STAB - 2 |  | JET VELOCITY (M/SEC) |  |  | 52.82 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 360 | 360 | 6.5" DCS | 22.78 | STAB - 3 |  | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
PENETREX % | 1.5 | 1.5 |  |  |  |  | HSI |  |  | 1.71 |  | TOTAL LENGTH (M) | [7 empty] | 374.44 |  |  | MPCL | 3
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 7.23 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 21 |  |  | MPCL SERV | 25
SOLIDS % | 39.88 | 39.62 | DAILY ON BOTTOM HRS |  | 5.31 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 6.99 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 114
DAILY WELL COST (US$) |  | 50803 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 19643612 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 98.68% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4399 | 625/645 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4399 | 800/825 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4399 | 980/1000 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43859 | 43859.0417 | 1 | DRL | PT-P | BHA | P/UP DIRECTIONAL ASSEMBLY, ADJUSTED MOTOR BEND AT 1.5˚. SCRIBED SAME WITH MWD AND UBHO.
43859.0417 | 43859.0625 | 0.5 | DRL | PT-P | E/C | SHALLOW FUNCTION TESTED MUD MOTOR & MWD TOOL @ 350 GPM, 940 PSI. OK.
43859.0625 | 43859.1146 | 1.25 | DRL | PT-P | BHA | CONT'D RIH AS PER BHA FROM 30M TO 374M. FLUSHED SAME.
43859.1146 | 43859.4896 | 9 | DRL | PT-P | RIH | RIH FROM 374M TO 4392M. FILLED UP STRING AFTER EVERY 15 STDS. (NO OBSTRUCTION OBSERVED WHILE PASSING THROUGH 9 5/8'' CSG WINDOW).
43859.4896 | 43859.7083 | 5.25 | DRL | PT-P | W/L | P/UP STRING INSIDE CSG. R/UP SLB W.LINE GEARS. RIH GYRO TOOLS ON SLB W.LINE FOR MOTOR ORIENTATION. POOH GYRO TOOLS, R/DOWN SLB W.LINE GEARS.
43859.7083 | 43859.7708 | 1.5 | DRL | PT-P | CIR | M/UP TDS, SWEPT OUT 30 BBL HV PILL AT 4394M PRIOR DRILLING.
43859.7708 | 43860 | 5.5 | DRL | PT-P | DM | COMMENCED DRILLING. DRILLED 8 1/2'' HOLE FROM 4394.6M TO 4398.4M IN SLIDE MODE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43860 | 43860.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 8 1/2'' HOLE FROM 4398.4M TO 4402M IN SLIDE/ROTARY MODE.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/ KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' DIRECTIONAL HOLE IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | ADJUSTED MOTOR BEND AT 1.5˚, SHALLOW HOLE TESTED DIRECTIONAL TOOLS,OK, RIH TO 4392M MEANWHILE FILLED UP STRING EVERY 15 STDS, RIH GYRO TOOL ON W/LINE FOR MOTOR ORIENTATION, SWEPT OUT 30 BBL HV PILL PRIOR COMMENCEMENT DRILLING, DRILLED AHEAD 8 1/2'' HOLE FROM 4394.60M TO 4398.40M IN SLIDE MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2'' HOLE IN SLIDE/ROTARY MODE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14