## DDR#273
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 272
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-22 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 55.13
RIG REP. (TP): |  | TARIQ M. BUTT / KHALID M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 18
2018-09-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 17 |  | BHA No. |  |  | 39 | IN (M) |  | 4150 |  | OUT (M) |  |  | STRING (BBL) | 132.84
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4427 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 830.24
DEPTH, MD (M) | 4445 | 4445 | TVD @ 00:00HR (M) |  | 4233.39 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.22 | 0.03013 |  | PITS (BBL) | 876
MW IN (SG) | 1.96 | 1.96 | DAILY PROGRESS (M) |  | 18 |  | TYPE |  | MDSi616 |  | XP MUD MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.94 | 1.0874 |  | ACT. SYS (BBL) | 1839.08
MW OUT (SG) | 1.96 | 1.96 | INST. ROP (M/HR) |  | 1.78 |  | SERIAL NO. |  | JP0206 |  | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.68 | 0.09313 |  | RESV. SYS (BBL) | 895
ECD (SG) | - | - | AVG. ROP (M/HR) |  | 1.73 |  | IADC CODE |  | - |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.63 | 0.22324 |  | KILL MUD (BBL) | 500
FL TEMP. °F | 149 | - | AVG. WOB (TON) |  | 4 - 8 |  | NOZZLES (1/32") |  | 6 x 14 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.62 | 0.084913 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 68 | 70 | AVG. RPM SURFACE |  | 50 - 90 |  | DEPTH IN (M) |  | 4150 |  | SPSA |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | TOTAL | 3234.08
PV | 51 | 50 | AVG. RPM DOWNHOLE |  | 178 - 219 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | DIESEL (LTR)
YIELD POINT | 30 | 29 | FLOWRATE (GPM) |  | 460 |  | METERAGE (M) |  | 277 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 0.67619 |  | RIG TANK | 96500
GEL ST. | 14/34 | 15/36 | PRESSURE (PSI) |  | 3650 - 3850 |  | RPM SURF. |  | 0 - 90 |  | 18 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.91 | 12.2481 |  | CAMP TANK | 23850
WL (ml/30 min.) | 3.6 | 3.6 | TORQ. ON-BTM (KLB-FT) |  | 8 - 12 |  | RPM BTM. |  | 115 - 219 |  | DRILLING JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71194 |  | CONSUMED | 12550
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 8 - 10 |  | WOB (TON) |  | 2 - 10 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2IF |  | 140.11 | 10.2202 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 145 |  | AVG. ROP (M/HR) |  | 1.5897 | [12 empty] | TOTAL | 120350
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  | 160 |  | BIT ROT HRS. |  | 174.25 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 125.86 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 1798.96 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 82.41 | [12 empty] | CONSUMED | 142450
KCl (mg/l) | 52434.3 | 52434.3 | JAR | 185.1 | STAB - 1 | 140.09 | JET VELOCITY (M/SEC) |  | 49.6 | [12 empty] | RECEIVED | 142450
CHLORIDES | 24500 | 24500 | 5" HWDPS | 148.49 | STAB - 2 |  | TFA (IN²) |  | 0.902 | [12 empty] | TOTAL | 440000
CALCIUM | 180 | 180 | 6 1/2" DCS | 148.49 | NMDC | 148.49 | HSI |  | 1.8 | [12 empty] | POB
OIL % | 7 | 7 | MUD MOTOR | 140.09 | SPSA | 148.49 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 351.89 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 148.49 |  | BIT NO. 17 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 18
SOLIDS % | 32.11 | 32.11 | ON BOTTOM HRS |  | 174.25 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 228.78 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4342 / 4159.8 |  | 44.18 |  | 77.4 |  |  | 2.26 |  | MWD |  | TOTAL | 104
DAILY WELL COST (US$) |  | 50555.09 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4374 / 4182.8 |  | 44.28 |  | 77.87 |  |  | 0.97 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17312935.8248 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4406 / 4205.7 |  | 44.13 |  | 77.29 |  |  | 0.4 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 95.92% | MUD CLEANER | 1 x 200 + 2 x 140 |  |  | 7" LINER |  |  |  | 4406 / 4205.7 |  | 44.92 |  | 76.74 |  |  | 1.32 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4418 |  | 800/800 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4418 |  | 1000/1000 |  | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4418 |  | 1200/1200 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-09-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43362 | 43362.4375 | 10.5 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 4427M TO 4445M IN ROTARY MODE.
43362.4375 | 43362.5417 | 2.5 | DRL | PT-UP | CS | STOPPED DRILLING AND CIRCULATED FOR GEOLOGICAL SAMPLES. OBSERVED NO CAVINGS & RECORDED MWD SURVEY PRIOR WIPER TRIP.
43362.5417 | 43362.5521 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - OK.
43362.5521 | 43362.5938 | 1 | DRL | PT-UP | POOH | POOH FROM 4445M TO 4136M (KOP POINT). BACK REAMED & PUMPED OUT, 4445 - 4391M & 4391 - 4277M INTERVALS RESPECTIVELY.
43362.5938 | 43362.6771 | 2 | DRL | PT-UP | CIR | CIRCULATED TO CLEAN HOLE & SWEPT OUT 15 BBL EACH LOW-VIS + HI-VIS TANDEM PILL. MEANWHILE REAMED KOP SEVERAL TIMES.
43362.6771 | 43362.8125 | 3.25 | DRL | PT-UP | POOH | POOH FROM 4136M TO 3335M (9 5/8" CSG WINDOW). CLEARED TIGHT SPOT AT 3990M.
43362.8125 | 43362.9062 | 2.25 | DRL | PT-UP | CIR | CIRCULATED TO CLEAN HOLE & SWEPT OUT 15 BBL EACH LOW-VIS + HI-VIS TANDEM PILL. MEANWHILE SERVICED TDS.
43362.9062 | 43362.9167 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - OK.
43362.9167 | 43363 | 2 | DRL | PT-UP | POOH | POOH FROM 3335M TO 2479M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43363 | 43363.1875 | 4.5 | DRL | PT-UP | POOH | POOH FROM 2479M TO 352M (TOP OF BHA).
43363.1875 | 43363.1979 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - OK.
43363.1979 | 43363.25 | 1.25 | DRL | PT-UP | BHA | POOH BHA FROM 352M TO 23M. L/D JAR & 1 X DC.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA / CLAYSTONE, LIMESTONE & SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH BHA.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2" DIRECTIONAL HOLE FROM 4442M TO 4445M IN ROTARY MODE. CIRCULATED FOR GEOLOGICAL SAMPLE. POOH FROM 4445M TO 2479M WITH CIRCULATIONS AT KOP AND 9 5/8" CSG WINDOW.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. PERFORM BOP P/T. AWAITING FOR GEOLOGICAL SAMPLES RESULT FOR WAY AHEAD.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21