## DDR#274
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 274
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4419.52 | 4418.85 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 273.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4419.52 | 4418.85 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-02-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 49 |  | BHA NO. |  |  | 63 | IN (M) |  | 4419.52 |  | OUT (M) | 4419.52 |  | STRING (BBL) | 50
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4419.52 |  | BIT NO. |  |  | 21RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 924.4
DEPTH, MD (M) | 4419.52 | 4419.52 | TVD @ 00:00HR (M) |  | 4418.85 |  | SIZE (IN) |  |  | 8 1/2'' |  | RR TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 789
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB (F.V) |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 1.07 | 0.14068 |  | ACT. SYS (BBL) | 1763.4
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | GFS15PS |  | ST. STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.36 | 0.17881 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | RJ4606 |  | 3 X 6 1/2'' DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.29 | 3.588 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 447 |  | 18 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.96 | 12.3267 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 59 | 61 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18 |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.79 | 1.2872 |  | TOTAL | 3203.4
PV | 36 | 35 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4419.52 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 139.95 | 10.271 |  | DIESEL (LTR)
YIELD POINT | 30 | 32 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4419.52 | [12 empty] | RIG TANK | 107293
GEL ST. | 8/15 | 8/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 24860
WL (ml/30 min) | 4.6 | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 6745
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 132153
ALK (FILT.) | 0.3/0.9 | 0.3/1.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 651862
MAX SHIELD % | 2.125 | 2.125 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 51289
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 8.97 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 110900
CHLORIDES (mg/l) | 80000 | 80000 | 5" HWDPS | 47.85 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 73500
HARDNESS (mg/l) | 340 | 340 | 6.5" DCS | 47.85 | STAB - 3 |  | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
NACL (mg/l) | 91742.4 | 91742.4 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
MAX GUARD % | 1.25 | 1.25 | DAILY BHA ROT. HRS |  | 2.01 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 19
SOLIDS % | 37.84 | 37.84 | DAILY ON BOTTOM HRS |  | 2.01 |  | BIT NO. 21RR |  |  | 1-2-WT-A-E-I-NO-BHA |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 2.08 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 103
DAILY WELL COST (US$) |  | 37221 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 19779193 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 99.36% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4399 | 625/645 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4399 | 800/825 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4399 | 980/1000 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43862 | 43862.0417 | 1 | DRL | PT-P | BHA | POOH FROM 19M TO SURFACE. MEANWHILE INSPECTED SPSA & MOTOR. RETRIEVED MWD TOOL. B/OUT & L/DOWN BIT. R/BACK MOTOR ASSEMBLY.
43862.0417 | 43862.125 | 2 | DRL | PT-P | BHA | P/UP & M/UP RR TC BIT + BIT SUB + ST. STAB. RIH AS PER BHA TO 347M. FLUSHED SAME.
43862.125 | 43862.5312 | 9.75 | DRL | PT-P | RIH | RIH FROM 347M TO 1785M. FILLED UP STRING EVERY 15 STDS.
43862.5312 | 43862.5625 | 0.75 | DRL | PT-P | RW | M/UP TDS, PRECAUTIONARY WASHED/REAMED DOWN FROM 4394M TO 4419M.
43862.5625 | 43862.6042 | 1 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD MEANWHILE RECIPROCATED STRING.
43862.6042 | 43862.7812 | 4.25 | DRL | PT-P | W/L | R/UP SLB W.LINE GEARS, RIH GYRO TOOL ON W.LINE, RECORDED SURVEY, POOH W.LINE TO SURFACE, R/DOWN SLB W.LINE GEARS.
43862.7812 | 43862.7917 | 0.25 | DRL | PT-P | POOH | POOH FROM 4419M TO 4383M (INSIDE CSG).
43862.7917 | 43862.8021 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43862.8021 | 43863 | 4.75 | DRL | PT-P | POOH | PUMPED SLUG. POOH FROM 4383M TO 1815M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43863 | 43863.1458 | 3.5 | DRL | PT-P | POOH | POOH FROM 1815M TO 347M.
43863.1458 | 43863.1562 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43863.1562 | 43863.1979 | 1 | DRL | PT-P | BHA | POOH FROM 347M TO SURFACE. MEANWHILE L/DOWN JAR , ST. STAB, BIT SUB AND BIT.
43863.1979 | 43863.25 | 1.25 | DRL | PT-P | BHA | P/UP & M/UP RR TC BIT + MUD MOTOR + FLOAT SUB + UBHO. ADJUSTED MOTOR BEND AT 1.83˚. SCRIBED SAME WITH UBHO. RIH TO 10M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH MOTOR ASSEMBLY IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH TO SURFACE, R/BACK MOTOR ASSEMBLY, RIH WITH RR TC BIT + BIT SUB + ST. STAB + SLICK BHA TO BTM AT 4419M, CIRCULATED TO CONDITION MUD, RECORDED GYRO SURVEY, FLOW CHECKED - WELL STATIC, POOH TO 1815M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH TO SURFACE, L/DOWN JAR, ST. STAB, BIT SUB AND BIT. P/UP 8 1/2'' TC BIT + DIRECTIONAL ASSEMBLY AND RIH TO BTM TO RESUME DRILLING.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14