## DDR#276
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 276
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4430 | 4429.24 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 275.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4435 | 4434.33 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 10.48
2020-02-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 50 |  | BHA NO. |  |  | 64 | IN (M) |  | 4419.52 |  | OUT (M) |  |  | STRING (BBL) | 250
CHECK TIME | 20:00 | 0:00 | MD @ 00:00HR (M) |  | 4419.52 |  | BIT NO. |  |  | 21RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 673
DEPTH, MD (M) | 4426.7 | 4419.52 | TVD @ 00:00HR (M) |  | 4418.85 |  | SIZE (IN) |  |  | 8 1/2'' |  | RR TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 876
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 10.48 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 8.375 | 5.5 |  | 4 1/2 IF |  | 8.24 | 1.0834 |  | ACT. SYS (BBL) | 1799
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  | 0.68 |  | TYPE |  |  | GFS15PS |  | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.078887 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.81 |  | SERIAL NO. |  |  | RJ4606 |  | UBHO |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.1249 |  | KILL MUD (BBL) | 240
FL TEMP. °F | 132.8 | 140 | AVG. WOB (TON) |  | 11 |  | IADC CODE |  |  | 447 |  | 24 X 5'' HWDP |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 223.64 | 16.4131 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 54 | 51 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18 |  | D.JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.79 | 1.2872 |  | TOTAL | 3239
PV | 32 | 31 | AVG. RPM DOWNHOLE |  | 117 |  | DEPTH IN (M) |  |  | 4419.52 |  | 11 X 5'' HWDP |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 102.94 | 7.5548 |  | DIESEL (LTR)
YIELD POINT | 29 | 28 | FLOWRATE (GPM) |  | 420 |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 98446
GEL ST. | 8/16 | 8/15 | PRESSURE (PSI) |  | 3140 |  | METERAGE (M) |  |  | 10.48 | [12 empty] | CAMP TANK | 23336
WL (ml/30 min) | 4.6 | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 0 | [12 empty] | CONSUMED | 5240
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 117 | [12 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  | 11 | [12 empty] | TOTAL | 121782
ALK (FILT.) | 0.3/0.9 | 0.3/1.1 | PICK-UP WT. (TON) |  | 170 |  | AVG. ROP (M/HR) |  |  | 0.8143 | [12 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 155 |  | BIT ROT HRS. |  |  | 12.87 | [12 empty] | RIG STORAGE | 653540
MAX SHIELD % | 2.125 | 2.125 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 90.35 | [12 empty] | CAMP STORAGE | 82000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 340.35 | [12 empty] | CONSUMED | 57940
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 11.97 | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  | 66 | [12 empty] | RECEIVED | 79100
CHLORIDES (mg/l) | 85000 | 96000 | 5" HWDPS | 50.85 | STAB - 2 |  | JET VELOCITY (M/SEC) |  |  | 55.17 | [12 empty] | DRL WASTE | 54000
HARDNESS (mg/l) | 340 | 340 | 6.5" DCS | 50.85 | STAB - 3 |  | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
NACL (mg/l) | 99992.4 | 118142.2 |  |  |  |  | HSI |  |  | 1.95 |  | TOTAL LENGTH (M) | [7 empty] | 346.4 |  |  | MPCL | 3
MAX GUARD % | 1.25 | 1.375 | DAILY BHA ROT. HRS |  | 3 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 17 |  |  | MPCL SERV | 19
SOLIDS % | 38.15 | 37.18 | DAILY ON BOTTOM HRS |  | 12.87 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 12 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 18 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 103
DAILY WELL COST (US$) |  | 46968 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 19861018 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 99.77% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4418 | 620/620 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4418 | 800/790 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4418 | 1050/1000 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-01-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43864 | 43864.0625 | 1.5 | DRL | NPT-P | W/L | POOH GYRO TOOL, R/DOWN SLB W.LINE GEARS.
43864.0625 | 43864.1771 | 2.75 | DRL | NPT-P | RW | M/UP TDS, WASHED/REAMED DRILLED HOLE SECTION FROM 4393M TO 4419M.
43864.1771 | 43864.25 | 1.75 | DRL | NPT-P | CIR | SWEPT OUT 30 BBL HV PILL, KEPT CIRCULATING TILL SHAKERS CLEAN.
43864.25 | 43864.4271 | 4.25 | DRL | NPT-P | W/L | R/UP SLB W.LINE GEARS, RIH GYRO TOOL FOR MOTOR ORIENTATION, POOH GYRO TOOL, R/DOWN SLB W.LINE GEARS.
43864.4271 | 43865 | 13.75 | DRL | PT-P | DM | RESUMED DRILLING. DRILLED 8 1/2'' HOLE FROM 4419.52M TO 4430M IN SLIDE MODE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43865 | 43865.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 8 1/2'' HOLE FROM 4430M TO 4435M IN SLIDE/ROTARY MODE.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' DIRECTIONAL HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | MOTOR ORIENTATION NOT SUCCESSFUL, POOH GYRO TOOL TO SURFACE, REAMED DRILLED HOLE SECTION FROM 4393M TO 4419M, R/UP W.LINE AND RIH GYRO FOR MOTOR ORIENTATION, DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4419.52M TO 4430M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE DRILL AHEAD TO +/- 4435M, GYRO SURVEY, DRILL AHEAD 8 1/2'' DIRECTIONAL HOLE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14