## DDR#277
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 277
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-22 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT S. RAO / M. AHSEN / M. MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 60.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 M (SECTION TD) | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 17RR2 |  | BHA No. |  |  | 41 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 247.8
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 673.3
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.22 | 0.03013 |  | PITS (BBL) | 994
MW IN (SG) |  | 2.05 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi616 |  | XP MUD MOTOR |  |  | 6.625 | 3.5 |  | 4 1/2 IF |  | 7.67 | 1.0505 |  | ACT. SYS (BBL) | 1915.1
MW OUT (SG) |  | 2.05 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JP0206 |  | FLOAT SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 0.49 | 0.067109 |  | RESV. SYS (BBL) | 761
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.88 | 0.25748 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3x14 + 3x16 |  | LOWER SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 70 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 |  | SPSA |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | TOTAL | 3176.1
PV |  | 54 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 4.3 | 0.58891 |  | DIESEL (LTR)
YIELD POINT |  | 30 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | RIG TANK | 98500
GEL ST. |  | 15/37 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 18 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.91 | 12.2481 |  | CAMP TANK | 26600
WL (ml/30 min.) |  | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | DRILLING JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.79 | 1.3408 |  | CONSUMED | 9000
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2IF |  | 140.11 | 10.2202 |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 125100
ALK (FILT.) |  | 0.7 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 122430
KCl (mg/l) |  | 52434.3 | JAR | 42.32 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 177430
CHLORIDES |  | 24500 | 5" HWDPS | 190.81 | STAB - 2 |  | TFA (IN²) |  | 1.04 | [12 empty] | TOTAL | 440000
CALCIUM |  | 180 | 6 1/2" DCS | 190.81 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 7 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 351.68 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 190.81 |  | BIT NO. 17RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 23
SOLIDS % |  | 35.15 | ON BOTTOM HRS |  | 0 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 22.06 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4342 / 4159.8 |  | 44.18 |  | 77.4 |  |  | 2.26 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 73461.09 | SHAKER-2 | 1 x 140 | 2 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4374 / 4182.8 |  | 44.28 |  | 77.87 |  |  | 0.97 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17509397.3073 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4406 / 4205.7 |  | 44.13 |  | 77.29 |  |  | 0.4 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 97.01% | MUD CLEANER | 1 x 200 + 2 x 140 |  |  | 7" LINER |  |  |  | 4406 / 4205.7 |  | 44.92 |  | 76.74 |  |  | 1.32 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-10-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43366 | 43366.1458 | 3.5 | DRL | PT-UP | RIH | RIH FROM 3364M TO 4270M. WHILE RIH CLEARED 3866M - 3870M INTERVAL BY REAMING.
43366.1458 | 43366.3125 | 4 | DRL | PT-UP | RW | REAMED DOWN FROM 4270M TO 4344M. HARD REAMED FROM 4344M TO 4370M WITH CONTINUOUS ROTARY STALLING.
43366.3125 | 43366.6771 | 8.75 | DRL | PT-UP | RW | VERY HARD REAMED FROM 4370M TO 4390M WITH CONTINUOUS ROTARY STALLING. WHILE REAMING SWEPT 20 BBL EACH LOW + HI VIS PILL AT 4376M. STRING STUCK AT 4386M WHILE REAMING, RELEASED STRING AFTER SEVERAL ATTEMPTS WITH JARRING UP & MAX 75 TON OVER PULL.
43366.6771 | 43366.9062 | 5.5 | DRL | PT-UP | RW | HARD REAMED DOWN FROM 4390M TO 4436M.
43366.9062 | 43367 | 2.25 | DRL | PT-UP | CIR | SWEPT 20 BBL EACH LOW + HI VIS PILL & CIRCULATED TO CLEAN HOLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43367 | 43367.0417 | 1 | DRL | PT-UP | CIR | CONT'D CIRCULATED TO CLEAN HOLE.
43367.0417 | 43367.0521 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - OK.
43367.0521 | 43367.1146 | 1.5 | DRL | PT-UP | POOH | POOH FROM 4436M TO 4200M. PRECAUTIONARY PUMPED OUT FROM 4436M TO 4333M.
43367.1146 | 43367.1562 | 1 | DRL | PT-UP | CIR | CIRCULATED BOTTOM UP.
43367.1562 | 43367.1667 | 0.25 | DRL | PT-UP | RIH | RIH FROM 4200M TO 4247M. OBSERVED COMPRESSION @ 4247M.
43367.1667 | 43367.25 | 2 | DRL | PT-UP | RW | REAMED / WASHED DOWN FROM 4247M TO 4400M & IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESAR-1 / LIMESTONE
OPERATIONS AT 06:00 HRS |  |  | REAMING DOWN IS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 3364M TO 4270M. HARD REAMED FROM 4270M TO 4436M. CIRCULATED TO CLEAN HOLE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO 4436M. CIRCULATE & CLEAN HOLE. POOH TO SURFACE. M/UP & RIH 8 1/2" PDC BIT WITH 02 X STRING STABS ROTARY BHA FOR CONDITION TRIP PRIOR RIH 7" LINER.
REMARKS
.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14