## DDR#279
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 279
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-09-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-22 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT S. RAO / M. AHSEN / M. MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 62.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 M (SECTION TD) | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 11RR4 |  | BHA No. |  |  | 42 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 244
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 678.5
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 976
MW IN (SG) |  | 2.05 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD506FX |  | BIT SUB |  |  | 6.5 | 3.5 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1898.5
MW OUT (SG) |  | 2.05 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5280230 |  | 1 X DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | RESV. SYS (BBL) | 869
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | ST. STAB |  |  | 8.125 | 2.875 |  | 4 1/2 IF |  | 1.88 | 0.25748 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 6 x OPEN |  | 1 X DC |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 68 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 |  | ST. STAB |  |  | 8.125 | 2.875 |  | 4 1/2 IF |  | 1.81 | 0.24789 |  | TOTAL | 3267.5
PV |  | 56 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 6 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 55.54 | 7.6066 |  | DIESEL (LTR)
YIELD POINT |  | 29 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | DRILLING JAR |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.79 | 0.71412 |  | RIG TANK | 125000
GEL ST. |  | 16/37 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 1 X DC |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 9.27 | 0.67619 |  | CAMP TANK | 25550
WL (ml/30 min.) |  | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 33 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 308.02 | 22.4683 |  | CONSUMED | 5550
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 40000
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 150550
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 75000
KCl (mg/l) |  | 52434.3 | JAR | 56.65 | STAB - 1 | 27 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 20000
CHLORIDES |  | 24500 | 5" HWDPS | 205.14 | STAB - 2 | 27 | TFA (IN²) | [14 empty] | TOTAL | 385000
CALCIUM |  | 180 | 6 1/2" DCS | 205.14 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 7 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 406.16 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 205.14 |  | BIT NO. 17RR2 |  | 2-4-BT-S-X-I-CT-BHA |  | BHA WT. IN MUD (TON) | [7 empty] | 25 |  |  | MPCL SERV | 21
SOLIDS % |  | 35.15 | ON BOTTOM HRS |  | 0 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 8 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 6.8 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4342 / 4159.8 |  | 44.18 |  | 77.4 |  |  | 2.26 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 35667.3733 | SHAKER-2 | 1 x 140 | 2 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4374 / 4182.8 |  | 44.28 |  | 77.87 |  |  | 0.97 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17590132.0606 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4406 / 4205.7 |  | 44.13 |  | 77.29 |  |  | 0.4 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 97.46% | MUD CLEANER | 1 x 200 + 2 x 140 |  |  | 7" LINER |  |  |  | 4406 / 4205.7 |  | 44.92 |  | 76.74 |  |  | 1.32 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-10-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43368 | 43368.1875 | 4.5 | DRL | PT-UP | POOH | POOH FROM 2508M TO 351M (TOP OF BHA).
43368.1875 | 43368.1979 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - OK.
43368.1979 | 43368.2917 | 2.25 | DRL | PT-UP | BHA | POOH BHA FROM 351M TO SURFACE. L/DOWN JAR, 1 X DC, DIRECTIONAL TOOLS & 8 1/2" BIT.
43368.2917 | 43368.375 | 2 | DRL | PT-UP | BHA | P/UP, M/UP & RIH 8 1/2" PDC RR BIT WITH ROTARY BHA & 02 X STRING STABS FROM SURFACE TO 406M.
43368.375 | 43368.5 | 3 | DRL | PT-UP | RIH | RIH FROM 406M TO 1668M. WHILE RIH FILLED UP STRING WITH MUD. OBSERVED HYDRAULIC POWER TONG DIES WORN OUT & NOT ABLE TO TORQUE UP CONNECTION PROPERLY.
43368.5 | 43368.5417 | 1 | DRL | NPT-UP | RR | WORKED ON HYDRAULIC POWER TONG, REPLACED WORN OUT TONG DIES.
43368.5417 | 43368.7917 | 6 | DRL | PT-UP | RIH | RIH FROM 1668M TO 4037M. OBSERVED OBSTRUCTION AT 4037M. WHILE RIH FILLED UP STRING WITH MUD.
43368.7917 | 43369 | 5 | DRL | PT-UP | RW | REAMED DOWN FROM 4037M TO 4359M. HARD REAMED FROM 4250M - 4266M & 4292M - 4300M INTERVALS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43369 | 43369.0833 | 2 | DRL | PT-UP | RW | HARD REAMED DOWN FROM 4359M TO 4388M. REAMED DOWN FROM 4388M TO 4436M.
43369.0833 | 43369.1667 | 2 | DRL | PT-UP | CIR | SWEPT 20 BBL EACH LOW + HI VIS PILL & CIRCULATED TO CLEAN HOLE.
43369.1667 | 43369.1771 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - OK.
43369.1771 | 43369.2292 | 1.25 | DRL | PT-UP | WT | POOH FOR WIPER TRIP FROM 4436M TO 4000M ON ELEVATORS.
43369.2292 | 43369.25 | 0.5 | DRL | PT-UP | WT | RIH FROM 4000M TO 4159M ON ELEVATORS. HOLE CONDITION GOOD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESAR-1 / LIMESTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH DIRECTIONAL BHA TO SURFACE. M/UP & RIH 8 1/2" PDC RR BIT WITH ROTARY BHA & 02 X STRING STABS FROM SURFACE TO 4037M. REAMED DOWN FROM 4037M TO 4359M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO 4436M. CIRCULATE TO CLEAN HOLE. SPOT LUBRA BEADS IN 8 1/2" OPEN HOLE SECTION. POOH TO SURFACE. RIH & CEMENT 7" LINER AS PER PROGRAM.
REMARKS |  |  | RECEIVED LUBRA BEADS YESTERDAY 0N 25-SEP-18 @ 2330 HRS.
.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14