## DDR#280
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 280
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4446.07 | 4445.33 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 279.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4446.07 | 4445.33 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0.77
2020-02-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 66 | IN (M) |  | 4445.3 |  | OUT (M) | 4446.07 |  | STRING (BBL) | 245
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 683.5
DEPTH, MD (M) | 4445 | 4446 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | 7 7/8 W.FORD RCJB |  |  | 8.375 | 3.75 |  | 4 1/2 IF |  | 1.25 | 0.16435 |  | PITS (BBL) | 793
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 1 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 9.3 | 0.6853 |  | ACT. SYS (BBL) | 1721.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | ST. STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.36 | 0.10022 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 23 X 5'' HWDP's |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 214.34 | 15.7944 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | D. JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.79 | 0.72141 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 57 | 54 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | 11 X 5'' HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 102.94 | 7.5855 |  | TOTAL | 3161.5
PV | 32 | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 28 | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 120310
GEL ST. | 8/17 | 8/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 20525
WL (ml/30 min) | 4.6 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5573
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 24000
ALK (MUD) | 0.5 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 140835
ALK (FILT.) | 0.3/0.9 | 0.4/1.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 574926
MAX SHIELD % | 2.125 | 2.125 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 85000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 60417
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 31.37 | STAB - 1 | 4.51 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 49500
CHLORIDES (mg/l) | 96000 | 96000 | 5" HWDPS | 70.25 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 340 | 340 | 6.5" DCS | 70.25 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
NACL (mg/l) | 118142.4 | 118142.4 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 338.98 |  |  | MPCL | 3
MAX GUARD % | 1.375 | 1.375 | DAILY BHA ROT. HRS |  | 2.5 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 21
SOLIDS % | 36.65 | 36.65 | DAILY ON BOTTOM HRS |  | 2.5 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 3.01 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 39765 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20038849 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 100.7% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4418 | 620/620 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4418 | 800/790 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4418 | 1050/1000 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43868 | 43868.2396 | 5.75 | DRL | NPT-UP | POOH / F | CONT'D POOH FROM 3218M TO 329M.
43868.2396 | 43868.25 | 0.25 | DRL | NPT-UP | FC/ F | FLOW CHECKED-WELL STATIC.
43868.25 | 43868.3542 | 2.5 | DRL | NPT-UP | BHA / F | POOH RCJB FROM 329M TO SURFACE. MEANWHILE L/DOWN JAR & RCJB. NO JUNK WAS FOUND IN CATCHER.
43868.3542 | 43868.4167 | 1.5 | DRL | NPT-UP | DP / F | L/DOWN 6 X 3 1/2'' DP's SGL BY SGL FROM DERRICK.
43868.4167 | 43868.5104 | 2.25 | DRL | NPT-UP | BHA / F | P/UP AND M/UP W.FORD RCJB + 5'' HWDP JT + ST. STAB. RIH AS PER BHA TO 338M. FLUSHED BHA.
43868.5104 | 43868.8438 | 8 | DRL | NPT-UP | RIH/ F | RIH RCJB FROM 338M TO 4418M. OBSERVED COMPRESSION AT 4418M.
43868.8438 | 43868.8958 | 1.25 | DRL | NPT-UP | RW / F | M/UP TDS, REAMED DOWN FROM 4418M TO BTM AT 4445.30M
43868.8958 | 43868.9167 | 0.5 | DRL | NPT-UP | RW / F | WORKED ON RCJB, CUT FORMATION FROM 4445.30M TO 4445.58M.( TO ENSURE BOTTOM)
43868.9167 | 43868.9792 | 1.5 | DRL | NPT-UP | RW / F | P/UP STRING, DROPPED BALL INSIDE STRING TO ACTIVATE REVERSE PHENOMENON OF RCJB. ACTIVATED AND CONFIRMED WITH PRESSURE INDICATION (SPP INCREASED 200-300 PSI). WORKED ON RCJB, CUT FORMATION FROM 4445.58M TO 4446.07M TO CATCH THE JUNK/CONES.
43868.9792 | 43869 | 0.5 | DRL | NPT-UP | POOH / F | P/UP STRING, TURNED OFF PUMPS. POOH FROM 4446M TO 4336M (INSIDE CSG)
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43869 | 43869.25 | 6 | DRL | NPT-UP | POOH/F | CONT'D POOH FROM 4336M TO 1288M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH TO SURFACE, L/DOWN JAR & RCJB. NO JUNK WAS FOUND IN CATCHER, P/UP AND M/UP RCJB AND RIH TO 4418M, REAMED DOWN TO BOTTOM AT 4445.30M, WORKED ON RCJB MEANWHILE CUT FORMATION DOWN TO 4446M, POOH TO 4336M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH TO SURFACE, CHECK AND RECOVER JUNK FROM RCJB, RIH WITH DIRECTIONAL BHA TO RESUME DRILLING.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14