## DDR#282
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 282
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4446.69 | 4445.83 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 281.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4446.69 | 4445.83 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0.62
2020-02-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 51 |  | BHA NO. |  |  | 68 | IN (M) |  | 4446.69 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 22 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1001
DEPTH, MD (M) | 4446.69 | 4446.69 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | CONE BUSTER MILL |  |  | 8.375 |  |  | 4 1/2 REG |  | 0.58 | 0.076257 |  | PITS (BBL) | 684
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER HUGHES |  | JUNK SUB |  |  | 7 | 2.3125 |  | 4 1/2 REG |  | 0.83 | 0.061161 |  | ACT. SYS (BBL) | 1685
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | VM-S30DX1 |  | BIT SUB (F.V) |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 1.07 | 0.078847 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5301683 |  | DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.03 | 1.1872 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 537 |  | ST. STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.36 | 0.17881 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 56 | 58 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18 |  | 7 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 64.59 | 8.4922 |  | TOTAL | 3125
PV | 31 | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4446.07 |  | D. JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.74 | 0.71773 |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4446.69 |  | 3 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.78 | 2.0471 |  | RIG TANK | 110539
GEL ST. | 8/17 | 8/17 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 9 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.86 | 6.1795 |  | CAMP TANK | 18180
WL (ml/30 min) | 4.5 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 6270
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 128719
ALK (FILT.) | 0.3/1.0 | 0.4/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 639125
MAX SHIELD % | 2.125 | 2.125 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 84000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 61308
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 6.66 | STAB - 1 | 4.5 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 146400
CHLORIDES (mg/l) | 96000 | 96000 | 5" HWDPS | 76.91 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 29000
HARDNESS (mg/l) | 340 | 340 | 6.5" DCS | 76.91 | STAB - 3 |  | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
NACL (mg/l) | 118142.4 | 118142.4 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 198.84 |  |  | MPCL | 3
MAX GUARD % | 1.375 | 1.375 | DAILY BHA ROT. HRS |  | 6.25 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 24
SOLIDS % | 36.65 | 36.65 | DAILY ON BOTTOM HRS |  | 6.25 |  | BIT NO. 22 |  |  | 3-4-BT-A-E-1/4-JD-BHA |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 7.7 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 49533 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20124764 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 101.1% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4418 | 620/620 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4418 | 800/790 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4418 | 1050/1000 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43870 | 43870.0417 | 1 | DRL | NPT-UP | RIH | CONT'D RIH FROM 4232M TO TAG COMPRESSION AT 4445.88M.
43870.0417 | 43870.1667 | 3 | DRL | NPT-UP | RW | SWEPT OUT 30 BBL HV PILL MEANWHILE REAMED DOWN FROM 4445.60M TO 4446.07M. OBSERVED FREQUENT ROTARY STALLING, PRESSURE PEAKS AND BIT BOUNCING.
43870.1667 | 43870.2083 | 1 | DRL | NPT-UP | DM | RESUMED DRILLING, DRILLED 8 1/2'' HOLE FROM 4446.07M TO 4446.50M.
43870.2083 | 43870.2708 | 1.5 | DRL | NPT-UP | POOH / S | POOH FROM 4446.5M TO 4417M, MEANWHILE RECORDED CHECKSHOT AT 4432M, 4424M, 4414M AND 4405M. RIH TO 4445M.
43870.2708 | 43870.3438 | 1.75 | DRL | NPT-UP | RW | REAMED DOWN FROM 4445M TO 4446.50M. OBSERVED FREQUENT ROTARY STALLING, PRESSURE PEAKS.
43870.3438 | 43870.3646 | 0.5 | DRL | NPT-UP | DM | RESUMED DRILLING, DRILLED 8 1/2'' HOLE FROM 4446.50M TO 4446.69M.
43870.3646 | 43870.7292 | 8.75 | DRL | NPT-UP | RIH | POOH FROM 4446.69M TO 347M (TOP OF BHA).
43870.7292 | 43870.7396 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43870.7396 | 43870.8542 | 2.75 | DRL | NPT-UP | BHA | POOH FROM 347M TO SURFACE. MEANWHILE R/BACK MUD MOTOR & STAB. L/DOWN JAR, NMDC AND TC BIT.
43870.8542 | 43870.9479 | 2.25 | DRL | NPT-UP | BHA | P/UP AND M/UP W.FORD CONE BUSTER MILL + JUNK SUB. RIH AS PER BHA TO 198M. FLUSHED SAME.
43870.9479 | 43871 | 1.25 | DRL | NPT-UP | RIH | CONT'D RIH FROM 198M TO 832M. FILLED UP STRING EVERY 15 STDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43871 | 43871.25 | 6 | DRL | NPT-UP | RIH | CONT'D RIH FROM 832M TO 3508M. FILLED UP STRING EVERY 15 STDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH WITH MILL + JUNK SUB IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO TAG COMP. AT 4445.88M, REAMED DOWN TO 4446.07M, DRILLED 8 1/2'' DOWN TO 4446.50M, POOH AND RECORDED MWD CHECKSHOT, REAMED/WASHED DOWN TO BTM AT 4446.5M. DRILLED 8 1/2'' HOLE DOWN TO 4446.69M, POOH TO SURFACE, R/BACK MUD MOTOR AND L/DOWN BIT. P/UP & M/UP JUNK MILL + JUNK SUB AND RIH TO 832M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO BTM AT 4446.69M, PUMP HV PILL AND WORK ON JUNK SUB, MILL JUNK AT BTM, CIRCULATE AND POOH TO SURFACE, RIH TO BTM WITH DIRECTIONAL BHA TO RESUME DRILLING.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14