## DDR#283
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 283
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5503.71 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4447.1 | 4446.69 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 282.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4447.1 | 4446.69 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0.41
2020-02-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 69 | IN (M) |  | 4447.1 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 996.1
DEPTH, MD (M) | 4447.1 | 4447.1 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | FLAT BTM MILL |  |  | 8.375 |  |  | 4 1/2 REG |  | 0.48 | 0.06311 |  | PITS (BBL) | 668
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | JUNK SUB |  |  | 7 | 2.3125 |  | 4 1/2 REG |  | 0.82 | 0.060425 |  | ACT. SYS (BBL) | 1664.1
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | JUNK SUB |  |  | 7 | 2.3125 |  | 4 1/2 REG |  | 0.83 | 0.061161 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | BIT SUB (F.V) |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 1.07 | 0.14068 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.03 | 1.1872 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 55 | 56 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | ST. STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.36 | 0.17881 |  | TOTAL | 3104.1
PV | 33 | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 7 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 64.59 | 8.4922 |  | DIESEL (LTR)
YIELD POINT | 25 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | D. JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.74 | 0.71773 |  | RIG TANK | 104776
GEL ST. | 8/16 | 8/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 3 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.78 | 3.6525 |  | CAMP TANK | 18545
WL (ml/30 min) | 4.5 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 9 X HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.86 | 6.1795 |  | CONSUMED | 6398
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.6 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 123321
ALK (FILT.) | 0.3/1.1 | 0.3/1.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 622748
MAX SHIELD % | 2.125 | 2.125 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 70000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 57377
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 14.06 | STAB - 1 | 11.9 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 27000
CHLORIDES (mg/l) | 96000 | 96000 | 5" HWDPS | 84.31 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 340 | 340 | 6.5" DCS | 84.31 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
NACL (mg/l) | 118142.4 | 118142.4 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 199.56 |  |  | MPCL | 3
MAX GUARD % | 1.375 | 1.375 | DAILY BHA ROT. HRS |  | 7.4 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 24
SOLIDS % | 36.65 | 36.65 | DAILY ON BOTTOM HRS |  | 2 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 7.66 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 105
DAILY WELL COST (US$) |  | 37338 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20162102 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 101.3% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4418 | 620/620 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4418 | 800/790 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-01-20 | 2020-02-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4418 | 1050/1000 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-01-12 | 2020-02-11 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43871 | 43871.3438 | 8.25 | DRL | NPT-UP | RIH | CONT'D RIH FROM 832M TO 4425M. FILLED UP STRING EVERY 15 STDS.
43871.3438 | 43871.4167 | 1.75 | DRL | NPT-UP | RW | REAMED DOWN FROM 4425M TO 4446.56M. WORKED ON JUNK SUB MEANWHILE SWEPT OUT 25 BBL HV PILL. CONT'D REAM / MILL DOWN TO 4446.69M.
43871.4167 | 43871.5 | 2 | DRL | NPT-UP | MIL | MILLED 8 1/2'' HOLE FROM 4446.69M TO 4447.10M.
43871.5 | 43871.7083 | 5 | DRL | NPT-UP | RW | P/UP STRING AND WASHED/REAMED DOWN FROM 4425M TO 4447.10M, MEANWHILE WORKED ON JUNK SUB INTERMITTENTLY. SWEPT HI- VIS.
43871.7083 | 43871.7188 | 0.25 | DRL | NPT-UP | POOH | POOH FROM 4447M TO 4367M (INSIDE CSG).
43871.7188 | 43871.7292 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43871.7292 | 43872 | 6.5 | DRL | NPT-UP | POOH | PUMPED SLUG. POOH FROM 4367M TO 1091M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43872 | 43872.0833 | 2 | DRL | NPT-UP | RIH | CONT'D POOH FROM 1091M TO 200M. (TOP OF BHA).
43872.0833 | 43872.0938 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43872.0938 | 43872.1771 | 2 | DRL | NPT-UP | BHA | POOH FROM 200M TO SURFACE. MEANWHILE L/DOWN JAR. B/OUT CONE BUSTER MILL & JUNK SUB. RECOVERED SIGNIFICANT QUANTITY OF JUNK FROM JUNK SUB.
43872.1771 | 43872.2292 | 1.25 | DRL | NPT-UP | BHA | P/UP AND M/UP 8 3/8'' FLAT BTM MILL + 7'' JUNK SUB + 7'' JUNK SUB. RIH AS PER BHA TO 228M. FLUSHED BHA.
43872.2292 | 43872.25 | 0.5 | DRL | NPT-P | RS | SLIP & CUT D.LINE IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | SLIP & CUT D.LINE IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 4425M, REAMED/ MILLED DOWN TO 4446.69M, WORKED ON JUNK SUB, MILLED 8 1/2'' HOLE FROM 4446.69M TO 4447.10M, SWEPT OUT HV PILLS, CONT'D WORK ON JUNK SUB, MEANWHILE REAMED DOWN TO BTM AT 4447.10M. CIRCULATED TO CLEAN HOLE, POOH TO 1091M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH FROM 1091M TO SURFACE, B/OUT AND L/DOWN MILL BIT + JUNK SUB, RECOVER JUNK, P/UP AND M/UP NEW TC BIT WITH PREVIOUS BHA AND RIH TO BTM, CIRCULATION, POOH.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14