## DDR#284
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 284
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-01
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-22 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / M. AHSEN / M.MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 67.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 M (SECTION TD) | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-09-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 138.4
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 842
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 921
MW IN (SG) |  | 2.05 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1901.4
MW OUT (SG) |  | 2.05 | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 426
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2827.4
PV |  | 45 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 135000
GEL ST. |  | 13/28 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 23000
WL (ml/30 min.) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 6500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 158000
ALK (FILT.) |  | 0.8 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 124960
KCl (mg/l) |  | 52434.3 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 124960
CHLORIDES |  | 24500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 180 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 7 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 7
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT NO. 11RR4 |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 29
SOLIDS % |  | 35.15 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4342 / 4159.8 |  | 44.18 |  | 77.4 |  |  | 2.26 |  | MWD |  | TOTAL | 122
DAILY WELL COST (US$) |  | 42249.6017 | SHAKER-2 | 1 x 140 | 2 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4374 / 4182.8 |  | 44.28 |  | 77.87 |  |  | 0.97 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17829976.4656 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4406 / 4205.7 |  | 44.13 |  | 77.29 |  |  | 0.4 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 98.79% | MUD CLEANER | 1 x 200 + 2 x 140 |  |  | 7" LINER |  |  |  | 4406 / 4205.7 |  | 44.92 |  | 76.74 |  |  | 1.32 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-08-29 | 2018-09-28 | NEXT BOP TEST DATE |  | 2018-10-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-09-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43373 | 43373.4792 | 11.5 | DRL | PT-P | RC | RIH 7" LINER FROM 4327M TO 4425M WITH CIRCULATION & ROTATION.
43373.4792 | 43373.5 | 0.5 | DRL | PT-P | RC | STOPPED ROTATION. SLACKED OFF LINER WEIGHT + 30 TON ON SHOE. OBSERVED NO DROP IN HOOK LOAD. CONFIRMED BOTTOM HOLDING.
43373.5 | 43373.5312 | 0.75 | DRL | PT-P | RU | P/U CEMENTING HEAD WITH PRE-LOADED DP DART. DROPPED BALL INSIDE STRING & M/UP CEMENT HEAD.
43373.5312 | 43373.5625 | 0.75 | DRL | PT-P | CIR | CHASED BALL WITH MUD @ 3 BPM. OBSERVED PRESSURE INCREASED FROM 600 PSI TO 2400 PSI AFTER PUMPING 148 BBL MUD. STOPPED MUD PUMP.
43373.5625 | 43373.5833 | 0.5 | DRL | PT-P | RC | HELD PRESSURE FOR 10 MINUTES. BLED OFF TO 400 PSI. SLACKED OFF STRING. OBSERVED LINER HANGER SLIPS BITE & HOLDING. APPLIED LINER WEIGHT + 30 TON WEIGHT ON SLIPS FOR 10 MINUTES. FOUND LINER HANGER SLIPS HOLDING. INCREASED SPP TO 2400 PSI TO RELEASE SETTING TOOL. HELD PRESSURE FOR 10 MINUTES. P/U STRING. OBSERVED FREE STRING MOVING @ 115 TON HOOK LOAD. CONFIRMED SETTING TOOL RELEASED. RECORDED 2000 FT-LB TORQUE @ 10 RPM. SLACKED OFF 15 TON ON LINER HANGER. HOOK LOAD = 100 TONS. LINER TOP @ 3229M & LINER SHOE @ 4425 M.
43373.5833 | 43373.6667 | 2 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE STARTED PREPARING MIX FLUID AND HOOKED UP SLB CEMENT PUMP & RIG PUMP TO CEMENT HEAD.
43373.6667 | 43373.7083 | 1 | DRL | PT-P | RC | DURING CIRCULATION OBSERVED CIRCULATION PRESSURE SUDDENLY DROPPED FROM 1600 PSI TO 1100 PSI & HOOK LOAD INCREASED FROM 100 TON TO 115 TON. ASSUMED LINER HANGER SLIPPED DOWN. P/UP 5" DP JOINT & TAGGED LINER TOP 9M DEEPER.
43373.7083 | 43373.7292 | 0.5 | DRL | PT-P | RD | L/D CEMENT HEAD & CEMENT LINES.
43373.7292 | 43373.7396 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - OK.
43373.7396 | 43373.7604 | 0.5 | DRL | PT-P | POOH | POOH LINER HANGER SETTING TOOL TO 3155M.
43373.7604 | 43373.7812 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43373.7812 | 43373.8438 | 1.5 | DRL | NPT-P | RS | SLIPPED & CUT 37M DRILLING LINE. CALIBRATED ACS + CROWN-O-MATIC + HOOK LOAD SENSORS.
43373.8438 | 43374 | 3.75 | DRL | PT-P | POOH | POOH FROM 3155M TO 1320M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43373 | 43373.1458 | 3.5 | DRL | PT-P | POOH | CONT'D POOH LINER HANGER SETTING TOOL FROM 1320M TO SURFACE & L/D SETTING TOOL + LINER WIPER PLUG.
43373.1458 | 43373.25 | 2.5 | DRL | PT-P | DP | RIH 3 1/2" DPS FROM SURFACE TO 334M FOR M/U STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESAR-1 / LIMESTONE
OPERATIONS AT 06:00 HRS |  |  | M/U 3 1/2" DP STANDS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH 7" LINER FROM 4327M TO 4425M WITH CIRCULATION & ROTATION. SET 7" LINER AT 4425M. DURING CIRCULATION FOR MUD CONDITIONING, CIRCULATION PRESSURE DROPPED & HOOK LOAD INCREASED. ASSUMED LINER HANGER SLIPPED DOWN. TAGGED LINER TOP 9M DEEPER. POOH LINER HANGER SETTING TOOL TO 1320M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | M/U 3 1/2" DP STANDS. PERFORM REMEDIAL CEMENT JOB.
REMARKS |  |  | RELEASED W.F TRS CREW & EQUIPMENT YESTERDAY ON 30-SEP-18 AND W.F LINER HANGER ENGINEER TODAY ON 1-OCT-18.
Formulas:
DHARIAN-1-ST-2 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14