## DDR#286
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 286
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / MASOOD / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4464 | 4463.28 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 285.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4467.1 | 4466.38 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 16.29
2020-02-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 52 |  | BHA NO. |  |  | 70 | IN (M) |  | 4447.2 |  | OUT (M) |  |  | STRING (BBL) | 254
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4464 |  | BIT NO. |  |  | 23 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 674.4
DEPTH, MD (M) | 4459 | 4464 | TVD @ 00:00HR (M) |  | 4463.28 |  | SIZE (IN) |  |  | 8.5'' |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 | 0.03287 |  | PITS (BBL) | 710
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 16.29 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 6.75 | 5 |  | 4 1/2 IF |  | 8.19 | 0.60351 |  | ACT. SYS (BBL) | 1638.4
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  | 0.62 |  | TYPE |  |  | SB537 |  | FLOAT SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.044213 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.86 |  | SERIAL NO. |  |  | RK1746 |  | ST. STAB |  |  | 8.25 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18407 |  | KILL MUD (BBL) | 240
FL TEMP. °F | 134.6 | 143.6 | AVG. WOB (TON) |  | 8.5 |  | IADC CODE |  |  | 537 |  | L.SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.53 | 0.069683 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 56 | 52 | AVG. RPM SURFACE |  | 0 |  | NOZZLES (1/32") |  |  | 3 X 18 |  | SPSA (MWD) |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2425 |  | TOTAL | 3078.4
PV | 32 | 32 | AVG. RPM DOWNHOLE |  | 117 |  | DEPTH IN (M) |  |  | 4447.2 |  | UBHO |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.1249 |  | DIESEL (LTR)
YIELD POINT | 27 | 25 | FLOWRATE (GPM) |  | 420 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 6.875 | 2.875 |  | 4 1/2 IF |  | 9.46 | 0.69709 |  | RIG TANK | 129477
GEL ST. | 8/17 | 8/16 | PRESSURE (PSI) |  | 3200-3250 |  | METERAGE (M) |  |  | 16.8 |  | 3 X 6.5'' DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.29 | 3.588 |  | CAMP TANK | 24634
WL (ml/30 min) | 4.6 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 18 X 5'' HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.5 | 12.3428 |  | CONSUMED | 6585
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 117 |  | D. JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.74 | 0.71773 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 158 |  | WOB (TON) |  |  | 8-10 |  | 12 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.36 | 8.2796 |  | TOTAL | 154111
ALK (FILT.) | 0.3/0.9 | 0.3/1.1 | PICK-UP WT. (TON) |  | 165 |  | AVG. ROP (M/HR) |  |  | 0.84635 | [12 empty] | WATER (LTR)
pH | 9.5 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | BIT ROT HRS. |  |  | 19.85 | [12 empty] | RIG STORAGE | 548018
MAX SHIELD % | 1.875 | 1.875 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 133.46 | [12 empty] | CAMP STORAGE | 55000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 133.46 | [12 empty] | CONSUMED | 79884
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 19.52 | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  | 75.6 | [12 empty] | RECEIVED | 26000
CHLORIDES (mg/l) | 95000 | 96000 | 5" HWDPS | 89.77 | STAB - 2 | 2.96 | JET VELOCITY (M/SEC) |  |  | 55.17 | [12 empty] | DRL WASTE | 105000
HARDNESS (mg/l) | 340 | 320 | 6.5" DCS | 89.77 | STAB - 3 |  | TFA (IN²) |  |  | 0.745 | [12 empty] | POB
NACL (mg/l) | 116492.4 | 118142.4 |  |  |  |  | HSI |  |  | 1.95 |  | TOTAL LENGTH (M) | [7 empty] | 347.72 |  |  | MPCL | 3
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 19 |  |  | MPCL SERV | 23
SOLIDS % | 36.65 | 36.65 | DAILY ON BOTTOM HRS |  | 19.85 |  | BIT NO. 23 |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 19.8 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 48860 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20283556 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 101.9% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4446 | 590/550 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4446 | 730/670 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4446 | 920/900 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2020-02-12 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 7 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43874 | 43874.1667 | 4 | DRL | PT-P | W/L | RIH GYRO TOOL FOR MOTOR ORIENTATION, POOH GYRO TOOL, R/DOWN SLB W/LINE GEARS.
43874.1667 | 43875 | 20 | DRL | PT-P | DM | RESUMED DRILLING, DRILLED 8 1/2'' HOLE FROM 4447.71M TO 4464M IN SLIDE MODE. MEANWHILE RECORDED CHECKSHOT AT 4444M & 4450M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43875 | 43875.0938 | 2.25 | DRL | PT-P | DM | DRILLED 8 1/2'' HOLE FROM 4464M TO 4465M IN SLIDE MODE.
43875.0938 | 43875.125 | 0.75 | DRL | PT-P | RW | WASHED/REAMED & CLEARED DRILLED SECTION.
43875.125 | 43875.2188 | 2.25 | DRL | PT-P | DM | RESUMED DRILLING IN ROTARY MODE FROM 4465M TO 4467M.
43875.2188 | 43875.25 | 0.75 | DRL | PT-P | RW | WASHED/REAMED & CLEARED DRILLED SECTION. RECORDED CHECKSHOT AT 4453M. OBSERVED BUILDING TREND.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | R/UP SLB W/LINE, RIH GYRO TOOL FOR MOTOR ORIENTATION, RECORD GYRO SURVEY, POOH GYRO TOOL, R/DOWN SLB W/LINE, DRILL AHEAD 8 1/2'' DIRECTIONAL HOLE IN SLIDE MODE FROM 4447.71M TO 4464M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2'' HOLE IN SLIDE / ROTARY MODE DOWN TO +/- 4467M, RECORD CHECKSHOT SURVEY, POOH TO SURFACE FOR BHA/BIT CHANGE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14