## DDR#287
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 287
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / M. AHSEN / M.MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 70.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 M (SECTION TD) | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 15RR2 |  | BHA No. |  |  | 42 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 900.2
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 | 0.034239 |  | PITS (BBL) | 802
MW IN (SG) |  | 2 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137 |  | BIT SUB (F.V) |  |  | 6.5 | 3.5 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1702.2
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RJ2167 |  | 6 X DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 55.54 | 7.6066 |  | RESV. SYS (BBL) | 572
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 | [12 empty] | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x OPEN | [12 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 57 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 | [12 empty] | TOTAL | 2774.2
PV |  | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 21 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 123500
GEL ST. |  | 14/24 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 21500
WL (ml/30 min.) |  | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 145000
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 35000
KCl (mg/l) |  | 52434.3 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 35000
CHLORIDES |  | 24500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 390000
CALCIUM |  | 180 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 6 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 56.86 |  |  | MPCL | 5
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 6 |  |  | MPCL SERV | 17
SOLIDS % |  | 36.15 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 7.5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 109
DAILY WELL COST (US$) |  | 35881.3025 | SHAKER-2 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 18097895.768 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4445 (TOL @ 3249) | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 100.3% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-08-29 | 2018-09-28 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-10-01 | 2018-10-31 | NEXT BOP TEST DATE |  | 2018-10-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43376 | 43376.2292 | 5.5 | DRL | PT-UP | RIH | RIH W.F RETRIEVEABLE PBR PACK-OFF ASSY ON 5" DPS FROM 1600M TO 3236M.
43376.2292 | 43376.25 | 0.5 | DRL | PT-UP | RIH | M/UP TDS, RIH WITH SLOW CIRCULATION, INSERTED PACK-OFF ASSY INSIDE PBR (CONFIRMED WITH SPP INCREASE) & TAGGED TOP OF LINER @ 3249M (LINER SHOE @ 4445M).
43376.25 | 43376.3125 | 1.5 | DRL | PT-UP | RU | INSTALLED W.F CEMENT HEAD (PRE-LOADED WITH DP DART) & SPACED OUT AS PER TALLY. R/UP SLB CEMENT LINES.
43376.3125 | 43376.4375 | 3 | DRL | PT-UP | CIR | CIRCULATED FOR ONE CYCLE TO CONDITION MUD. MEANWHILE PREPARED MIX FLUID FOR CEMENT SLURRIES.
43376.4375 | 43376.4583 | 0.5 | DRL | PT-UP | P/T | HELD PJSM. P/TESTED CMT HOOK UP @ 500 PSI FOR 04 MIN & 5000 PSI FOR 08 MIN - OK. MIXED RETARDER IN MIX FLUID.
43376.4583 | 43376.5312 | 1.75 | DRL | PT-UP | CIR | CIRCULATED TO HOMOGINIZE MUD. PUMPED 120 BBL MUDPUSH II SPACER OF 17.5 PPG WITH RIG PUMP @ 5 BPM. MEANWHILE WEIGHTED UP CMT SLURRIES.
43376.5312 | 43376.625 | 2.25 | DRL | PT-UP | CMC | CARRIED OUT LINER CMT JOB AS PER PROGRAM. SWITCHED OVER TO CMT UNIT & PUMPED 10 BBL MUDPUSH II SPACER OF 17.5 PPG @ 5 BPM, FOLLOWED BY 50 BBL LEAD SLURRY OF 18 PPG @ 5BPM, FOLLOWED BY 50 BBL TAIL SLURRY OF 18.5 PPG @ 5BPM. DISPLACED CMT WITH 10 BBL SPACER + 120 BBL MUD + 20 BBL SPACER + 168.5 BBL MUD (TOTAL DISPLACEMENT = 318.5 BBL) THRU CMT PUMPING UNIT @ 5BPM. DURING DISPLACEMENT LINER WIPER PLUG SHEARED AT 2500 PSI. BUMPED PLUGS @ 1300 PUMPING PRESS. INCREASED & HELD PRESS TO 2500 PSI FOR 10 MINUTES, FOUND NO PRESS DROP. BLED OFF PRESS, OBSERVED NO BACK FLOW & FOUND FLOATS HOLDING. APPLIED 35 TON COMPRESSION & SET 7" LINER TOP PACKER, FOUND NO INDICATION OF PACKER SETTING AT SURFACE.
43376.625 | 43376.6458 | 0.5 | DRL | PT-UP | RD | L/DOWN CEMENT HEAD. P/BACK PBR PACK-OFF ASSY TO 3165M.
43376.6458 | 43376.6875 | 1 | DRL | PT-UP | CIR | M/UP TDS & CIRCULATED FOR BTM UP. DUMPED 40 BBL SPACER & 55 BBL SPACER CONTAMINATED MUD ON BTM UP.
43376.6875 | 43376.6979 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED & PUMPED SLUG.
43376.6979 | 43377 | 7.25 | DRL | PT-UP | POOH | POOH FROM 3165M 30M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43377 | 43377.0208 | 0.5 | DRL | PT-UP | POOH | CONT'D POOH FROM 30M TO SURFACE & L/DOWN PBR PACK-OFF ASSY.
43377.0208 | 43377.0417 | 0.5 | DRL | PT-P | BHA | M/UP & RIH USED 8 1/2" TRICONE BIT (15RR2) WITH SLICK BHA TO 56M.
43377.0417 | 43377.25 | 5 | DRL | PT-P | RIH | RIH FROM 56M TO 2213M. WHILE RIH FILLED UP STRING WITH MUD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESAR-1 / LIMESTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 8 1/2" BIT
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH W.F RETRIEVEABLE PBR PACK-OFF ASSY ON 5" DPS FROM 1600M TO 3236M. RIH WITH SLOW CIRCULATION & INSERTED PACK-OFF ASSY INSIDE PBR. RESUMED CIRCULATION THRU 7" LINER SHOE & CONDITIONED MUD. PERFORMED 7" LINER CMT JOB AS PER PROGRAM & SET LINER TOP PACKER. P/BACK PBR PACK-OFF ASSY TO 3165M. CIRCULATED FOR BTM UP & DUMPED SPACER & SPACER CONTAMINATED MUD. POOH FROM 3165M TO 30M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 8 1/2" BIT WITH SLICK BHA TO TAG/CLEAR TOP OF 7" LINER. CIRCULATE & POOH TO SURFACE. L/DOWN 5" G-105 DPS WHILE POOH.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14