## DDR#287
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 287
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4467.1 | 4466.38 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 286.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4467.1 | 4466.38 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 3.1
2020-02-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 53 |  | BHA NO. |  |  | 71 | IN (M) |  | 4467.1 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4467.1 |  | BIT NO. |  |  | 24 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 992
DEPTH, MD (M) | 4467.1 | 4467.1 | TVD @ 00:00HR (M) |  | 4466.38 |  | SIZE (IN) |  |  | 8.5'' |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 648
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 3.1 |  | MANUFACTURER |  |  | BAKER |  | MUD MOTOR |  |  | 6.75 | 5 |  | 4 1/2 IF |  | 8.19 | 0.60351 |  | ACT. SYS (BBL) | 1640
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | VM-S30DX1 |  | FLOAT SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.044213 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.69 |  | SERIAL NO. |  |  | 5295494 |  | ST. STAB |  |  | 8.25 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18407 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 9 |  | IADC CODE |  |  | 537 |  | L.SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.53 | 0.069683 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 53 | 54 | AVG. RPM SURFACE |  | 40 |  | NOZZLES (1/32") |  |  | 3 X 16 |  | SPSA (MWD) |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2425 |  | TOTAL | 3080
PV | 32 | 32 | AVG. RPM DOWNHOLE |  | 117 |  | DEPTH IN (M) |  |  | 4467.1 |  | UBHO |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.1249 |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  | 420 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 6.875 | 2.875 |  | 4 1/2 IF |  | 9.46 | 0.69709 |  | RIG TANK | 122937
GEL ST. | 8/15 | 8/16 | PRESSURE (PSI) |  | 3300-3350 |  | METERAGE (M) |  |  |  |  | 3 X 6.5'' DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.29 | 3.588 |  | CAMP TANK | 24026
WL (ml/30 min) | 4.5 | 4.5 | TORQ. ON-BTM (KLB-FT) |  | 3 |  | RPM SURF. |  |  |  |  | 18 X 5'' HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.5 | 12.3428 |  | CONSUMED | 7148
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | D. JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.74 | 0.71773 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | 12 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.36 | 8.2796 |  | TOTAL | 146963
ALK (FILT.) | 0.3/1 | 0.3/1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 655253
MAX SHIELD % | 1.875 | 1.875 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 50000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 57846
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 23.02 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 166900
CHLORIDES (mg/l) | 96000 | 96000 | 5" HWDPS | 93.27 | STAB - 2 | 6.46 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 87000
HARDNESS (mg/l) | 320 | 320 | 6.5" DCS | 93.27 | STAB - 3 |  | TFA (IN²) |  |  | 0.589 | [12 empty] | POB
NACL (mg/l) | 118142.4 | 118142.4 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 347.71 |  |  | MPCL | 3
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 3.5 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 19 |  |  | MPCL SERV | 22
SOLIDS % | 36.02 | 36.02 | DAILY ON BOTTOM HRS |  | 4.36 |  | BIT NO. 23 |  |  | 4-3-LT/BT-A-E-1/16''-WT-BHA |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 6.35 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 51503 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20335059 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 102.2% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4446 | 590/550 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4446 | 730/670 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4446 | 920/900 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43875 | 43875.0938 | 2.25 | DRL | PT-P | DM | DRILLED 8 1/2'' HOLE FROM 4464M TO 4465M IN SLIDE MODE.
43875.0938 | 43875.125 | 0.75 | DRL | PT-P | RW | WASHED/REAMED & CLEARED DRILLED SECTION.
43875.125 | 43875.2188 | 2.25 | DRL | PT-P | DM | RESUMED DRILLING IN ROTARY MODE FROM 4465M TO 4467M.
43875.2188 | 43875.2604 | 1 | DRL | PT-P | RW | WASHED/REAMED & CLEARED DRILLED SECTION. RECORDED CHECKSHOT AT 4453M. OBSERVED BUILDING TREND.
43875.2604 | 43875.2812 | 0.5 | DRL | PT-P | POOH | POOH TO 4369 M.
43875.2812 | 43875.2917 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC.
43875.2917 | 43875.6354 | 8.25 | DRL | PT-P | POOH | PUMPED SLUG & POOH UP TO BHA. 347M.
43875.6354 | 43875.6458 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC.
43875.6458 | 43875.7292 | 2 | DRL | PT-P | BHA | POOH TO SURFACE. L/DOWN NMDC. RACKED BACK M.MOTOR & SPSA. L/DOWN BIT.
43875.7292 | 43875.8125 | 2 | DRL | PT-P | BHA | P/UP & M/UP NEW TC BIT (BAKER, VM-S30, 3 X 16) + MUD MOTOR + FLOAT SUB + ST. STAB + SPSA + UBHO. CHECKED MOTOR BEND AT 1.50˚. SCRIBED MOTOR BEND WITH MWD + UBHO. RIH TO 30M.
43875.8125 | 43875.8333 | 0.5 | DRL | PT-P | E / C | SHALLOW TESTED SLB DIRECTIONAL TOOLS AT 400 GPM, 1100 PSI.
43875.8333 | 43875.8854 | 1.25 | DRL | PT-P | BHA | RIH AS PER BHA TO 347M. FLUSHED BHA.
43875.8854 | 43876 | 2.75 | DRL | PT-P | RIH | RIH FROM 347M TO 1526M. FILLED UP STRING EVERY 15 STD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43876 | 43876.25 | 6 | DRL | PT-P | RIH | RIH FROM 1526M TO 4316M. FILLED UP STRING EVERY 15 STD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH WITH DIRECTIONAL BHA IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2'' HOLE IN SLIDE / ROTARY MODE DOWN TO 4467M, RECORDED CHECKSHOT SURVEY, OBSERVED BUILDING TREND, POOH TO SURFACE. R/BACK MUD MOTOR, P/UP AND M/UP NEW TC BIT + DIRECTIONAL BHA, RIH TO 1526M. FILLED UP STRING EVERY 15 STDS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO BTM AT 4467M, PRECAUTIONARY WASH DOWN LAST STD, CIRCULATE PRIOR GYRO RUN, R/UP W/LINE, RECORD GYRO SURVEY FOR MOTOR ORIENTATION, DRILL AHEAD 8 1/2'' HOLE IN SLIDE/ ROTARY MODE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14