## DDR#288
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 288
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / M. AHSEN / M.MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 71.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 900.2
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 751
MW IN (SG) |  | 2 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1651.2
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 572
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2723.2
PV |  | 43 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 21 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 118000
GEL ST. |  | 14/22 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 21000
WL (ml/30 min.) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 6000
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 139000
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 86350
KCl (mg/l) |  | 52434.3 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 136350
CHLORIDES |  | 24500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 180 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 6
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT NO. 15RR2 |  | 2-3-FC-C3-E-I-NO-BHA |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 17
SOLIDS % |  | 34.11 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 7.5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 109
DAILY WELL COST (US$) |  | 38423.7317 | SHAKER-2 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 18136319.4996 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4445 (TOL @ 3253) | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 100.5% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-09-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 2 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43377 | 43377.0208 | 0.5 | DRL | PT-UP | POOH | POOH PBR PACK-OFF ASSY FROM 30M TO SURFACE & L/DOWN THE SAME.
43377.0208 | 43377.0417 | 0.5 | DRL | PT-P | BHA | M/UP & RIH USED 8 1/2" TRICONE BIT (15RR2) WITH SLICK BHA TO 56M.
43377.0417 | 43377.3542 | 7.5 | DRL | PT-P | RIH | RIH FROM 56M TO 3165M. WHILE RIH FILLED UP STRING WITH MUD.
43377.3542 | 43377.3958 | 1 | DRL | PT-P | RW | M/UP TDS & WASHED DOWN FROM 3165M TO 3245M. RIH DOWN HESITANTLY WITH CIRCULATION, TAGGED & CONFIRMED TOP OF 7" LINER @ 3253M.
43377.3958 | 43377.4583 | 1.5 | DRL | PT-P | CIR | CIRCULATED AT TOP OF LINER & OBSERVED SOFT CMT CUTTINGS ON BTM UP.
43377.4583 | 43377.6667 | 5 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 3253M TO 1156M. WHILE POOH R/BACK 13 X 5" G-105 DP STANDS & L/DOWN 32 X 5" G-105 DP JOINTS SINGLE BY SINGLE.
43377.6667 | 43377.6875 | 0.5 | DRL | PT-P | DRI | CONDUCTED FIRE DRILL @ RIG SITE, FOUND GOOD RESPONSE.
43377.6875 | 43377.9271 | 5.75 | DRL | PT-P | POOH | POOH FROM 1156M TO 56M. WHILE POOH L/DOWN 115 X 5" G-105 DP JOINTS SINGLE BY SINGLE.
43377.9271 | 43377.9792 | 1.25 | DRL | PT-P | BHA | POOH FROM 56M TO SURFACE. WHILE POOH L/DOWN 6 X 6 1/2" DC JOINTS, BIT SUB & BIT. L/DOWN 3 X 6 1/2" DC JOINTS FROM DERRICK.
43377.9792 | 43378 | 0.5 | DRL | PT-P | WB | HELD PJSM. RETRIEVED WEAR BUSHING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43378 | 43378.25 | 6 | DRL | PT-P | BOPT | M/UP TEST PLUG ASSY WITH 5" DP & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (2 7/8" - 5"), LOWER 5" PIPE RAM BOP, TDS HYDRAULIC IBOP, TDS MANUAL IBOP, 4 1/2 IF FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE @ 300/8000 PSI FOR 5/10 MIN - OK. RETRIEVED & L/DOWN 5" DP TEST PLUG ASSY, M/UP TEST PLUG ASSY WITH 3 1/2" DP & SET TEST PLUG INSIDE 11" THS. P/TESTED ANNULAR BOP @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (2 7/8" - 5"), 3 1/2 IF FOSV, CHOKE MANIFOLD MASTER VALVE, CO-FLEX HOSE & BLIND / SHEAR RAM BOP @ 300/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG, SET WEAR BUSHING & L/DOWN TEST PLUG ASSY.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | PREPARING TO RIH 6" TRICONE BIT WITH SLICK BHA
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH PBR PACK-OFF ASSY FROM 30M TO SURFACE & L/DOWN THE SAME. M/UP & RIH 8 1/2" TRICONE BIT (15RR2) WITH SLICK BHA & TAGGED TOP OF 7" LINER @ 3253M, CIRCULATED & CLEARED TOL. POOH TO SURFACE. WHILE POOH L/DOWN 5" G-105 DPS & 6 1/2" DCS. RETRIEVED WEAR BUSHING FOR P/TEST BOP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | M/UP & RIH 6" TRICONE BIT WITH SLICK BHA TO +/- 500M. REPLACE CROWN BLOCK FAST SHEAVE. CONTINUE RIH 6" BIT & DRILL OUT FLOATS & SHOE TRACK CEMENT.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14