## DDR#288
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 288
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4471 | 4470.27 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 287.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4472.8 | 4472.05 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 3.9
2020-02-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 53 |  | BHA NO. |  |  | 71 | IN (M) |  | 4467.1 |  | OUT (M) |  |  | STRING (BBL) | 254
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4471 |  | BIT NO. |  |  | 24 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 675.9
DEPTH, MD (M) | 4467.1 | 4471 | TVD @ 00:00HR (M) |  | 4470.27 |  | SIZE (IN) |  |  | 8.5'' |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 709
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 3.9 |  | MANUFACTURER |  |  | BAKER |  | MUD MOTOR |  |  | 6.75 | 5 |  | 4 1/2 IF |  | 8.19 | 0.60351 |  | ACT. SYS (BBL) | 1638.9
MW OUT (SG) |  | 1.85 | INST. ROP (M/HR) |  | 0.55 |  | TYPE |  |  | VM-S30DX1 |  | FLOAT SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.044213 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.8 |  | SERIAL NO. |  |  | 5295494 |  | ST. STAB |  |  | 8.25 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18407 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  | 150 | AVG. WOB (TON) |  | 8.5 |  | IADC CODE |  |  | 537 |  | L.SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.53 | 0.069683 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 55 | 52 | AVG. RPM SURFACE |  | 0 |  | NOZZLES (1/32") |  |  | 3 X 16 |  | SPSA (MWD) |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2425 |  | TOTAL | 3078.9
PV | 32 | 31 | AVG. RPM DOWNHOLE |  | 116 |  | DEPTH IN (M) |  |  | 4467.1 |  | UBHO |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.1249 |  | DIESEL (LTR)
YIELD POINT | 24 | 24 | FLOWRATE (GPM) |  | 412 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 6.875 | 2.875 |  | 4 1/2 IF |  | 9.46 | 0.69709 |  | RIG TANK | 117833
GEL ST. | 8/15 | 7/14 | PRESSURE (PSI) |  | 3300-3400 |  | METERAGE (M) |  |  | 4 |  | 3 X 6.5'' DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.29 | 3.588 |  | CAMP TANK | 23336
WL (ml/30 min) | 4.5 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 0 |  | 18 X 5'' HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.5 | 12.3428 |  | CONSUMED | 5794
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 116 |  | D. JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.74 | 0.71773 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 158 |  | WOB (TON) |  |  | 8-10 |  | 12 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.36 | 8.2796 |  | TOTAL | 141169
ALK (FILT.) | 0.3/1 | 0.3/1 | PICK-UP WT. (TON) |  | 165 |  | AVG. ROP (M/HR) |  |  | 0.80483 | [12 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | BIT ROT HRS. |  |  | 4.97 | [12 empty] | RIG STORAGE | 655253
MAX SHIELD % | 1.875 | 1.875 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 37.28 | [12 empty] | CAMP STORAGE | 55000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 37.28 | [12 empty] | CONSUMED | 25000
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 27.02 | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  | 75.6 | [12 empty] | RECEIVED | 30000
CHLORIDES (mg/l) | 96000 | 98000 | 5" HWDPS | 97.27 | STAB - 2 | 10.46 | JET VELOCITY (M/SEC) |  |  | 69.83 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 320 | 320 | 6.5" DCS | 97.27 | STAB - 3 |  | TFA (IN²) |  |  | 0.589 | [12 empty] | POB
NACL (mg/l) | 118142.4 | 121442.4 |  |  |  |  | HSI |  |  | 3.13 |  | TOTAL LENGTH (M) | [7 empty] | 347.71 |  |  | MPCL | 3
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 4 |  | MOTOR Rev/Unit vol |  |  | 0.28 |  | BHA WT. IN MUD (TON) | [7 empty] | 19 |  |  | MPCL SERV | 23
SOLIDS % | 36.02 | 35.93 | DAILY ON BOTTOM HRS |  | 4.97 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 11.41 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 108
DAILY WELL COST (US$) |  | 42818 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20377877 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 102.4% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4466 | 650/640 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4466 | 780/780 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4466 | 960/980 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43876 | 43876.2708 | 6.5 | DRL | PT-P | RIH | RIH FROM 1526M TO 4430 M. FILLED UP STRING EVERY 15 STD.
43876.2708 | 43876.3125 | 1 | DRL | PT-P | RW | WASHED DOWN TO 4457M. OBSERVED TIGHT HOLE AT 4457 M.
43876.3125 | 43876.375 | 1.5 | DRL | PT-P | RW | REAMED / CLEARED FROM 4457 M TO BOTTOM @ 4467M
43876.375 | 43876.4062 | 0.75 | DRL | PT-P | DM | RESUMED DRILLING IN ROTARY MODE. DRILLED 8-1/2" HOLE FROM 4467 M TO 4468M.
43876.4062 | 43876.4688 | 1.5 | DRL | PT-P | CIR | CIRCULATED FOR BOTTOM UP. RECORDED SCR.
43876.4688 | 43876.7396 | 6.5 | DRL | PT-P | S / W/L | PJSM. R/UP SCHL W.LINE FOR GYRO SURVEY. RECORDED SURVEYS DURING RIH GYROSCOPE. ORIENTED TOOL FACE TO 190˚ - 205˚ AFTER SEVERAL ATTEMPTS. POOH GYROSCPE TO SURFACE. RE-RECORDED SURVEYS DURING POOH OF GYROSCOPE TOOL. R/D GYROSCOPE & WIRELINE EQUIPMENT.
43876.7396 | 43877 | 6.25 | DRL | PT-P | DM | L/DOWN SINGLE. M/UP 5" DP STAND & RESUMED DRILLING 8.5" HOLE FROM 4468M TO 4471 IN SLIDE MODE. RECORDED CHECKSHOT AT 4457.5M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43877 | 43877.0729 | 1.75 | DRL | PT-P | DM | DRILLED 8 1/2'' HOLE FROM 4471M TO 4472.47M IN SLIDE MODE. MEANWILE RECORDED CHECKSHOT AT 4458.5M.
43877.0729 | 43877.0938 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 4472M TO 4372M.
43877.0938 | 43877.1042 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43877.1042 | 43877.1458 | 1 | DRL | NPT-UP | POOH | PUMPED SLUG. POOH FROM 4372M TO 4080M. (DECIDED TO DRILL AHEAD WITH CURRENT BHA).
43877.1458 | 43877.2292 | 2 | DRL | NPT-UP | RIH | RIH BACK TO BTM AT 4472M, PRECAUTIONARY WASHED DOWN FROM 4460M.
43877.2292 | 43877.25 | 0.5 | DRL | PT-P | DM | RESUMED DRILLING IN SLIDE MODE, DRILLED 8 1/2'' HOLE FROM 4472.47M TO 4472.80M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO BTM AT 4467M, REAMED TIGHT HOLE FROM 4457 M TO 4467M. DRILLED IN ROTARY MODE FROM 4467M TO 4468M. CIRCULATED FOR BOTTOMS UP. R/UP W/LINE, RECORD GYRO SURVEYS & ORIENTED TOOL FACE. POOH & R/D GYRO & W.LINE, DRILL AHEAD 8 1/2'' HOLE IN SLIDE/ ROTARY MODE DOWN TO 4471M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2'' HOLE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14