## DDR#289
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 289
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4485.27 | 4484.5 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 288.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4488.45 | 4487.7 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 14.27
2020-02-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 53 |  | BHA NO. |  |  | 71 | IN (M) |  | 4467.1 |  | OUT (M) |  |  | STRING (BBL) | 255
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4485.27 |  | BIT NO. |  |  | 24 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 677.8
DEPTH, MD (M) | 4479 | 4485 | TVD @ 00:00HR (M) |  | 4484.5 |  | SIZE (IN) |  |  | 8.5'' |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 705
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 14.27 |  | MANUFACTURER |  |  | BAKER |  | MUD MOTOR |  |  | 6.75 | 5 |  | 4 1/2 IF |  | 8.19 | 0.60351 |  | ACT. SYS (BBL) | 1637.8
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  | 1.03 |  | TYPE |  |  | VM-S30DX1 |  | FLOAT SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.044213 |  | RESV. SYS (BBL) | 1200
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5295494 |  | ST. STAB |  |  | 8.25 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18407 |  | KILL MUD (BBL) | 240
FL TEMP. °F | 145 | 150 | AVG. WOB (TON) |  | 12 |  | IADC CODE |  |  | 537 |  | L.SAVER SUB |  |  | 6.75 | 2.875 |  | 4 1/2 IF |  | 0.53 | 0.069683 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 52 | 51 | AVG. RPM SURFACE |  | 0 |  | NOZZLES (1/32") |  |  | 3 X 16 |  | SPSA (MWD) |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 9.45 | 1.2425 |  | TOTAL | 3077.8
PV | 31 | 31 | AVG. RPM DOWNHOLE |  | 118 |  | DEPTH IN (M) |  |  | 4467.1 |  | UBHO |  |  | 6.625 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.1249 |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  | 417 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 6.875 | 2.875 |  | 4 1/2 IF |  | 9.46 | 0.69709 |  | RIG TANK | 109937
GEL ST. | 8/16 | 8/15 | PRESSURE (PSI) |  | 3300-3450 |  | METERAGE (M) |  |  | 18.27 |  | 3 X 6.5'' DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.29 | 3.588 |  | CAMP TANK | 22689
WL (ml/30 min) | 4.3 | 4.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 0 |  | 18 X 5'' HWDP's |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.5 | 12.3428 |  | CONSUMED | 8543
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 115-118 |  | D. JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.74 | 0.71773 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 158 |  | WOB (TON) |  |  | 8-12 |  | 12 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.36 | 8.2796 |  | TOTAL | 132626
ALK (FILT.) | 0.3/1 | 0.3/1 | PICK-UP WT. (TON) |  | 165 |  | AVG. ROP (M/HR) |  |  | 0.75558 | [12 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | BIT ROT HRS. |  |  | 24.18 | [12 empty] | RIG STORAGE | 698973
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 135.1 | [12 empty] | CAMP STORAGE | 60000
KCl (%) | 5 | 5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 172.38 | [12 empty] | CONSUMED | 91102
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 27.02 | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  | 75 | [12 empty] | RECEIVED | 146500
CHLORIDES (mg/l) | 99000 | 100000 | 5" HWDPS | 97.27 | STAB - 2 | 10.46 | JET VELOCITY (M/SEC) |  |  | 69.23 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 320 | 320 | 6.5" DCS | 97.27 | STAB - 3 |  | TFA (IN²) |  |  | 0.589 | [12 empty] | POB
NACL (mg/l) | 1230924 | 124742 |  |  |  |  | HSI |  |  | 3.05 |  | TOTAL LENGTH (M) | [7 empty] | 347.71 |  |  | MPCL | 4
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  | 0.28 |  | BHA WT. IN MUD (TON) | [7 empty] | 19 |  |  | MPCL SERV | 23
SOLIDS % | 35.89 | 35.85 | DAILY ON BOTTOM HRS |  | 19.21 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 21.05 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | [11 empty] | TOTAL | 108
DAILY WELL COST (US$) |  | 50025.5373 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 20432902.6705 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 102.6% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4466 | 650/640 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4466 | 780/780 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4466 | 960/980 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-06 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 8 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-02-20 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43877 | 43877.0729 | 1.75 | DRL | PT-P | DM | DRILLED 8 1/2'' HOLE FROM 4471M TO 4472.47M IN SLIDE MODE. MEANWILE RECORDED CHECKSHOT AT 4458.5M.
43877.0729 | 43877.0938 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 4472M TO 4372M.
43877.0938 | 43877.1042 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43877.1042 | 43877.1458 | 1 | DRL | NPT-UP | POOH | PUMPED SLUG. POOH FROM 4372M TO 4080M. (DECIDED TO DRILL AHEAD WITH CURRENT BHA).
43877.1458 | 43877.2292 | 2 | DRL | NPT-UP | RIH | RIH BACK TO BTM AT 4472M, PRECAUTIONARY WASHED DOWN FROM 4460M.
43877.2292 | 43878 | 18.5 | DRL | PT-P | DM | RESUMED DRILLING IN SLIDE MODE, DRILLED 8 1/2'' HOLE FROM 4472.47M TO 4485.27M. RECORDED CHECKSHOT AT 4461M, 4465M & 4468M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43878 | 43878.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 8 1/2'' HOLE IN SLIDE MODE FROM 4485.27M TO 4488.45M. RECORDED CHECKSHOT AT 4473.47M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2'' HOLE FROM 4471M TO 4472.47M IN SLIDE MODE. POOH TO 4080M, DECIDED TO DRILL AHEAD WITH SAME BHA, RIH BACK TO BTM AT 4472M, RESUME DRILLING, DRILLED AHEAD FROM 4472.47M TO 4485.27M. RECORDED CHECKSHOT MEANWHILE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2'' HOLE IN SLIDE/ ROTARY MODE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14