## DDR#290
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 290
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 73.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 18 |  | BHA No. |  |  | 43 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 173
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 649
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRICONE BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.19 | 0.014142 |  | PITS (BBL) | 921
MW IN (SG) |  | 2 | DAILY PROGRESS (M) |  |  |  | TYPE |  | XR+ |  | JUNK SUB |  |  | 5 | 1.5 |  | 3 1/2 REG |  | 0.82 | 0.061035 |  | ACT. SYS (BBL) | 1743
MW OUT (SG) |  | 2 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RH3679 |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.079643 |  | RESV. SYS (BBL) | 822
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 117 |  | 15 X 4 3/4" DCS |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 139.04 | 10.3491 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | 120 | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x OPEN |  | DRILLING JAR |  |  | 4.5625 | 2.1875 |  | 3 1/2 IF |  | 8.99 | 0.66915 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 55 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 3 X 4 3/4" DCS |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 27.87 | 2.0744 |  | TOTAL | 3065
PV |  | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 15 X 3 1/2" HWDPS |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 141.64 | 5.4822 |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 109000
GEL ST. |  | 16/28 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 19850
WL (ml/30 min.) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5600
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 128850
ALK (FILT.) |  | 0.7 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 74400
KCl (mg/l) |  | 52434.3 | JAR | 12.28 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 74400
CHLORIDES |  | 24500 | 3 1/2" HWDPS | 12.28 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 180 | 4 3/4" DCS | 12.28 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 319.62 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 12.28 |  | BIT NO. 18 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 15
SOLIDS % |  | 34.11 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 8 |  |  | SECURITY | 4
M.B.T. |  | 7.5 | CIRC. HRS |  | 13.67 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 103
DAILY WELL COST (US$) |  | 45014.0082 | SHAKER-2 | 1 x 140 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 18210871.5976 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4445 (TOL @ 3253) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 100.9% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-09-06 | 2018-10-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43379 | 43379.2292 | 5.5 | DRL | PT-P | DP | RIH BIT FROM 1830M TO 2546M & FLUSHED STRING. WHILE RIH P/UP 75 X 3 1/2" DPS FROM PIPE RACKS.
43379.2292 | 43379.4792 | 6 | DRL | PT-P | RIH | RIH FROM 2546M TO 4353M ON 5" DP STANDS FROM DERRICK. OBSERVED 03 TON COMPRESSION @ 4353M.
43379.4792 | 43379.5208 | 1 | DRL | PT-P | RW | M/UP TDS & CLEARED COMPRESSION WITH CIRCULATION. WASHED DOWN FROM 4353M & TAGGED RUBBER WIPER PLUGS @ 4408M. RECORDED 5 - 6 KLB.FT OFF BTM TORQUE @ 10 RPM.
43379.5208 | 43380 | 11.5 | DRL | PT-P | DC | DRILLED OUT WIPER PLUGS, LANDING COLLAR @ 4408.5M & SHOE TRACK CMT TO 4418M. MEANWHILE PUMPED 25 BBL HI-VIS PILL @ 4412M & ADJUSTED PARAMETERS TO IMPROVE CMT DRILLING RATE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43380 | 43380.0833 | 2 | DRL | PT-P | DC | CONT'D DRILLED OUT CMT FROM 4418M, FLOAT COLLAR @ 4420M & SHOE TRACK CMT TO 4439M.
43380.0833 | 43380.1771 | 2.25 | DRL | PT-P | CIR | CIRCULATED & CLEANED HOLE.
43380.1771 | 43380.25 | 1.75 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 4439M TO 3839M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH 6" TRICONE BIT WITH SLICK BHA
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH BIT FROM 1830M TO 4408M & TAGGED RUBBER WIPER PLUGS. DRILLED OUT PLUGS, LANDING COLLAR & SHOE TRACK CMT TO 4418M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. CONDUCT 7" LINER SCRAPER TRIP.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14