## DDR#292
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 292
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-09
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 75.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-08 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 18RR1 |  | BHA No. |  |  | 45 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 900.9
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRICONE BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.19 |  |  | PITS (BBL) | 705
MW IN (SG) |  | 2 | DAILY PROGRESS (M) |  |  |  | TYPE |  | XR+ |  | MUD MOTOR |  |  | 4.75 | 2.1875 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1605.9
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RH3679 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.82 |  |  | RESV. SYS (BBL) | 1190
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 117 |  | ST. STAB |  |  | 5.875 | 2.3125 |  | 3 1/2 IF |  | 1.23 |  |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x OPEN |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 56 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 |  | SLIM PULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 3295.9
PV |  | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 4445 |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 2.45 |  |  | DIESEL (LTR)
YIELD POINT |  | 22 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 99000
GEL ST. |  | 14/26 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 18750
WL (ml/30 min.) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4000
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 117750
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 40000
KCl (mg/l) |  | 52434.3 | JAR | 16.38 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 40000
CHLORIDES |  | 24500 | 3 1/2" HWDPS | 16.38 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 180 | 4 3/4" DCS | 16.38 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 21.71 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 16.38 |  | BIT NO. 18RR1 |  | 8-2-BT-N2&3-E-I-WT-LOG |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 21
SOLIDS % |  | 34.11 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 7.5 | CIRC. HRS |  | 18.2 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 13
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 114
DAILY WELL COST (US$) |  | 37242 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 18352735 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4445 (TOL @ 3253) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 101.7% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43381 | 43381.1458 | 3.5 | DRL | PT-P | RIH | CONT'D RIH 6" TRICONE BIT WITH 7" CSG SCRAPER FROM 2802M TO 4439M. WHILE RIH SCRAPED 7" LINER TWICE FROM 4400M TO 4439M.
43381.1458 | 43381.2396 | 2.25 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43381.2396 | 43381.6042 | 8.75 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 4439M TO 461M.
43381.6042 | 43381.6979 | 2.25 | DRL | PT-P | BHA | POOH TO SURFACE.RACKED BACK ALL BHA. L/DOWN JAR,SCRAPER & BIT
43381.6979 | 43381.7083 | 0.25 | DRL | PT-P | SM | HELD PJSM.
43381.7083 | 43381.75 | 1 | DRL | PT-P | P/T | R/UP SHOOTING NIPPLE + W.LINE BOP. ANCHORED & FLUSHED SAME. PRESSURE TESTED @ 400 PSI.OBSERVED BLIND RAM NOT HOLDING PRESSURE FROM TOP.
43381.75 | 43382 | 6 | DRL | PT-P | W/L | R/UP SHCL W.LINE GEARS + TOOLS. CONDUCTED CBL / VDL AS PER PROGRAM.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43382 | 43382.0521 | 1.25 | DRL | PT-P | W/L | R/DOWN SCHL W.LINE TOOLS AND GEARS.
43382.0521 | 43382.1667 | 2.75 | DRL | PT-P | BHA | P/UP AND M/UP RR TRI-CONE BIT + DIRECTIONAL BHA (MOTOR + MWD TOOLS).
43382.1667 | 43382.2188 | 1.25 | DRL | NPT-UP | E/C | FUNCTION TESTED PBL SUB, WHILE RECOVERING THE BALLS FROM CATCHER, FOUND 2 X DE-ACTIVATION BALLS LOST. BROKE OUT CONNECTION ONE BY ONE AND RECOVERED SAME FROM PBL INTERNAL BODY THROUGH HAMMERING (BALLS GOT STUCK IN PBL BODY WHILE DEACTIVATING THE TOOL).
43382.2188 | 43382.2396 | 0.5 | DRL | PT-P | E/C | REPEATED THE TEST SUCCESSFULLY AND RECOVERED ALL (ACTIVATION + DE-ACTIVATION) THREE BALLS FROM CATCHER.
43382.2396 | 43382.25 | 0.25 | DRL | PT-P | BHA | ADJUSTED ABH TO 1.15°. SCRIBING TOOL FACE IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | SCRIBING TOOL FACE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | 7'' CSG SCRAPER TRIP IN, POOH TO SURFACE, L/DOWN JAR + SCRAPER + BIT. PERFORMED SCHL W.LINE CBL/VDL LOG.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | R/DOWN SCHL W.LINE. RIH WITH DIR BHA DOWN TO 4439M. DISPLACE MUD IN WELL WITH 1.5 SP.GR PERFLEX MUD. DRILL OUT CMT. PRESSURE TEST LINER AT 3500 PSI. DRILL OUT SHOE & FORMATION.CONDUCT FIT @ 1.80 EMW. DRILL AHEAD 6'' DIRECTIONAL HOLE.
REMARKS |  |  | RECEIVED 6" HOLE FISHING TOOLS. DEMOBILIZED 8.5" HOLE FISHING TOOLS. DIRECTIONAL CREW ARRIVED ON 08-10-18.
Formulas:
DHARIAN-1-ST-2 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14