## DDR#293
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 293
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 76.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4445 / 4233.39 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 19 |  | BHA No. |  |  | 45 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 95
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 748
DEPTH, MD (M) |  | 4445 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.16 |  |  | PITS (BBL) | 899
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SKH613 |  | MUD MOTOR |  |  | 4.75 | 2.1875 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1742
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E238865 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.82 |  |  | RESV. SYS (BBL) | 1184
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | ST. STAB |  |  | 5.875 | 2.3125 |  | 3 1/2 IF |  | 1.23 |  |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x 14 |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 55 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 |  | SLIM PULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 3426
PV |  | 36 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 2.45 |  |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | NMDC |  |  | 4.6875 | 2 1/8" |  | 3 1/2 IF |  | 9.32 |  |  | RIG TANK | 95500
GEL ST. |  | 13/24 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 9X 4-3/4" DCs |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 83.39 |  |  | CAMP TANK | 18200
WL (ml/30 min.) |  | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 12X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.34 |  |  | CONSUMED | 4050
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 4.75" HYD D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 8.99 |  |  | RECEIVED
ALK (MUD) |  | 0.2 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 18X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.65 |  |  | TOTAL | 113700
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 102470
KCl (mg/l) |  | 45760.8 | JAR | 16.38 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 102470
CHLORIDES |  | 22000 | 3 1/2" HWDPS | 16.38 | STAB - 2 |  | TFA (IN²) |  | 0.4509 | [12 empty] | TOTAL | 440000
CALCIUM |  | 180 | 4 3/4" DCS | 16.38 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 406.37 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 16.38 |  | BIT NO. 19 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 16
SOLIDS % |  | 15.9 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS |  | 18.2 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 107
DAILY WELL COST (US$) |  | 38945 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 18391680 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4445 (TOL @ 3253) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 101.9% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776 / 3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1 | 4353/4167.8
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1 | 4423/4217.4
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43382 | 43382.0521 | 1.25 | DRL | PT-P | W/L | R/DOWN SCHL W.LINE TOOLS AND GEARS.
43382.0521 | 43382.1667 | 2.75 | DRL | PT-P | BHA | P/UP AND M/UP RR TRI-CONE BIT + DIRECTIONAL BHA (MOTOR + MWD TOOLS).
43382.1667 | 43382.2188 | 1.25 | DRL | NPT-UP | E/C | FUNCTION TESTED PBL SUB, WHILE RECOVERING THE BALLS FROM CATCHER, FOUND 2 X DE-ACTIVATION BALLS LOST. BROKE OUT CONNECTION ONE BY ONE AND RECOVERED SAME FROM PBL INTERNAL BODY THROUGH HAMMERING (BALLS GOT STUCK IN PBL BODY WHILE DEACTIVATING THE TOOL).
43382.2188 | 43382.2396 | 0.5 | DRL | PT-P | E/C | REPEATED THE TEST SUCCESSFULLY AND RECOVERED ALL (ACTIVATION + DE-ACTIVATION) THREE BALLS FROM CATCHER.
43382.2396 | 43382.3021 | 1.5 | DRL | PT-P | E/C | ADJUSTED ABH TO 1.15°. SCRIBED TOOL FACE. SHALLOW FUNCTION TESTED MWD TOOL @ 208 GPM, SPP = 1120 PSI.
43382.3021 | 43382.4062 | 2.5 | DRL | PT-P | BHA | B/OUT RR TRI-CONE BIT, M/UP NEW 6'' PDC BIT (NOV, SR # E238865, 3 X 14/32'' NOZZLES). RIH AS PER BHA DOWN TO 406M.
43382.4062 | 43382.4583 | 1.25 | DRL | PT-P | RS | SLIPPED & CUT 35M D.LINE.
43382.4583 | 43382.8125 | 8.5 | DRL | PT-P | RIH | CONT'D RIH FROM 406M DOWN TO 3239M. FILLED UP STRING EVERY 15 STANDS.
43382.8125 | 43382.8438 | 0.75 | DRL | PT-P | CIR | M/UP TDS AND WASHED DOWN TO 3249M. CIRCULATED & RECORDED PRESSURES AT DIFFERENT SPM. DISCONNECTED TDS, DROPPED PBL ACTIVATION BALL. CHASED SAME WITH LOW GPM. BALL SEATED FOLLOWED BY REDUCTION IN PRESSURE FROM 2800 PSI TO 2400 PSI. CONFIRMED PBL ACTIVATION AS MWD SIGNALS LOST.
43382.8438 | 43382.9479 | 2.5 | DRL | PT-P | DISP | CONT'D CIRCULATION AND DISPLACED 2.0 SG MUD IN HOLE WITH 1.50 SG 5 % KCL PERFLEX MUD. MEANWHILE DUMPED AND CLEANED SAND TRAP.
43382.9479 | 43382.9583 | 0.25 | DRL | PT-P | P/T | STOPPED CIRCULATION. SPACED OUT, CLOSED BOP (UPR), INCREASED SPP IN STAGES TO TEST 7'' TOL @ 3500 PSI. HELD FOR 10 MINS, OK. BLED OFF PRESSURE.
43382.9583 | 43382.9792 | 0.5 | DRL | PT-P | CIR | OPENED BOP, DISCONNECTED PIPE & DROPPED 2 X DEACTIVATION BALLS. CHASED SAME WITH LOW GPM. BALLS SEATED FOLLOWED BY THE SUDDEN INCREASE IN PRESSURE FROM 1100 PSI TO 2600 PSI. REGAINED CIRCULATION THROUGH BIT AND CONFIRMED SAME WITH MWD SIGNALS. PBL DEACTIVATED.
43382.9792 | 43383 | 0.5 | DRL | PT-P | RIH | DISCONNECTED TDS AND CONT'D RIH FROM 3249M TO 3470M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43383 | 43383.1042 | 2.5 | DRL | PT-P | RIH | CONT'D RIH FROM 3470M TO 4410M. FILLED UP STRING EVERY 15 STANDS.
43383.1042 | 43383.1146 | 0.25 | DRL | PT-P | RW | WASHED DOWN FROM 4410M TO 4439M.
43383.1146 | 43383.1354 | 0.5 | DRL | PT-P | DC | DRILLED OUT CMT FROM 4439M TO 4444M (ABOVE 7'' R/SHOE).
43383.1354 | 43383.1562 | 0.5 | DRL | PT-P | CT | SPACED OUT & CLOSED BOP (UPR). INCREASED SPP IN STAGES & PRESSURE TESTED 7'' LINER @ 3500 PSI. HELD FOR 5 MINS, OK.
43383.1562 | 43383.1875 | 0.75 | DRL | PT-P | DFS | CONT'D DRILL OUT CMT + 7'' REAMER SHOE FROM 4444M TO 4446M. (FOUND TOP OF REAMER SHOE AT 4445M)
43383.1875 | 43383.2188 | 0.75 | DRL | PT-P | DM | DRILLED 6'' DIRECTIONAL HOLE FROM 4446M TO 4449M.
43383.2188 | 43383.25 | 0.75 | DRL | PT-P | CIR | CIRCULATION TO HOMOGENIZE MUD IN PROGRESS. DUMPED 2.0 SP.GR MUD RETURNS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | R/DOWN SCHL W.LINE. RIH WITH DIR BHA DOWN TO 3239M, FUNCTION TESTED PBL SUB + MWD TOOL DURING BHA P/UP. OPERATED PBL PORTS BY DROPPING THE BALL, DISPLACED 2.0 SG MUD IN WELL WITH 1.50 SG PERFLEX MUD, P/TESTED 7'' TOL AT 3500 PSI, OK. RIH DOWN TO 3470M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO 4339M, DRILL OUT CMT TILL 4444M, P/TEST 7'' LINER, DRILL OUT 7'' LINER SHOE + 3 M NEW FORMATION, CIRCULATE TO HOMOGENIZE MUD COLUMN, FIT @ 1.80 EMW, DRILL AHEAD 6'' DIRECTIONAL HOLE.
REMARKS |  |  | SCHL W.LINE RELEASED ON 09-10-18.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14