## DDR#295
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 295
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-12
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4555 / 4309.73 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 78.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 59
2018-10-11 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 19 |  | BHA No. |  |  | 45 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 172
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4555 |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 660.8
DEPTH, MD (M) | 4526 | 4555 | TVD @ 00:00HR (M) |  | 4309.7 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.16 |  |  | PITS (BBL) | 862
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  | 59 |  | TYPE |  | SKH613 |  | MUD MOTOR |  |  | 4.75 | 2.1875 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1694.8
MW OUT (SG) | 1.5 | 1.5 | INST. ROP (M/HR) |  | 2.23 |  | SERIAL NO. |  | E238865 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.82 |  |  | RESV. SYS (BBL) | 1315
ECD (SG) | 1.57 | 1.57 | AVG. ROP (M/HR) |  | 3.05 |  | IADC CODE |  |  |  | ST. STAB |  |  | 5.875 | 2.3125 |  | 3 1/2 IF |  | 1.23 |  |  | KILL MUD (BBL) | 250
FL TEMP. °F | 131 | 131 | AVG. WOB (TON) |  | 2 |  | NOZZLES (1/32") |  | 3 x 14 |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 62 | 58 | AVG. RPM SURFACE |  | 40 |  | DEPTH IN (M) |  | 4445 |  | SLIM PULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 3259.8
PV | 35 | 36 | AVG. RPM DOWNHOLE |  | 203 |  | DEPTH OUT (M) |  |  |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 2.45 |  |  | DIESEL (LTR)
YIELD POINT | 27 | 24 | FLOWRATE (GPM) |  | 240 |  | METERAGE (M) |  | 110 |  | NMDC |  |  | 4.6875 | 2 1/8" |  | 3 1/2 IF |  | 9.32 |  |  | RIG TANK | 107500
GEL ST. | 14/18 | 13/18 | PRESSURE (PSI) |  | 3600 |  | RPM SURF. |  | 102 |  | 9X 4-3/4" DCs |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 83.39 |  |  | CAMP TANK | 17000
WL (ml/30 min.) | 3.5 | 3.5 | TORQ. ON-BTM (KLB-FT) |  | 5-6 |  | RPM BTM. |  | 230 |  | 12X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.34 |  |  | CONSUMED | 7600
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 2-4 |  | 4.75" HYD D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 8.99 |  |  | RECEIVED | 25000
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 137 |  | AVG. ROP (M/HR) |  | 3.3598 |  | 18X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.65 |  |  | TOTAL | 124500
ALK (FILT.) | 0.5 | 0.6 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 32.74 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 235.46 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 399.04 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 77.04 | [12 empty] | CONSUMED | 129960
KCl (mg/l) | 52434.3 | 52434.3 | JAR | 46.39 | STAB - 1 | 30.01 | JET VELOCITY (M/SEC) |  | 51.5 | [12 empty] | RECEIVED | 129960
CHLORIDES | 24500 | 24500 | 3 1/2" HWDPS | 46.39 | STAB - 2 |  | TFA (IN²) |  | 0.4509 | [12 empty] | TOTAL | 440000
CALCIUM | 180 | 180 | 4 3/4" DCS | 46.39 | NMDC | 30.01 | HSI |  | 1.6 | [12 empty] | POB
OIL % |  |  | MUD MOTOR | 30.01 | SPSA | 30.01 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 406.37 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 46.39 |  | BIT NO. 19 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 16
SOLIDS % | 15.8 | 15.8 | ON BOTTOM HRS |  | 19.34 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 23.58 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4450 |  | 45.44 |  | 75 |  |  | 0.88 |  | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 46053 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4478 |  | 46.09 |  | 75.08 |  |  | 0.7 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 18502847 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4508 |  | 46.3 |  | 75.2 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 102.5% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4536.55 |  | 46.29 |  | 74.06 |  |  | 0.87 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 750/1144/1620 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40/50 |  | 4457 |  | 1320/2095/2985 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 800/1160/1620 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 9 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43384 | 43385 | 24 | DRL | PT-P | DM | CONT'D DRILLING 6'' DIRECTIONAL HOLE IN ROTARY & SLIDE MODES FROM 4496M TO 4555M. REAMED DRILLED INTERVALS & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43385 | 43385.2083 | 5 | DRL | PT-P | DM | CONT'D DRILLING 6'' DIRECTIONAL HOLE IN ROTARY MODE FROM 4555M TO 4574M. REAMED DRILLED INTERVALS & RECORDED MWD SURVEY AT CONNECTION.
43385.2083 | 43385.25 | 1 | DRL | NPT-UP | STK | WHILE DRILLING FROM 4573M TO 4574.42M OBSERVED HIGH DRILLING TORQUE. P/UP STRING, SPP SHOT TO 5000 PSI FOLLOWED BY STRING STUCK. REDUCED PUMP RATE TO 30 SPM, WORKED ON STRING & REGAINED NORMAL CIRCULATION AT 80 SPM / 3600 PSI. WORK ON STRING IN PROGRESS. MEANWHILE PREPARING LUBE PILL.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WORK ON STRING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' DIRECTIONAL HOLE DOWN TO 4555M IN ROTARY/ SLIDE MODE. REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION. PUMPED BRIDGE PILL AFTER CONNECTION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6'' DIRECTIONAL HOLE.
REMARKS |  |  | MARKED TOP OF NAMMAL FORMATION @ 4547M, SWEEPING 20 BBL BRIDGE PILL EVERY 15 M, DEMOB 7'' SCRAPER ON 11-10-18.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14