## DDR#295
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [16 empty] | Report No. |  | 295
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [7 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-23
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [7 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [7 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / MUHAMMAD MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4562 | 4560.66 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 294.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4564 | 4562.64 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 65.14
2020-02-22 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA | [5 empty] | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8 1/2'' |  | RUN NO. |  |  | 56 |  |  | BHA NO. |  |  | 73 | IN (M) |  | 4496.53 |  | OUT (M) |  |  | STRING (BBL) | 256
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4562 |  | BIT NO. |  |  | 26 |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 691.3
DEPTH, MD (M) | 4541 | 4562 | TVD @ 00:00HR (M) |  | 4560.66 |  | SIZE (IN) |  |  | 8.5'' |  |  | PDC |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 672
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  | 65.14 |  | MANUFACTURER |  |  | NOV |  |  | XCEED675-8-3/8 STAB |  |  | 6.875 | 2.25 |  | 4 1/2 REG |  | 7.6 | 1.0182 |  | ACT. SYS (BBL) | 1619.3
MW OUT (SG) | 1.85 | 1.85 | INST. ROP (M/HR) |  | 2.95 |  | TYPE |  |  | SKFX616M |  |  | LOWER SAVER SUB |  |  | 6.875 | 2.75 |  | 5 1/2 FH |  | 0.48 | 0.06431 |  | RESV. SYS (BBL) | 1160
ECD (SG) | 1.9444 | 1.9444 | AVG. ROP (M/HR) |  | 4.08 |  | SERIAL NO. |  |  | E260746 |  |  | TELESCOPE 675 |  |  | 6.875 | 5 |  | 5 1/2 FH |  | 7.47 | 0.98214 |  | KILL MUD (BBL) | 240
FL TEMP. °F | 150 | 151 | AVG. WOB (TON) |  | 7-12 |  | IADC CODE | [5 empty] | UPPER SAVER SUB |  |  | 6.875 | 2.75 |  | 5 1/2 FH |  | 0.61 | 0.080202 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 54 | 53 | AVG. RPM SURFACE |  | 115-120 |  | NOZZLES (1/32") |  |  | 3X12 + 3X13 |  |  | NMDC |  |  | 6.875 | 2.75 |  | 4 1/2 IF |  | 9.34 | 1.3209 |  | TOTAL | 3019.3
PV | 31 | 31 | AVG. RPM DOWNHOLE |  | 115-120 |  | DEPTH IN (M) |  |  | 4496.53 |  |  | 3X 6.5'' DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.67 | 3.638 |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  | 450-480 |  | DEPTH OUT (M) | [5 empty] | 18X5" HWDP |  |  | 6.875 | 2.75 |  | 4 1/2 IF |  | 168.44 | 12.4121 |  | RIG TANK | 118752
GEL ST. | 8/19 | 8/17 | PRESSURE (PSI) |  | 3350-4025 |  | METERAGE (M) |  |  | 65.47 |  |  | D. JAR |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.73 | 1.2793 |  | CAMP TANK | 18783
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  | 5-7.5 |  | RPM SURF. |  |  | 110-120 |  |  | 12X5"HWDP |  |  | 6.625 | 2.0625 |  | 4 1/2 IF |  | 111.96 | 8.2502 |  | CONSUMED | 9254
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 110-120 | [13 empty] | RECEIVED | 48000
ALK (MUD) | 0.5 | 0.6 | STRING WT. (TON) - ROT |  | 154 |  | WOB (TON) |  |  | 3-12 | [13 empty] | TOTAL | 137535
ALK (FILT.) | 0.3/1.1 | 0.3/1.2 | PICK-UP WT. (TON) |  | 165 |  | AVG. ROP (M/HR) |  |  | 3.9775 | [13 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 160 |  | BIT ROT HRS. |  |  | 16.46 | [13 empty] | RIG STORAGE | 763250
MAX SHIELD % | 2.25 | 2.5 | D & I SURVEY-(OFF BIT-M)Telescope |  | 12.47 |  | K-REVS IN 24 HRS |  |  | 112.93 | [13 empty] | CAMP STORAGE | 65000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 116.01 | [13 empty] | CONSUMED | 73725
KCl (mg/l) | 51480.9 | 51480.9 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 83.5 | [13 empty] | RECEIVED | 130000
CHLORIDES (mg/l) | 100000 | 99000 | JAR | 23.18 | STAB - 1 |  | JET VELOCITY (M/SEC) |  |  | 63.07 | [13 empty] | DRL WASTE
HARDNESS (mg/l) | 320 | 320 | 5" HWDPS | 21.43 | STAB - 2 |  | TFA (IN²) |  |  | 0.84 | [13 empty] | POB
NACL (mg/l) | 124742.4 | 123092.4 | 6.5" DCS | 21.43 | STAB - 3 |  | HSI |  |  | 2.82 |  |  | TOTAL LENGTH (M) | [7 empty] | 343.54 |  |  | MPCL | 3
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 19.91 |  | MOTOR REV/GAL | [5 empty] | BHA WT. IN MUD (TON) | [7 empty] | 22.2147 |  |  | MPCL SERV | 19
SOLIDS % | 35.65 | 35.69 | DAILY ON BOTTOM HRS |  | 15.98 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14.9342 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 22.77 |  | BIT NO. : 25 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA | [5 empty] | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 |  | 4522.39/4521.33 |  | 6.36 |  | 15.15 |  |  | 6.47 |  | C/shot |  | TOTAL | 108
DAILY WELL COST (US$) |  | 68788.82 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 |  | 4526.98/4525.89 |  | 6.71 |  | 7.82 |  |  | 5.91 |  | DMAG Survey |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20848426.7766 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 |  | 4532.95/4531.82 |  | 6.87 |  | 1.68 |  |  | 3.73 |  | C/shot |  | LAST CSG SIZE | 9.625
% OF AFE SPENT |  | 104.7% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4391 | 4543.48/4542.27 |  | 7.37 |  | 348.35 |  |  | 4.91 |  | C/shot |  | FIT (EMW) | 2
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996 |  | 4550.39/4549.12 |  | 7.63 |  | 342.29 |  |  | 3.61 |  | C/shot
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [10 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 935.283
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 30 |  | 4466 | 650/640 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 40 |  | 4466 | 780/780 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 50 |  | 4466 | 960/980 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA | [5 empty] | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS | [5 empty] | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-21 |  | OPR. HRS OF CENTRIFUGE-1 | [5 empty] | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-03-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 6 |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43883 | 43883.2083 | 5 | DRL | PT-P | DM | DRILLED 8.5" HOLE FROM 4496.86M TO 4512M. RECORDED CHECK SHOT AT 4499M.
43883.2083 | 43883.2292 | 0.5 | DRL | NPT-UP | S | ATTEMPTED TO RECORD MWD SURVEY. OBSERVED NOISY SIGNAL & NO SUCCESS IN RECORDING MWD SURVEY. DECIDED TO DRILL FEW METER AHEAD & TRY AGAIN.
43883.2292 | 43883.5417 | 7.5 | DRL | PT-P | DM | DRILLED 8.5" HOLE FROM 4512M TO 4538M.
43883.5417 | 43883.625 | 2 | DRL | NPT-UP | S | MADE SEVERAL ATTEMPTS TO RECORD CHECK SHOT SURVEY; BUT FAILED DUE TO NOISY SIGNALS. TRIED DIFFERENT PUMPS COMBINATION; NO SUCCESS. CHANGED D&M PRESSURE SENSOR @ STAND PIPE. SIGNALS QUALITY PARTIALLY IMPROVED. RECORDED SURVEY.
43883.625 | 43884 | 9 | DRL | PT-P | DM | DOWN LINKED COMMANDS TO XCEED & RESUMED DRILLING. DRILLED 8.5" HOLE FROM 4538M TO 4562M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43884 | 43884.0417 | 1 | DRL | PT-P | DM | DRILLED 8.5" HOLE FROM 4562M TO 4564M. RECORDED CHECK SHOT. FOUND PLANNED TRAJECTORY NOT ACHIEVABLE WITH XCEED. DECIDED TO POOH.
43884.0417 | 43884.0938 | 1.25 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN.
43884.0938 | 43884.1042 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43884.1042 | 43884.125 | 0.5 | DRL | PT-P | POOH | POOH FROM 4564M TO 4367M.
43884.125 | 43884.1354 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43884.1354 | 43884.25 | 2.75 | DRL | PT-P | POOH | POOH FROM 4367M TO 3163M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE/KULDANA : CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8.5" HOLE FROM 4496.86M TO 4562M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WITH 8.5" TC BIT & MUD MOTOR TO BOTTOM. DRILL AHEAD 8.5" HOLE.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14