## DDR#296
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 296
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 79.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 19
2018-10-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 19 |  | BHA No. |  |  | 45 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 162
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4574.42 |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 675.5
DEPTH, MD (M) | 4574 | 4574 | TVD @ 00:00HR (M) |  | 4322.59 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.16 |  |  | PITS (BBL) | 866
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  | 19 |  | TYPE |  | SKH613 |  | MUD MOTOR |  |  | 4.75 | 2.1875 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1703.5
MW OUT (SG) | 1.5 | 1.5 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E238865 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.82 |  |  | RESV. SYS (BBL) | 331
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | ST. STAB |  |  | 5.875 | 2.3125 |  | 3 1/2 IF |  | 1.23 |  |  | KILL MUD (BBL) | 1300
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x 14 |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 60 | 61 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 |  | SLIM PULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 3334.5
PV | 38 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 2.45 |  |  | DIESEL (LTR)
YIELD POINT | 26 | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 129 |  | NMDC |  |  | 4.6875 | 2 1/8" |  | 3 1/2 IF |  | 9.32 |  |  | RIG TANK | 119000
GEL ST. | 09/13 | 09/15 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 102 |  | 9X 4-3/4" DCs |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 83.39 |  |  | CAMP TANK | 16450
WL (ml/30 min.) | 3.5 | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 230 |  | 12X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.34 |  |  | CONSUMED | 14050
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 2-4 |  | 4.75" HYD D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 8.99 |  |  | RECEIVED | 25000
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 3.451 |  | 18X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.65 |  |  | TOTAL | 135450
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 37.38 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 62.92 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 461.96 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 129960
KCl (mg/l) | 52434.3 | 52434.3 | JAR | 52.04 | STAB - 1 | 35.66 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 129960
CHLORIDES | 24600 | 24600 | 3 1/2" HWDPS | 52.04 | STAB - 2 |  | TFA (IN²) |  | 0.4509 | [12 empty] | TOTAL | 440000
CALCIUM | 180 | 180 | 4 3/4" DCS | 52.04 | NMDC | 35.66 | HSI | [14 empty] | POB
OIL % |  |  | MUD MOTOR | 35.66 | SPSA | 35.66 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 406.37 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 52.04 |  | BIT NO. 19 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 15
SOLIDS % | 15.79 | 15.79 | ON BOTTOM HRS |  | 4.64 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 22.75 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4450 |  | 45.44 |  | 75 |  |  | 0.88 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 57622 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4478 |  | 46.09 |  | 75.08 |  |  | 0.7 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 18560469 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4508 |  | 46.3 |  | 75.2 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 102.8% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4536.55 |  | 46.29 |  | 74.06 |  |  | 0.87 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 750/1144/1620 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40/50 |  | 4457 |  | 1320/2095/2985 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 800/1160/1620 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4547/4304.1
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43385 | 43385.2083 | 5 | DRL | PT-P | DM | CONT'D DRILLING 6'' DIRECTIONAL HOLE IN ROTARY MODE FROM 4555M TO 4574M. REAMED DRILLED INTERVALS & RECORDED MWD SURVEY AT CONNECTION.
43385.2083 | 43385.2917 | 2 | DRL | NPT-UP | STK/CIR | WHILE DRILLING FROM 4573M TO 4574.42M OBSERVED HIGH DRILLING TORQUE. P/UP STRING, SPP SHOT TO 5000 PSI FOLLOWED BY STRING STUCK. REDUCED PUMP RATE TO 30 SPM, WORKED ON STRING & REGAINED NORMAL CIRCULATION AT 80 SPM / 3600 PSI. WORKED ON STRING, MEANWHILE PREPARED LUBE PILL.
43385.2917 | 43385.3229 | 0.75 | DRL | NPT-UP | STK/SP | PUMPED 35 BBL 10 % LUBE PILL. DISPLACED WITH MUD & SPOTTED 10 BBLS AGAINST BHA. LEFT 25 BBLS INSIDE STRING.
43385.3229 | 43385.3854 | 1.5 | DRL | NPT-UP | STK/CIR | WORKED ON STUCK STRING. DURING WORKING DISPLACED 1 BBL OF LUBE PILL IN ANNULUS AFTER EVERY 5 MINUTES. NO PROGRESS
43385.3854 | 43385.4688 | 2 | DRL | NPT-UP | STK/CIR | CIRCULATED OUT LUBE PILL MEANWHILE WORKED ON THE STUCK STRING. PREPARED 40 BBL WEIGHTED PILL OF 1.8 SP.GR.
43385.4688 | 43385.5938 | 3 | DRL | NPT-UP | STK/CIR | SWEPT 40 BBL WEIGHTED PILL OF 1.8 SP.GR.
43385.5938 | 43385.8854 | 7 | DRL | NPT-UP | STK/CIR | KEPT CIRCULATING & WORKING ON STUCK STRING INTERMITTENTLY. MEANWHILE PREPARED 29 BBL BLACK MAGIC SPOTTING FLUID.
43385.8854 | 43385.9167 | 0.75 | DRL | NPT-UP | STK/SP | PUMPED 29 BBL BLACK MAGIC PILL. DISPLACED WITH MUD & SPOTTED 7 BBL AGAINST BHA, LEFT 22 BBL INSIDE STRING.
43385.9167 | 43386 | 2 | DRL | NPT-UP | STK | SOAKING TIME FOR BLACK MAGIC PILL MEANWHILE DISPLACED 0.5 BBL AFTER EVERY 30 MINS IN ANNULUS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43386 | 43386.1875 | 4.5 | DRL | NPT-UP | STK | CONT'D SOAKING TIME FOR BLACK MAGIC PILL, MEANWHILE KEPT DISPLACING 0.5BBL BLACK MAGIC PILL AFTER EVERY 30MINS IN ANNULUS.
43386.1875 | 43386.25 | 1.5 | DRL | NPT-UP | STK | WORKED ON STUCK STRING INTERMITTENTLY, MEANWHILE KEPT DISPLACING 0.5BBL BLACK MAGIC PILL AFTER EVERY 30 MINS IN ANNULUS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WORK ON STUCK STRING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' DIRECTIONAL HOLE DOWN TO 4574.42M. WHILE DRILLING OBSERVED HIGH DRILLING TORQUE, P/UP STRING, SPP SHOT FOLLOWED BY STRING STUCK, WORKED ON STRING NO SUCCESS, SPOTTED LUBE PILL AND CONT'D WORKING ON STRING, NO PROGRESS, CIRCULATED OUT SAME, SWEPT OUT 40 BBL HIGH WEIGHTED PILL MEANWHILE WORKED ON STRING, NO PROGRESS, PREPARED BLACK MAGIC PILL AND SPOTTED IN ANNULUS, SOAKING TIME FOR BLACK MAGIC PILL MEANWHILE DISPLACING 0.5BBL/30MINS IN ANNULUS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | SOAKING TIME FOR BLACK MAGIC PILL, WORK ON STUCK STRING, RELEASE STRING, POOH INSIDE LINER SHOE, CIRCULATION.
REMARKS |  |  | FISHING ENGR. ARRIVED ON LOCATION.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14