## DDR#299
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 299
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 82.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 19 |  | BHA No. |  |  | 45 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 162
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4574.42 |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 675.5
DEPTH, MD (M) |  | 4574 | TVD @ 00:00HR (M) |  | 4322.59 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.16 |  |  | PITS (BBL) | 775
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | SKH613 |  | MUD MOTOR |  |  | 4.75 | 2.1875 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1612.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E238865 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.82 |  |  | RESV. SYS (BBL) | 423
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | ST. STAB |  |  | 5.875 | 2.3125 |  | 3 1/2 IF |  | 1.23 |  |  | KILL MUD (BBL) | 1300
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x 14 |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 70 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4445 |  | SLIM PULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 3335.5
PV |  | 43 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 2.45 |  |  | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 129 |  | NMDC |  |  | 4.6875 | 2 1/8" |  | 3 1/2 IF |  | 9.32 |  |  | RIG TANK | 107500
GEL ST. |  | 14/18 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 9X 4-3/4" DCs |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 83.39 |  |  | CAMP TANK | 14750
WL (ml/30 min.) |  | 3.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 12X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.34 |  |  | CONSUMED | 4550
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 4.75" HYD D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 8.99 |  |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  | 137 |  | AVG. ROP (M/HR) |  |  |  | 18X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.65 |  |  | TOTAL | 122250
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 461.96 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 42000
KCl (mg/l) |  | 52434.3 | JAR | 52.04 | STAB - 1 | 35.66 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 42000
CHLORIDES |  | 24600 | 3 1/2" HWDPS | 52.04 | STAB - 2 |  | TFA (IN²) |  | 0.4509 | [12 empty] | TOTAL | 440000
CALCIUM |  | 180 | 4 3/4" DCS | 52.04 | NMDC | 35.66 | HSI | [14 empty] | POB
OIL % |  |  | MUD MOTOR | 35.66 | SPSA | 35.66 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 406.37 |  |  | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  | 52.04 |  | BIT NO. 19 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 28
SOLIDS % |  | 15.79 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS |  | 0 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 18
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4450 |  | 45.44 |  | 75 |  |  | 0.88 |  | MWD |  | TOTAL | 123
DAILY WELL COST (US$) |  | 67876 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4478 |  | 46.09 |  | 75.08 |  |  | 0.7 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 18694335 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4508 |  | 46.3 |  | 75.2 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 103.6% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4536.55 |  | 46.29 |  | 74.06 |  |  | 0.87 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 750/1144/1620 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40/50 |  | 4457 |  | 1320/2095/2985 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 800/1160/1620 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4547/4304.1
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43388 | 43388.5 | 12 | DRL | NPT-UP | STK/ WOE | CONT'D WORK ON STUCK STRING INTERMITTENTLY, MEANWHILE ARRANGING REMAINING EQP. OF CT (PUMPER + ACCESSORIES). FLUSHED WITH 27 BBLS OF WATER & DRIFTED COIL TUBING WITH 0.43" BALL. FUNCTION TESTED BOP & SPINCAT (JETTING TOOL).
43388.5 | 43388.7812 | 6.75 | DRL | NPT-UP | STK /CTB | SET SLIPS ON 5" DPs AT 140 TON H.LOAD.BROKE OUT TDS. R/UP SAFETY VALVE+ CTU BOP FLANGE ON STRING. R/UP CTU BOP+ INJECTOR HEAD.
43388.7812 | 43388.8229 | 1 | DRL | NPT-UP | STK / P/T | H/UP DOWEL UNIT + LINES. FLUSHED . CLOSED SAFETY VALVE BELOW CTU BOP. P/TESTED CT BOP @ 3500 PSI, HELD PRESSURE FOR 10 MINS, OK.
43388.8229 | 43388.9792 | 3.75 | DRL | NPT-UP | STK / CTB | ARRANGED CT PUMPER + BATCH MIXER, R/DOWN DOWEL UNIT. R/UP CT PUMPER + BATCH MIXER, CONNECTED HOSES AND PRESSURE TESTED H.UP AT 3500 PSI, OK.
43388.9792 | 43389 | 0.5 | DRL | NPT-UP | STK / CTB | RAN CT INSIDE STRING TO 350M MEANWHILE TRICKLING WITH 1.5 SG MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43389 | 43389.1042 | 2.5 | DRL | NPT-UP | STK/ CTB | CONT'D RUN IN CT INSIDE STRING TO 500M, OBSERVED CIRCULATING PRESSURE INCREASED TO 4200 PSI AT 0.25 BPM. STOPPED RUNNING CT INSIDE STRING. FLUSHED & DISPLACED 1.50 SG MUD WITH WATER TO CHECK & AVOID PLUGGING OF SPINCAT (JETTING TOOL) JETS. CIRCULATED AND STABILIZED PRESSURE AT 4200 PSI/ 0.80 BPM.
43389.1042 | 43389.2396 | 3.25 | DRL | NPT-UP | STK/ CTB | CONT'D RUN CT INSIDE STRING TO 3150M, MEANWHILE TRICKLING WITH FRESH WATER.
43389.2396 | 43389.25 | 0.25 | DRL | NPT-UP | STK/ CTB | CIRCULATING THROUGH CT FOR BTM UP, MEANWHILE PREPARING VISCOSIFIED WATER FOR FURTHER CIRCULATION.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION THROUGH CT IN PROGRESS, MEANWHILE PREPARING VISCOSIFIED WATER.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D WORK ON STUCK STRING INTERMITTENTLY, MEANWHILE ARRANGE CT REMAINING EQP, COIL TUBING JOB TO CLEAN INSIDE STRING.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE CT CLEAN OUT JOB, FPIT JOB.
REMARKS |  |  | RELEASED SCHL W/LINE, DIRECTIONAL SERVICES, FISHING ENGR. ON 15-10-18.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14