## DDR#299
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [16 empty] | Report No. |  | 299
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [7 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-02-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [7 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [7 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4608 | 4605.3 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 298.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4626 | 4622.68 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 10.5
2020-02-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA | [5 empty] | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 58 |  |  | BHA NO. |  |  | 73 | IN (M) |  | 4597.5 |  | OUT (M) |  |  | STRING (BBL) | 258.6
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4608 |  | BIT NO. |  |  | 26 RR |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 701
DEPTH, MD (M) | 4597.5 | 4608 | TVD @ 00:00HR (M) |  | 4605.3 |  | SIZE (IN) |  |  | 8.5 |  |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.031555 |  | PITS (BBL) | 617
MW IN (SG) | 1.88 | 1.9 | DAILY PROGRESS (M) |  | 10.5 |  | MANUFACTURER |  |  | NOV |  |  | XCEED675-8-3/8 STAB |  |  | 6.875 | 2.25 |  | 4 1/2 REG |  | 7.6 | 1.0182 |  | ACT. SYS (BBL) | 1576.6
MW OUT (SG) |  | 1.89 | INST. ROP (M/HR) |  | 3.28 |  | TYPE |  |  | SKFX616M |  |  | LOWER SAVER SUB |  |  | 6.875 | 2.75 |  | 5 1/2 FH |  | 0.48 | 0.06431 |  | RESV. SYS (BBL) | 1300
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 4.1502 |  | SERIAL NO. |  |  | E260746 |  |  | TELESCOPE 675 |  |  | 6.875 | 5 |  | 5 1/2 FH |  | 7.47 | 0.98214 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  | 125.6 | AVG. WOB (TON) |  | 10-12 |  | IADC CODE | [5 empty] | UPPER SAVER SUB |  |  | 6.875 | 2.75 |  | 5 1/2 FH |  | 0.61 | 0.080202 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 58 | 56 | AVG. RPM SURFACE |  | 120 |  | NOZZLES (1/32") |  |  | 3x12 + 3x13 |  |  | NMDC |  |  | 6.875 | 2.75 |  | 4 1/2 IF |  | 9.34 | 1.3209 |  | TOTAL | 3116.6
PV | 33 | 33 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH IN (M) |  |  | 4597.5 |  |  | 3x 6.5'' DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.67 | 3.638 |  | DIESEL (LTR)
YIELD POINT | 27 | 25 | FLOWRATE (GPM) |  | 445 |  | DEPTH OUT (M) | [5 empty] | 18x 5" HWDP |  |  | 6.875 | 2.75 |  | 4 1/2 IF |  | 168.44 | 12.4121 |  | RIG TANK | 91894
GEL ST. | 9/17 | 9/16 | PRESSURE (PSI) |  | 3350-3450 |  | METERAGE (M) |  |  | 10.5 |  |  | D. JAR |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.73 | 1.2793 |  | CAMP TANK | 16562
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  | 7-8 |  | RPM SURF. |  |  | 120 |  |  | 12x 5"HWDP |  |  | 6.625 | 2.0625 |  | 4 1/2 IF |  | 111.96 | 8.2502 |  | CONSUMED | 5978
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | RPM BTM. |  |  | 120 | [13 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 160 |  | WOB (TON) |  |  | 10-12 | [13 empty] | TOTAL | 108456
ALK (FILT.) | 0.3/1.1 | 0.3/0.9 | PICK-UP WT. (TON) |  | 165 |  | AVG. ROP (M/HR) |  |  | 4.1502 | [13 empty] | WATER (LTR)
pH | 10 | 9.5 | SLACK-OFF WT. (TON) |  | 158 |  | BIT ROT HRS. |  |  | 2.53 | [13 empty] | RIG STORAGE | 801074
MAX SHIELD % | 3 | 3 | D & I SURVEY-(OFF BIT-M)Telescope |  | 11.95 |  | K-REVS IN 24 HRS |  |  | 17.11 | [13 empty] | CAMP STORAGE | 78000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 17.11 | [13 empty] | CONSUMED | 52986
KCl (mg/l) | 51480.9 | 51480.9 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 77.7 | [13 empty] | RECEIVED | 139700
CHLORIDES (mg/l) | 99000 | 99000 | JAR | 33.79 | STAB - 1 |  | JET VELOCITY (M/SEC) |  |  | 60.32 | [13 empty] | DRL WASTE | 104000
HARDNESS (mg/l) | 320 | 320 | 5" HWDPS | 32.04 | STAB - 2 |  | TFA (IN²) |  |  | 0.7201 | [13 empty] | POB
NACL (mg/l) | 123092.4 | 123092.4 | 6.5" DCS | 32.04 | STAB - 3 |  | HSI |  |  | 2.53 |  |  | TOTAL LENGTH (M) | [7 empty] | 343.54 |  |  | MPCL | 4
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 5.65 |  | MOTOR REV/GAL | [5 empty] | BHA WT. IN MUD (TON) | [7 empty] | 21 |  |  | MPCL SERV | 19
SOLIDS % | 36.22 | 38.76 | DAILY ON BOTTOM HRS |  | 2.53 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 6.46 |  | BIT NO. : 26 RR | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA | [5 empty] | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 |  | 4550.39/4549.12 |  | 7.63 |  | 342.29 |  |  | 3.61 |  | C/shot |  | TOTAL | 114
DAILY WELL COST (US$) |  | 63014.3533 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 |  | 4560.30/4558.93 |  | 8.93 |  | 332.69 |  |  | 5.73 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 21043662.366 | SHAKER-3 | 2 x 140 + 1 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 |  | 4564.20/4562.78 |  | 9.59 |  | 328.95 |  |  | 6.87 |  | C/shot |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 105.7% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4391 | 4569.30/4567.80 |  | 10.95 |  | 325.9 |  |  | 8.61 |  | C/shot |  | FIT (EMW) | 2
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996 |  | 4583.47/4581.60 |  | 15.18 |  | 320.48 |  |  | 10.7 |  | MWD |  | MAASP (PSI) | 623.2492
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [10 empty] | SLOW CIRCULATION RATE (1.90 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 30 |  | 4583 | 600/580 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 40 |  | 4583 | 700/680 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 50 |  | 4583 | 850/850 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA | [5 empty] | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4580/4578.39
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS | [5 empty] | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR
TRIP DRILL | 2020-01-04 | 2020-02-03 | LAST BOP TEST DATE |  | 2020-02-21 |  | OPR. HRS OF CENTRIFUGE-1 | [5 empty] | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-03-06 |  | OPR. HRS OF CENTRIFUGE-2 | [5 empty] | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43887 | 43887.0521 | 1.25 | DRL | PT-P | POOH | CONT'D POOH FROM 941M TO 347M (BHA TOP).
43887.0521 | 43887.0625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43887.0625 | 43887.1562 | 2.25 | DRL | PT-P | BHA | POOH BHA FROM 347M TO SURFACE. RETRIEVED MWD TOOL. L/D JAR, MUD MOTOR, SPSA, ST. STAB & BIT.
43887.1562 | 43887.2396 | 2 | DRL | PT-P | BHA | P/U & M/U RR 8 1/2" PDC BIT + EXCEED + TELESCOPE + NMDC & RIH DOWN TO 343M. FILLED UP STRING AFTER EVERY 8 STANDS.
43887.2396 | 43887.2604 | 0.5 | DRL | PT-P | RIH | CONT'D RIH FROM 343M TO 515M.
43887.2604 | 43887.2708 | 0.25 | DRL | PT-P | E/C | FUNCTION TESTED XCEED-TELESCOPE. FOUND WORKING GOOD. RECORDED 1625 PSI @ 450 GPM.
43887.2708 | 43887.6458 | 9 | DRL | PT-P | RIH | RESUMED RIH. RIH DOWN TO 4370M. FILLED STRING AFTER EVERY 8 STANDS.
43887.6458 | 43887.6875 | 1 | DRL | NPT-P | RS | SLIP & CUT 200 FT DRILL LINE. ADJUSTED CROWNOMATIC & RESET ACS.
43887.6875 | 43887.7083 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43887.7083 | 43887.7292 | 0.5 | DRL | PT-P | RIH | RESUMED RIH. TAGGED COMPRESSION AT 4487M.
43887.7292 | 43887.8438 | 2.75 | DRL | PT-P | RW | M/UP TDS. REAMED / WASHED DOWN TO BOTTOM.
43887.8438 | 43887.9167 | 1.75 | DRL | PT-P | CIR | CIRCULATED BOTTOMS UP. DOWNLINKED TOOL. RECORDED SCR & MWD SURVEY.
43887.9167 | 43888 | 2 | DRL | PT-P | DM | RESUMED DRILLING & DRILLED 8 1/2" HOLE FROM 4597.5M TO 4608M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-02-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43888 | 43888.1667 | 4 | DRL | PT-P | DM | CONT'D DRILLING 8 1/2" HOLE FROM 4608M TO 4626M.
43888.1667 | 43888.25 | 2 | DRL | PT-P | RW | OBSERVED TIGHT HOLE WHILE BACK REAMING / REAMING THE DRILLED INTERVAL. OBSERVED ROTARY STALLED & PRESSURE SPIKES IN INTERVAL 4626-4611M & 4603-4602M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | CHORGALI : LIMESTONE, SHALE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | REAMING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 941M TO SURFACE. RIH RR 8 1/2" PDC BIT WITH RSS (EXCEED + TELESCOPE) DOWN TO 515M. F/T RSS. RIH DOWN TO 4487M. REAMED / WASHED DOWN TO BOTTOM. CIRCULATED BOTTOMS UP. DRILLED 8 1/2" HOLE FROM 4597.5M TO 4608M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" HOLE AS PER PLAN.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14