## DDR # 03
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 3
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR / SAIF TURK / MEHDI / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 296 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 2.5833
RIG REP.: |  | JAVED IQBAL / KHALID |  |  | MD/TVD @ 06:00HRS: |  | 334 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 77
2017-12-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 26" |  | BIT No. |  | 2 | 2 | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 9.3
CHECK TIME | 6:00 | 23:59 | MD @ 00:00HR (M) |  | 296 |  | SIZE (IN) |  | 26 | 26 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 610.39
DEPTH, MD (M) |  | 296 | TVD @ 00:00HR (M) |  | 296 |  | MANUFACTURER |  | BAKER | BAKER | 26"PDC BIT |  |  | 26 |  |  | 7 5/8 REG |  | 0.57 |  |  | PITS (BBL) | 906
MW IN (SG) |  | 1.09 | DAILY PROGRESS (M) |  | 77 |  | TYPE |  | TD509S | TD509S | BITSUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 1.08 | 0.5 |  | ACT. SYS (BBL) | 1512.48
MW OUT (SG) |  | 1.09 | INST. ROP (M/HR) |  | 5.83 |  | SERIAL NO. |  | 5278922 | 5278922 | SHOCK SUB |  |  | 12 | 2.75 |  | 7 5/8 REG |  | 4.16 | 2 |  | RESV. SYS (BBL) | 400
ECD (SG) |  | 1.0953 | AVG. ROP (M/HR) |  | 6.58 |  | IADC CODE |  | S423 | S423 | 2X11" DCS |  |  | 11 | 3 |  | 7 5/8 REG |  | 18.32 | 8.18 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  | 91.4 | AVG. WOB (TON) |  | 7 |  | NOZZLES |  | 9X14 | 9X14 | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 2.34 | 1 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  | 105 |  | DEPTH IN (M) |  | 47 | 47 | 1X11" DC |  |  | 11 | 3 |  | 7 5/8 REG |  | 9.2 | 4.11 |  | TOTAL | 3438.17
PV |  | 13 | AVG. RPM DOWNHOLE |  | 105 |  | DEPTH OUT (M) |  |  |  | 26"S.STB |  |  | 26 | 3.125 |  | 7 5/8 REG |  | 2.23 | 1 |  | DIESEL (LTR)
YIELD POINT |  | 33 | FLOWRATE (GPM) |  | 850 |  | METERAGE (M) |  | 249 | -47 | 6X9.5" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 55.58 | 17.95 |  | RIG TANK | 108000
GEL ST. |  | 16/29 | PRESSURE (PSI) |  | 1070 |  | RPM SURF. |  | 90-110 | 90-110 | X-OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.3 |  | CAMP TANK | 22900
WL (ml/30 min.) |  | 10 | TORQ. ON-BTM (KLB-FT) |  | 8 |  | RPM BTM. |  | 90-110 | 90-110 | D.JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 5.15 | 1.15 |  | CONSUMED | 7700
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4 |  | WOB (TON) |  | 1-11 | 1-11 | 3X8" DCs |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 27.85 | 6.22 |  | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  | 84 |  | AVG. ROP (M/HR) |  | 7.02 | -1.3251 | X-OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.74 | 0.17 |  | TOTAL | 130900
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  | 85 |  | BIT ROT HRS. |  | 35.47 | 35.47 | 15 X 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.41 | 10.3 |  | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  | 83 |  | K-REVS IN 24 HRS |  | 73.77 | 73.77 | [11 empty] | RIG STORAGE | 200000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 212.82 | 212.82 | [11 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 10.3 | 10.3 | [11 empty] | CONSUMED
NaCl (mg/l) |  | 495 | JAR | 24.84 | NMDC |  | JET VELOCITY (M/SEC) |  | 64.5 | 64.5 | [11 empty] | RECEIVED | 135400
CHLORIDES |  | 300 | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) |  | 1.35 | 1.35 | [11 empty] | TOTAL | 240000
CALCIUM |  | 100 | DCS |  | STAB - 2 |  | HSI |  | 1.7 | 1.7 | [11 empty] | POB
OIL% |  |  | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 268.56 |  |  | MPCL | 5
SAND % |  | 0.5 | BHA ROT. HRS |  | 45.16 |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 49 |  |  | MPCL SERV | 13
SOLIDS % |  | 4 | ON BOTTOM HRS |  | 35.47 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 34 |  |  | SECURITY
M.B.T. |  | 20 | CIRC. HRS |  | 46.11 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  |  | 66 |  | 0.5 | [8 empty] | TOTAL | 104
DAILY WELL COST (US$) |  | 39065 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 110 |  | 0.5 | [8 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1629656 | SHAKER-3 | 1 X 80 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 210 |  | 0.5 | [8 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 9.029% | MUD CLEANER | 3 X 200 |  |  | 7" LINER | [14 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | CHINJI
FIRE DRILL |  |  | BLIND RAMS |  |  |  | P-3 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43092 | 43092.0417 | 1 | DRL | PT-P | S | CONTINUED RECORDING TOTCO DEVIATION SURVEY ON SLICKLINE (DEV: 0.5° @ 210M).
43092.0417 | 43092.25 | 5 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED 26" HOLE FROM 219M TO 238M. OBSERVED SHAKERS OVERFLOW REPEATEDLY DUE TO PLUGGING OF SCREENS. CLEANED SHAKER SCREENS CONTINUOUSLY WITH WASHING GUN.
43092.25 | 43092.3333 | 2 | DRL | PT-P | BHA | POOH TO SURFACE. FOUND HOLE CONDITION GOOD.
43092.3333 | 43092.5 | 4 | DRL | NPT-UP | OTH | PREPARED FRESH MUD OF 1.08 SP.GR. MONITORED WELL DURING MUD PREPARATION. WELL STATIC.
43092.5 | 43092.5833 | 2 | DRL | PT-P | BHA | RIH DOWN TO BOTTOM. DURING RIH, ADDED 26" S.STAB @ TOP OF 3RD JOINT OF 11" DC.
43092.5833 | 43093 | 10 | DRL | PT-P | D | RESUMED DRILLING. DRILLED AHEAD 26" HOLE FROM 238M TO 296M. REAMED AT EACH CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43093 | 43093.25 | 6 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED AHEAD 26" HOLE FROM 296M TO 334M. REAMED AT EACH CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAGRI (20% SAND 80% CLAY)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 26" HOLE SECTION
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RECORDED TOTCO SURVEY. WHILE DRILLING FROM 219M TO 238M, OBSERVED SHAKERS OVERFLOW REPEATEDLY DUE TO PLUGGING OF SCREENS. POOH TO CHECK HOLE CONDITION. PREPARED FRESH MUD OF 1.08 SP.GR. RIH DOWN TO BOTTOM. DRILLED 26" HOLE FROM 238M TO 296M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 26" HOLE SECTION.
REMARKS