## DDR#30
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 30
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-03
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 29.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-06-02 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 109
CHECK TIME | 10:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1971
DEPTH, MD (M) | 2085 | 2085 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 530
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 2610
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 1711
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 64 | 66 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 4321
PV | 45 | 46 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 36 | 35 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 136171
GEL ST. | 13/15 | 14/16 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 22252
WL (ml/30 min) | 7 | 6.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 6030
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.2 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 158423
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9 | 9.3 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 82000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 24000
KCl (mg/l) | 41947.4 | 50336.9 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 21000
CHLORIDES (mg/l) | 20000 | 24000 | MOTOR |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL | 482000
HARDNESS (mg/l) | 460 | 460 | 9 1/2" DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
SAND % | 0.25 | 0.25 | 8" DCS |  | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 5
LUBRICANT % | 0.25 | 0.25 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 28
SOLIDS % | 34.72 | 34.57 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 51240.83 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 20" SURFACE/ K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3333554.3734 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 16.75% | MUD CLEANER | 3 x 120 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43618 | 43618.0833 | 2 | DRL | NPT-UP | RIH | RIH 5 1/2" OEDPS WITH MULE SHOE FROM 1493M TO 2073M. WASHED DOWN FROM 2073M TO BTM @ 2085M. OBSERVED WELL TRICKLING WHILE RIH.
43618.0833 | 43618.2083 | 3 | DRL | NPT-UP | CIR | CIRCULATED FOR BTM UP. RECORDED MAX MWT OUT = 1.99 SG AFTER CIRCULATION. MIN MUD CUT OF 1.02 SG RECEIVED DURING CIRCULATION. DUMPED 320 BBL LIGHT WEIGHT MUD.
43618.2083 | 43618.4792 | 6.5 | DRL | NPT-UP | SHUT | SHUT-IN WELL & RECORDED BOTH SIDP = 0 & SICP = 0.
43618.4792 | 43618.6354 | 3.75 | DRL | NPT-UP | CIR | DIRECT CIRCULATED COMPLETE CYCLE WITH 2.06 SG MUD, RECORDED MWT OUT = 2.04 SG AFTER COMPLETE CYCLE. OBSERVED NO LOSS / GAIN DURING CIRCULATION.
43618.6354 | 43618.6562 | 0.5 | DRL | NPT-UP | FC | P/BACK TO 2062M. FLOW CHECKED - WELL STATIC.
43618.6562 | 43618.6771 | 0.5 | DRL | NPT-UP | P/T | HELD PJSM. R/UP, FLUSHED & P/TESTED SLB CMT LINES AT 300 / 1000 PSI.
43618.6771 | 43618.7292 | 1.25 | DRL | NPT-UP | LOT | CLOSED BOP & ESTABLISHED LOT = 2.16 SG EMW. OPENED BOP & R/DOWN CMT LINES.
43618.7292 | 43618.8958 | 4 | DRL | NPT-UP | CIR | DIRECT CIRCULATED COMPLETE CYCLE WITH 2.06 SG MUD, RECORDED MWT OUT = 2.05 SG AFTER COMPLETE CYCLE. OBSERVED NO LOSS / GAIN DURING CIRCULATION.
43618.8958 | 43618.9167 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43618.9167 | 43619 | 2 | DRL | NPT-UP | POOH | POOH 5 1/2" OEDPS FROM 2062M TO 1532M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43619 | 43619.1146 | 2.75 | DRL | NPT-UP | POOH | CONT'D POOH 5 1/2" OEDPS FROM 1532M TO 570M (INSIDE 20" CASING SHOE).
43619.1146 | 43619.1354 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43619.1354 | 43619.2083 | 1.75 | DRL | NPT-UP | POOH | POOH 5 1/2" OEDPS FROM 570M TO SURFACE. L/DOWN MULE SHOE.
43619.2083 | 43619.25 | 1 | DRL | PT-P | BOPT | HELD PJSM. M/U & RIH TEST PLUG ASSY, RETRIEVED WEAR BUSHING & SET TEST PLUG IN 21-1/4" CHH.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | P/TEST BOP IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH 5 1/2" OEDPS FROM 1493M TO BTM @ 2085M. CIRCULATED FOR BTM UP. SHUT-IN WELL & RECORDED BOTH SIDP = 0 & SICP = 0. CIRCULATED WITH 2.06 SG MUD. FLOW CHECKED - WELL STATIC. ESTABLISHED LOT = 2.16 SG EMW. CIRCULATED WITH 2.06 SG MUD & OBSERVED NO LOSS / GAIN DURING CIRCULATION. FLOW CHECKED - WELL STATIC. POOH 5 1/2" OEDPS FROM 2062M TO 1532M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | P/TEST BOP STACK. RIH 17 1/2" BIT WITH ROTARY BHA.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21