## DDR#301
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 301
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 84.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 19 |  | BHA No. |  |  | 45 | IN (M) |  | 4445 |  | OUT (M) |  |  | STRING (BBL) | 162
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4574.42 |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 675.5
DEPTH, MD (M) |  | 4574 | TVD @ 00:00HR (M) |  | 4322.59 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.16 |  |  | PITS (BBL) | 995
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | SKH613 |  | MUD MOTOR |  |  | 4.75 | 2.1875 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1832.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E238865 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.82 |  |  | RESV. SYS (BBL) | 205
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | ST. STAB |  |  | 5.875 | 2.3125 |  | 3 1/2 IF |  | 1.23 |  |  | KILL MUD (BBL) | 1300
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 x 14 |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 65 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4446 |  | SLIM PULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 3337.5
PV |  | 41 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 2.45 |  |  | DIESEL (LTR)
YIELD POINT |  | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 129 |  | NMDC |  |  | 4.6875 | 2 1/8" |  | 3 1/2 IF |  | 9.32 |  |  | RIG TANK | 110000
GEL ST. |  | 14/18 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 9X 4-3/4" DCs |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 83.39 |  |  | CAMP TANK | 29600
WL (ml/30 min.) |  | 3.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 12X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.34 |  |  | CONSUMED | 3600
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 4.75" HYD D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 8.99 |  |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  | 137 |  | AVG. ROP (M/HR) |  |  |  | 18X 3-1/2" HWDPs |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.65 |  |  | TOTAL | 139600
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 461.96 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 107470
KCl (mg/l) |  | 52434.3 | JAR | 52.04 | STAB - 1 | 35.66 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 107470
CHLORIDES |  | 24600 | 3 1/2" HWDPS | 52.04 | STAB - 2 |  | TFA (IN²) |  | 0.4509 | [12 empty] | TOTAL | 440000
CALCIUM |  | 180 | 4 3/4" DCS | 52.04 | NMDC | 35.66 | HSI | [14 empty] | POB
OIL % |  |  | MUD MOTOR | 35.66 | SPSA | 35.66 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 406.37 |  |  | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  | 52.04 |  | BIT NO. 19 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 14 |  |  | MPCL SERV | 28
SOLIDS % |  | 15.79 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS |  | 0 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4450 |  | 45.44 |  | 75 |  |  | 0.88 |  | MWD |  | TOTAL | 122
DAILY WELL COST (US$) |  | 28220 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4478 |  | 46.09 |  | 75.08 |  |  | 0.7 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 18750531 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4508 |  | 46.3 |  | 75.2 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 103.9% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4536.55 |  | 46.29 |  | 74.06 |  |  | 0.87 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 750/1144/1620 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40/50 |  | 4457 |  | 1320/2095/2985 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 800/1160/1620 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4547/4304.1
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43390 | 43390.1458 | 3.5 | DRL | NPT-UP | STK/ CTB | HELD PJSM. R/DOWN CT INJECTOR HEAD, CT BOP & SAFETY VALVE.
43390.1458 | 43390.4896 | 8.25 | DRL | NPT-UP | STK | CONNECTED TDS, WORKED ON STUCK STRING INTERMITTENTLY. MEANWHILE ARRANGED W.LINE FOR FPIT.
43390.4896 | 43390.5 | 0.25 | DRL | NPT-UP | STK/ SM | PJSM FOR SCHL W.LINE RIG UP.
43390.5 | 43390.7292 | 5.5 | DRL | NPT-UP | STK/ W/L | R/UP SCHL W.LINE FOR DUMMY TRIP( TOOL OD 1.69"). RIH DUMMY TOOL ON WIRE LINE INSIDE STRING DOWN TO 4288m. OBSERVED COMPRESSION AT 4288 M. MADE THREE ATTEMPTS, TOOL DID NOT PASS . POOH TOOL TO SURFACE.
43390.7292 | 43390.7396 | 0.25 | DRL | NPT-UP | STK/ SM | PJSM FOR SCHL W.LINE PULLEY RIG UP UNDER CROWN BLOCK.
43390.7396 | 43390.875 | 3.25 | DRL | NPT-UP | STK/ W/L | HUNG WIRE LINE PULLEY UNDER CROWN BLOCK. R/UP SCHL WIRELINE GEARS. SET HOOK LOAD AT 175 TONS. RAN DUMMY TOOL ON WIRE LINE THROUGH TDS DOWN TO 4115M. OBSERVED W.LINE CABLE ARMOR DAMAGED. DISCUSSED & DECIDED TO TERMINATE THE OPERATION WITH EXISTING CABLE.
43390.875 | 43391 | 3 | DRL | NPT-UP | STK/ W/L | PULLED OUT W.LINE FROM INSIDE STRING TO SURFACE. R/DOWN W.LINE TOOL & GEARS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43391 | 43391.25 | 6 | DRL | NPT-UP | STK | CONNECTED TDS, WORKED ON STUCK STRING INTERMITTENTLY, MEANWHILE ARRANGING W.LINE FOR FPIT.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WORK ON STUCK STRING INTERMITTENTLY. MEANWHILE ARRANGING W.LINE FOR FPIT.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | R/DOWN CT INJECTOR HEAD, BOP, WORKED ON STUCK STRING INTERMITTENTLY, R/UP SCHL W.LINE, RIH DUMMY TOOL DOWN TO 4288M, OBSERVED COMPRESSION. PULLED OUT & RERUN W.LINE BY KEEPING THE STRING IN TENSION, RIH TO 4115M, OBSERVED W.LINE CABLE ARMOR DAMAGED, PULLED OUT TO SURFACE, R/DOWN SCHL. W.L.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE WORK ON STUCK STRING INTERMITTENTLY. MEANWHILE ARRANGING W.LINE FOR FPIT, FPIT JOB.
REMARKS |  |  | DISPATCHED 5'' LINER HANGER TO W.FORD YARD ON 17-10-18.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14