## DDR#307
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 307
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO/ SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4574.42 / 4322.59 METER | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 90.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4574.42 / 4322.59 METER | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | 19 | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 834
DEPTH, MD (M) |  | 4574 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | NOV | [11 empty] | PITS (BBL) | 800
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | SKH613 | [11 empty] | ACT. SYS (BBL) | 1634
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | E238865 | [11 empty] | RESV. SYS (BBL) | 286
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [15 empty] | KILL MUD (BBL) | 1100
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [15 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 53 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [15 empty] | TOTAL | 3020
PV |  | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 17 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [15 empty] | RIG TANK | 102897
GEL ST. |  | 7/13 | PRESSURE (PSI) |  |  |  | RPM SURF. | [15 empty] | CAMP TANK | 26273
WL (ml/30 min.) |  | 3.9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | CONSUMED | 12699
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [15 empty] | RECEIVED | 0
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [15 empty] | TOTAL | 129170
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [15 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [15 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 129670
KCl (mg/l) |  | 52434.3 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 129670
CHLORIDES |  | 24600 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [15 empty] | TOTAL | 385000
CALCIUM |  | 180 | 4 3/4" DCS |  | NMDC |  | HSI | [15 empty] | POB
OIL % |  |  | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  | 0 |  | BIT NO. 19 |  | LOST IN HOLE |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 13
SOLIDS % |  | 15.79 | ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS |  | 0 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 44
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 |  | 4450 |  | 45.44 |  | 75 |  |  | 0.88 |  | MWD |  | TOTAL | 101
DAILY WELL COST (US$) |  | 42435 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 |  | 4478 |  | 46.09 |  | 75.08 |  |  | 0.7 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19086205 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) |  | 4508 |  | 46.3 |  | 75.2 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 105.7% | MUD CLEANER | 1 x 140 | 2 x 170 | [6 empty] | 4536.55 |  | 46.29 |  | 74.06 |  |  | 0.87 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" |  | 6725 PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 750/1144/1620 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" |  | 4670 PSI | 97% |  | 0.101 |  | 30/40/50 |  | 4457 |  | 1320/2095/2985 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" |  | 6725PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 800/1160/1620 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-05 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4547/4304.1
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-10-26 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43396 | 43396.0625 | 1.5 | DRL | NPT-UP | BHA | CONT'D POOH BHA FROM 227M TO SURFACE. FOUND 9TH DC SEVERED, EXPECTED TOP OF FISH = ± 4456M. L/DOWN ALL BHA COMPONENTS DURING POOH FOR INSPECTION.
43396.0625 | 43396.0729 | 0.25 | DRL | NPT-UP | RS | SERVICED TDS.
43396.0729 | 43396.4583 | 9.25 | DRL | NPT-UP | RIH | P/UP & M/UP 3 1/2'' MULE SHOE ON 3 1/2'' DP'S, RIH AND TAGGED TOP OF FISH AT 4459.40M.
43396.4583 | 43396.6667 | 5 | DRL | NPT-UP | CIR | CIRCULATED AND CONDITIONED MUD PRIOR TO PERFORM SIDE TRACK CEMENT PLUG JOB. MEANWHILE MIXED MUDPUSH II OF 15.00 lb/gal, IN MUD TANK.
43396.6667 | 43396.7083 | 1 | DRL | NPT-UP | RU / P/T | HELD PJSM. R/UP SCHL CIR HEAD AND CMT LINE. FLUSHED WITH WATER. P/T SAME AT LOW 500 - HIGH AT 3000 PSI - OK. PREPARED MIX FLUID.
43396.7083 | 43396.75 | 1 | DRL | NPT-UP | CIR | CIRCULATED, MEANWHILE CONT'D BATCH MIXING, WEIGHTED UP CMT SLURRY UP TO 17.50 lb/gal. ADDED RETARDER IN SPACER AND CMT SLURRY.
43396.75 | 43396.8021 | 1.25 | DRL | NPT-UP | CMT | PUMPED 40 bbls MUDPUSH II OF 15.0 lb/gal SPACER AHEAD FROM RIG PUMP. SQUEEZED AND PUSHED FOAM BALL INSIDE STRING. SWITCHED OVER TO DOWEL PUMPER, PUMPED 25.0 bbls OF 17.50 lb/gal BATCH-MIXED CMT SLURRY. STARTED DISPLACEMENT AS FOLLOWS: PUMPED 10 bls OF 15.0 lb/gal MUDPUSH II + PUMPED 162 bbls MUD OF 12.50 lbs/gal FROM DOWEL PUMPER. CLOSED VALVE, OBSERVED NO BACK FLOW. (TOTAL DISP. 172 bbls).
43396.8021 | 43396.875 | 1.75 | DRL | NPT-UP | POOH | DISCONNECTED CIRCULATING HEAD, POOH AT SLOW SPEED TO 4148M.
43396.875 | 43396.9375 | 1.5 | DRL | NPT-UP | WOC / CIR | CONNECTED CIRCULATING HEAD, CLOSED PIPE RAM AND REVERSE CIRCULATED 2 X STRING VOLUMES. DUMPED CONTAMINATION + SPACER OF 12.33 lb/gal TO 15 lb/gal. (TOTAL VOLUME DUMPED = 72 bbls).
43396.9375 | 43397 | 1.5 | DRL | NPT-UP | WOC / CIR | DIRECT CIRCULATION, CIRCULATED TO CONDITION MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43397 | 43397.25 | 6 | DRL | NPT-UP | WOC/POOH | POOH FROM 4148M TO 1254M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH BHA TO SURFACE AND L/DOWN SAME, P/UP AND M/UP 3 1/2'' MULE SHOE AND RIH ON 3 1/2'' DP'S & 5'' DP'S, RIH AND TAGGED FISH AT 4459.40M. CIRCULATION, PERFORMED KICK OFF PLUG JOB, POOH UPTO 4148M, REVERSE CIRCULATED OUT 2 X STRING VOLUMES, DUMPED CONTAMINATION + SPACER, DIRECT CIRCULATED.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WOC, POOH TO SURFACE, BOPT, P/UP & M/UP TC BIT AND RIH TO TAG/DRESS CMT.
REMARKS
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21