## DDR#309
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 309
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO/ SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 92.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4574.42 / 4322.59 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-10-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 20 |  | BHA No. |  |  | 46 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 168
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 659.6
DEPTH, MD (M) | 4574 | 4574 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | 6'' TC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.18 |  |  | PITS (BBL) | 763
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MX20G |  | BIT SUB (F.V) |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 |  |  | ACT. SYS (BBL) | 1590.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5289899 |  | 8 X 4 3/4'' DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 74.23 |  |  | RESV. SYS (BBL) | 328
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 517 |  | D. JAR |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 9.18 |  |  | KILL MUD (BBL) | 1100
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 X OPEN |  | 1 X 4 3/4''DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.29 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 59 | 55 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 27 X 3 1/2'' HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 254.66 |  |  | TOTAL | 3018.6
PV | 24 | 24 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 22 | 20 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 91936
GEL ST. | 7/16 | 7/13 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 25200
WL (ml/30 min.) | 3.5 | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5694
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 0
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 117136
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9 | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 96370
KCl (mg/l) | 52434 | 52434 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 96370
CHLORIDES | 24600 | 24600 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 385000
CALCIUM | 250 | 200 | 4 3/4" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  |  | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 348.61 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 0 |  | BIT NO. 20 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 13 |  |  | MPCL SERV | 16
SOLIDS % | 15.79 | 15.79 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 0 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4450 |  | 45.44 |  | 75 |  |  | 0.88 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 33290 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4478 |  | 46.09 |  | 75.08 |  |  | 0.7 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19176258 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4508 |  | 46.3 |  | 75.2 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 106.2% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4536.55 |  | 46.29 |  | 74.06 |  |  | 0.87 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 750/1144/1620 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40/50 |  | 4457 |  | 1320/2095/2985 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 30/40/50 |  | 4457 |  | 800/1160/1620 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4547/4304.1
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43398 | 43398.0625 | 1.5 | DRL | NPT-UP | WOC/RIH | CONT'D RIH FROM 3526M TO 4125M. FILLED UP STRING EVERY 15 STANDS.
43398.0625 | 43398.0833 | 0.5 | DRL | NPT-UP | RW | PRECAUTIONARY WASHED DOWN FROM 4125M & TAGGED CMT AT 4184M.
43398.0833 | 43398.8854 | 19.25 | DRL | NPT-UP | DC | DRILLED OUT CMT FROM 4184M TO 4447M. OBSERVED MODERATELY HARD TO HARD CMT BELOW 4230M.
43398.8854 | 43399 | 2.75 | DRL | NPT-UP | CIR | PUMPED 25 BBL HI-VIS AND CIRCULATED OUT SAME. KEPT CIRCULATING TILL SHAKERS CLEAN.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43399 | 43399.0104 | 0.25 | DRL | NPT-UP | PS | PUMPED SLUG.
43399.0104 | 43399.25 | 5.75 | DRL | NPT-UP | POOH | POOH FROM 4447M TO 1887M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH FROM 3526M TO 4125M, PRECAUTIONARY WASHED DOWN AND TAGGED CMT @ 4184M, DRILLED OUT CMT DOWN TO 4447M, SWEPT OUT 25 BBL HV PILL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, P/UP & M/UP KICK OFF ASSY AND RIH, SIDETRACK.
REMARKS |  |  | DEMOBILIZED USED D.JAR TO W.FORD YARD ON 25-10-18, 1 X DD ARRIVED ON LOCATION.
Formulas:
DHARIAN-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14