## DDR#31
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 31
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2201 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 30.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2201 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 9
2018-01-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3RR1 | 3RR1 | BHA No. |  |  | 5 | IN (M) |  | 1654 |  | OUT (M) | 2201 |  | STRING (BBL) | 123
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2201 |  | SIZE (IN) |  | 17.5 | 17.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2089
DEPTH, MD (M) | 2201 | 2201 | TVD @ 00:00HR (M) |  | 2201 |  | MANUFACTURER |  | NOV | NOV | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 831
MW IN (SG) | 1.52 | 1.52 | DAILY PROGRESS (M) |  | 9 |  | TYPE |  | TFH519 | TFH519 | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.82 | 2.9 |  | ACT. SYS (BBL) | 3043
MW OUT (SG) | 1.52 | 1.52 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244694 | E244694 | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.79 | 0.2 |  | RESV. SYS (BBL) | 1046
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 | S422 | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.42 | 0.8 |  | KILL MUD (BBL) | 400
FL TEMP. °F | 149 | 149 | AVG. WOB (TON) |  |  |  | NOZZLES |  | 5 X 18/32" | 5X18/32" | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) | 57 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 1654 | 1654 | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.43 | 2.7 |  | TOTAL | 4489
PV | 31 | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 2201 |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.8 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 29 | 31 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 547 |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 9.43 | 2.4 |  | RIG TANK | 100000
GEL ST. | 7/24 | 8/26 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 100 - 115 |  | 9 1/2" FILTER SUB |  |  | 9.5 | 3.875 |  | 7 5/8 REG |  | 2.45 | 0.79144 |  | CAMP TANK | 13600
WL (ml/30 min.) | 4.8 | 4.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 190 - 205 |  | 3 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.63 | 8.9256 |  | CONSUMED | 15600
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 3 - 10 |  | X/OVER |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.93 | 0.30043 |  | RECEIVED
ALK (MUD) | 0.8 | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 2.7612 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.47 | 4.1243 |  | TOTAL | 113600
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 198.1 |  | DRILLING JAR |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.65 | 1.2616 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 85 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.46 | 4.1221 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 2190 |  | X/OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.95 | 0.21213 |  | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.17 | 4.1809 |  | CONSUMED | 100000
KCl (mg/l) | 53387.6 | 53387.6 | JAR | 187.8 | NMDC | 187.8 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 102850
CHLORIDES | 25000 | 25000 | 5" HWDPS | 187.8 | STAB - 1 | 187.8 | TFA (IN²) |  | 1.24 | [12 empty] | TOTAL | 445000
CALCIUM | 140 | 160 | 8" DCS | 187.8 | STAB - 2 |  | HSI | [14 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS | 187.8 | SPSA | 187.8 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 164.38 |  |  | MPCL | 3
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 187.8 |  | BIT No. 3RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 22
SOLIDS % | 16.28 | 16.28 | ON BOTTOM HRS |  | 179.3 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | 5
M.B.T. | 10 | 10 | CIRC. HRS |  | 233.59 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 80 | 2 X 80 |  | 20" SURFACE CASING |  |  | 594 | 2080 |  | 0.89 |  | 89.99 |  |  | 0.39 |  | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 47064 | SHAKER-2 | 2 X 120 | 1 X 80 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 2108 |  | 1.05 |  | 96.19 |  |  | 0.2 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3332966 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2137 |  | 1.47 |  | 109.86 |  |  | 0.53 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 18.47% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2165 |  | 1.83 |  | 108.59 |  |  | 0.39 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 295
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 2200 |  | 260/400 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 2200 |  | 240/380 |  | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2017-12-31 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 5 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43120 | 43120.3229 | 7.75 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 2192 M TO 2196 M IN SLIDE MODE.
43120.3229 | 43120.4583 | 3.25 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 2196 M TO 2201 M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEY. (OBSVD SLOW ROP)
43120.4583 | 43120.5312 | 1.75 | DRL | PT-P | CIR | CIRCULATED BOTTOMS UP.
43120.5312 | 43120.5417 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC.
43120.5417 | 43120.6667 | 3 | DRL | PT-P | POOH | POOH F/2201 M TO 1528 M ON ELEVATOR. OBSERVED TIGHT SPOT AT 1528 M (5-15 T).
43120.6667 | 43120.7083 | 1 | DRL | PT-P | RW | CONNECTED TDS, HARD BACK REAMED F/1528 M TO 1491 M.
43120.7083 | 43121 | 7 | DRL | PT-P | RW | SOFT BACK REAMED FROM 1491 M TO 847 M. (HARD BACK REAMED F/ 1310 M TO 1280 M ).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43121 | 43121.0729 | 1.75 | DRL | PT-P | RW | CONT'D SOFT BACK REAMED FROM 847 M TO 588 M.
43121.0729 | 43121.0833 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC
43121.0833 | 43121.125 | 1 | DRL | PT-P | RW | WHILE POOH INSIDE CSG, OBSERVED O/PULL (5-10 T). CONNECTED TDS AND PUMPED OUT FROM 588 M TO 528 M.
43121.125 | 43121.1667 | 1 | DRL | PT-P | POOH | POOH FROM 528 M TO 165 M ON ELEVATOR.
43121.1667 | 43121.1771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC.
43121.1771 | 43121.25 | 1.75 | DRL | PT-P | BHA | CONT'D POOH FROM 165 M TO 63 M, MEANWHILE L/DOWN BHA IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (90% CLAYSTONE & 10% SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | POOH MEANWHILE L/DOWN BHA IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2'' HOLE FROM 2192 M TO 2201 M IN SLIDE / ROTARY MODE. CIRCULATION PRIOR POOH, POOH TO 1528, BACK REAMED FROM 1528 M TO 847 M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH TO SURFACE MEANWHILE L/DOWN BHA FOR NECESSARY INSPECTION, BOP TEST, P/UP BIT+ INSPECTED BHA AND RIH TO BTM AT 2201 M, DRILL AHEAD 17 1/2'' HOLE
REMARKS |  |  | RECORDED CHECK SHOT AT 2180 M: INCL: 1.94°, AZM: 104.14°
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21