## DDR#31
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 31
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 30.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-06-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 5 |  | BHA NO. |  |  | 6 | IN (M) |  | 2085 |  | OUT (M) |  |  | STRING (BBL) | 105
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 17 1/2" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1949
DEPTH, MD (M) | 2085 | 2085 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | HLB |  | TRICONE BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.51 | 0.16475 |  | PITS (BBL) | 696
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  |  |  | TYPE |  | EBXTA3GRC |  | BIT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.07 | 0.34565 |  | ACT. SYS (BBL) | 2750
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 13183610 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.43 | 0.78498 |  | RESV. SYS (BBL) | 1628
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 135M |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 X 20 + 1 X 22 |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.37 | 0.7656 |  | KILL MW (SG)
µ FUNNEL (SEC) | 65 | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2085 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.3 | 5.9116 |  | TOTAL | 4378
PV | 46 | 47 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.14 | 0.6913 |  | DIESEL (LTR)
YIELD POINT | 35 | 32 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.91 | 11.9234 |  | RIG TANK | 129881
GEL ST. | 13/15 | 12/14 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.30043 |  | CAMP TANK | 21705
WL (ml/30 min) | 6.7 | 6.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CONSUMED | 6817
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | DRILLING JAR |  |  | 7.9375 | 3 |  | 6 5/8 REG |  | 9.53 | 2.128 |  | RECEIVED
ALK (MUD) | 0.2 | 0.2 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | TOTAL | 151586
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | X/OVER |  |  | 7.625 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | WATER (LTR)
PH | 9.3 | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 8.4468 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 191400
KCl (mg/l) | 50336.9 | 50336.9 | JAR | 1.5 | STAB - 1 | 200 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 189400
CHLORIDES (mg/l) | 24000 | 24000 | MOTOR |  | STAB - 2 | 200 | TFA (IN²) |  | 1.29 | [12 empty] | TOTAL | 480000
HARDNESS (mg/l) | 460 | 460 | 9 1/2" DCS | 210 | STAB - 3 | 1.5 | HSI | [14 empty] | POB
SAND % | 0.25 | 0.25 | 8" DCS | 210 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.38 |  |  | MPCL | 5
LUBRICANT % | 0.25 | 0.25 | BHA ROT. HRS |  | 210 |  | BIT NO. 5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 25
SOLIDS % | 34.82 | 34.82 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 4.88 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 57139.98 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 20" SURFACE/ K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3390694.3534 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 17.03% | MUD CLEANER | 3 x 120 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2073 | 300 / 325 / 375 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2073 | 300 / 325 / 375 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2073 | 300 / 325 / 375 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43619 | 43619.1146 | 2.75 | DRL | NPT-UP | POOH | POOH 5 1/2" OEDPS FROM 1532M TO 570M (INSIDE 20" CASING SHOE).
43619.1146 | 43619.1354 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43619.1354 | 43619.2083 | 1.75 | DRL | NPT-UP | POOH | POOH 5 1/2" OEDPS FROM 570M TO SURFACE. L/DOWN MULE SHOE.
43619.2083 | 43619.4583 | 6 | DRL | PT-P | BOPT | HELD PJSM. M/U & RIH TEST PLUG ASSY, RETRIEVED WEAR BUSHING & SET TEST PLUG IN 21-1/4" CHH. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, PIPE RAMS, BLIND RAMS, HCR & MANUAL VALVES AT CHOKE / KILL LINES, FH FOSV, IBOP, ROTARY HOSE, STAND PIPE MANIFOLD VALVES, CO-FLEXIP & MASTER VALVE AT CHOKE MANIFOLD AT 300 / 3000 PSI FOR 5 / 10 MINS, OK. RETRIEVED TEST PLUG AND INSTALLED WEAR BUSHING. L/DOWN TEST PLUG ASSEMBLY.
43619.4583 | 43619.6458 | 4.5 | DRL | NPT-UP | BHA | P/UP, M/UP & RIH NEW 17 1/2" TC BIT NO. 5 WITH 03 X STRING STABS ROTARY BHA TO 215M. WHILE RIH P/UP 4 X 9 1/2" DCS, 03 X STABS & JAR FROM CATWALK.
43619.6458 | 43619.6875 | 1 | DRL | NPT-UP | RIH | RIH BHA FROM 215M TO 570M (INSIDE 20" CASING SHOE).
43619.6875 | 43619.7083 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43619.7083 | 43620 | 7 | DRL | NPT-UP | RW | RIH FROM 570M TO 1447M. WHILE RIH OBSERVED & CLEARED SEVERAL TIGHT SPOTS FROM 583M - 784M, 911M - 922M, 1032M - 1046M, 1168M - 1188M, 1223M - 1245M & 1340M - 1360M WITH REAMING / WASHING DOWN.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43620 | 43620.2188 | 5.25 | DRL | NPT-UP | RW | CONT'D RIH FROM 1447M TO 2080M. OBSERVED & CLEARED TIGHT SPOTS FROM 1631M - 1635M, 1710M - 1717M & CLEARED HOLE FILL FROM 2076M - 2080M.
43620.2188 | 43620.25 | 0.75 | DRL | NPT-UP | CIR | CIRCULATING & ADDING LCM / WELLBORE STRENGTHENING MATERIAL IN MUD SYSTEM AS PER PROGRAM.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH 5 1/2" OEDPS FROM 1532M TO SURFACE. P/TESTED BOP STACK. M/UP & RIH NEW 17 1/2" TC BIT WITH 03 X STRING STABS ROTARY BHA TO 1447M. WHILE RIH OBSERVED & CLEARED SEVERAL TIGHT SPOTS WITH REAMING / WASHING DOWN.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE & ADD LCM / WELLBORE STRENGTHENING MATERIAL IN MUD SYSTEM AS PER PROGRAM.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14