## DDR#313
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 313
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-10-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO/ HAMZA /MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4466 / 4248.71 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 96.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4475 / 4254.42 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 12
2018-10-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 22 | 22 | BHA No. |  |  | 48 | IN (M) |  | 4454 |  | OUT (M) |  |  | STRING (BBL) | 200.5
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4466 |  | SIZE (IN) |  | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 614.5
DEPTH, MD (M) | 4454 | 4466 | TVD @ 00:00HR (M) |  | 4248.71 |  | MANUFACTURER |  | SMITH | SMITH | 6'' PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 790
MW IN (SG) | 1.5 | 1.55 | DAILY PROGRESS (M) |  | 12 |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | MUD MOTOR |  |  | 5.875 | 3.75 |  | 3 1/2 REG |  | 7.21 | 0.53666 |  | ACT. SYS (BBL) | 1605
MW OUT (SG) | 1.5 | 1.55 | INST. ROP (M/HR) |  | 0.15 |  | SERIAL NO. |  | JN5339 | JN5339 | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.79 | 0.058802 |  | RESV. SYS (BBL) | 310
ECD (SG) | 1.6324 | 1.6324 | AVG. ROP (M/HR) |  | 1.45 |  | IADC CODE |  |  |  | LOWER SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.46 | 0.034239 |  | KILL MUD (BBL) | 1100
FL TEMP. °F | 118 | 118 | AVG. WOB (TON) |  | 3.5 |  | NOZZLES (1/32") |  | 3 X 13 | 3 X 13 | SLIMPULSE |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 | 0.70339 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 56 | 58 | AVG. RPM SURFACE |  | 40 |  | DEPTH IN (M) |  | 4454 | 4454 | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.3 | 0.32006 |  | TOTAL | 3015
PV | 28 | 29 | AVG. RPM DOWNHOLE |  | 175 |  | DEPTH OUT (M) |  |  |  | 9 X 4 3/4'' DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 83.41 | 6.2084 |  | DIESEL (LTR)
YIELD POINT | 20 | 20 | FLOWRATE (GPM) |  | 220 |  | METERAGE (M) |  | 12 |  | 3 X 3 1/2'' HWDP |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 28.36 | 1.0555 |  | RIG TANK | 101509
GEL ST. | 7/15 | 8/16 | PRESSURE (PSI) |  | 3000 |  | RPM SURF. |  | 40 |  | D. JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.18 | 0.68329 |  | CAMP TANK | 23336
WL (ml/30 min.) | 3.4 | 3.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 175 |  | 18 X 3 1/2'' HWDP |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 169.78 | 6.3944 |  | CONSUMED | 5836
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 1-4 | [12 empty] | RECEIVED
ALK (MUD) | 1 | 1 | STRING WT. (TON) - ROT |  | 142 |  | AVG. ROP (M/HR) |  | 1.4493 | [12 empty] | TOTAL | 124845
ALK (FILT.) | 0.7 | 0.8 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 8.28 | [12 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 67.11 | [12 empty] | RIG STORAGE | 380000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 67.11 | [12 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 71.26 | [12 empty] | CONSUMED | 73590
KCl (mg/l) | 51480.9 | 47667.5 | JAR | 3.1 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 55.2 | [12 empty] | RECEIVED | 73590
CHLORIDES | 23000 | 24000 | 3 1/2" HWDPS | 3.1 | STAB - 2 |  | TFA (IN²) |  | 0.39 | [12 empty] | TOTAL | 415000
CALCIUM | 240 | 220 | 4 3/4" DCS | 3.1 | NMDC | 3.1 | HSI | [14 empty] | POB
OIL % |  |  | MUD MOTOR | 3.1 | SPSA | 3.1 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 313.14 |  |  | MPCL | 6
LUBE % | 0.5 | 1 | BHA ROT. HRS |  | 3.1 |  | BIT NO. 22 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 11 |  |  | MPCL SERV | 17
SOLIDS % | 16.39 | 18.39 | ON BOTTOM HRS |  | 8.28 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 9.7 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 17
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 140 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 123
DAILY WELL COST (US$) |  | 84284.84 | SHAKER-2 | 1 x 120 | 2 x 140 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 19390042.5895 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 107.4% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4447 |  | 755 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4447 |  | 1085 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4447 |  | 1500 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4547/4304.1
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43402 | 43402.0521 | 1.25 | DRL | NPT-UP | BHA | POOH BHA FROM 265M TO SURFACE.
43402.0521 | 43402.1354 | 2 | DRL | NPT-UP | BHA/ E/C | P/UP AND M/UP USED TC BIT + MUD MOTOR + DIRECTIONAL TOOLS. SET ABH TO 1.5°. SCRIBED TOOL FACE. SHALLOW FUNCTION TESTED DIRECTIONAL TOOLS @ 200 GPM, 750 PSI. B/OUT USED BIT AND REPLACED WITH NEW PDC BIT.
43402.1354 | 43402.1875 | 1.25 | DRL | NPT-UP | BHA | RIH AS PER BHA DOWN TO 313M.
43402.1875 | 43402.5938 | 9.75 | DRL | NPT-UP | RIH | RIH FROM 313M TO 4446M.
43402.5938 | 43402.6354 | 1 | DRL | NPT-UP | RW | CONNECTED TDS, TURNED ON PUMP, RECORDED WEIGHTS, WASHED DOWN & TAGGED BTM AT 4454M. RECORDED SCR.
43402.6354 | 43402.9062 | 6.5 | DRL | NPT-UP | DM | DRILLED 6'' DIRECTIONAL HOLE IN SLIDE MODE FROM 4454M TO 4461M.
43402.9062 | 43403 | 2.25 | DRL | NPT-UP | DM | DRILLED 6'' DIRECTIONAL HOLE IN ROTARY MODE FROM 4461M TO 4466M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-10-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43403 | 43403.1146 | 2.75 | DRL | NPT-UP | DM | DRILLED 6'' DIRECTIONAL HOLE IN ROTARY MODE FROM 4466M TO 4472M.
43403.1146 | 43403.25 | 3.25 | DRL | NPT-UP | DM | DRILLED 6'' DIRECTIONAL HOLE IN SLIDE MODE FROM 4472M TO 4475M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 265M TO SURFACE. RIH WITH DIRECTIONAL BHA AND DRILLED 6" DIRECTIONAL HOLE IN ROTARY / SLIDE MODE FROM 4454M TO 4466M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6" DIRECTIONAL HOLE SECTION IN SLIDING / ROTATING MODE.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14