## DDR#314
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [16 empty] | Report No. |  | 314
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [7 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [7 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [7 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4815 | 4795.85 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 313.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4815 | 4795.85 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-03-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA | [5 empty] | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. | [5 empty] | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 367.7
CHECK TIME | 13:30 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. | [5 empty] | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 624.7
DEPTH, MD (M) | 4815 | 4815 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [16 empty] | PITS (BBL) | 536
MW IN (SG) | 1.96 | 1.96 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [16 empty] | ACT. SYS (BBL) | 1528.4
MW OUT (SG) | 1.96 | 1.96 | INST. ROP (M/HR) |  |  |  | TYPE | [16 empty] | RESV. SYS (BBL) | 956
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [16 empty] | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [16 empty] | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 66 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [16 empty] | TOTAL | 2724.4
PV | 42 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [16 empty] | DIESEL (LTR)
YIELD POINT | 28 | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [16 empty] | RIG TANK | 89208
GEL ST. | 11/20 | 09/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [16 empty] | CAMP TANK | 16562
WL (ml/30 min) | 4.3 | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [16 empty] | CONSUMED | 5445
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [16 empty] | RECEIVED | 24000
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [16 empty] | TOTAL | 105770
ALK (FILT.) | 0.2/1.0 | 0.2/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [16 empty] | WATER (LTR)
pH | 9 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [16 empty] | RIG STORAGE | 551357
MAX SHIELD % | 3 | 2.75 | D & I SURVEY-(OFF BIT-M)Telescope |  |  |  | K-REVS IN 24 HRS | [16 empty] | CAMP STORAGE | 80000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [16 empty] | CONSUMED | 65917
KCl (mg/l) | 48620.8 | 45760.8 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [16 empty] | RECEIVED | 64600
CHLORIDES (mg/l) | 104000 | 101000 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [16 empty] | DRL WASTE | 116000
HARDNESS (mg/l) | 350 | 320 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [16 empty] | POB
PENETRAX % | 1 | 0.5 | 6.5" DCS |  | STAB - 3 |  | HSI | [5 empty] | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
MAX GUARD % | 2 | 1.75 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL | [5 empty] | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 26
SOLIDS % | 42.12 | 42.69 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  |  |  | BIT NO. 26 RR3 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA | [5 empty] | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 |  | 4694.62/4684.81 |  | 22.91 |  | 286.48 |  |  | 3.36 |  | MWD |  | TOTAL | 109
DAILY WELL COST (US$) |  | 40957.85 | SHAKER-2 | 2 x 200 + 1 x 170 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 |  | 4722.95/4710.87 |  | 23.29 |  | 285 |  |  | 0.73 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 21927692.831 | SHAKER-3 | 2 x 140 + 1 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4391 | 4749.77/4735.55 |  | 22.77 |  | 287.05 |  |  | 1.07 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 110.2% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER#01 (VM140HC, 32#, VT) |  |  |  | 4496 - 4996 |  | 4781.65/4765.04 |  | 21.82 |  | 286.3 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 2
[7 empty] | 7'' LINER#02 (VM140HC, 32#, VT) | [5 empty] | 4798.8/4780.90 |  | 23.01 |  | 286.88 |  |  | 2.112 |  | MWD |  | MAASP (PSI) | 249.2997
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [10 empty] | SLOW CIRCULATION RATE (1.96 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 30 |  | 4762 | 940/920/920 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 40 |  | 4762 | 1080/1060/1060 |  |  | PATALA | 4715/4703.61
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 50 |  | 4762 | 1250/1250/1250 |  |  | HANGU | 4740/4726.58
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA | [5 empty] | DOWNHOLE FLUID LOSSES | [10 empty] | DANDOT | 4753/4738.56
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS | [5 empty] | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | BAGHANWALA | 4773/4757
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-09 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 24 |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 150 |  | JUTANA | 4788/4770.97
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-2 | [5 empty] | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KUSSAK | 4813/4794.01
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43902 | 43902.0312 | 0.75 | DRL | PT-P | CIR | CONT'D CIRCULATION FOR 1.5 TIMES LINER VOLUME AT 125 GPM.
43902.0312 | 43902.375 | 8.25 | DRL | PT-P | RC | RIH 7" LINER ON 5" DP STRING FROM 1421M TO 3406M. WHILE RIH, DRIFTED DRILL STRING STANDS WITH 2 5/8" DRIFT. FILLED AFTER 5 STANDS.
43902.375 | 43902.3854 | 0.25 | DRL | PT-P | CIR | BROKE CIRCULATION.
43902.3854 | 43902.5625 | 4.25 | DRL | PT-P | RC | RIH 7" LINER ON 5" DP STRING FROM 3406M TO 4380M. WHILE RIH, DRIFTED DRILL STRING STANDS WITH 2 5/8" DRIFT. FILLED AFTER 5 STANDS.
43902.5625 | 43902.5833 | 0.5 | DRL | PT-P | CIR | BROKE CIRCULATION & RECORDED PARAMETERS.
43902.5833 | 43902.6354 | 1.25 | DRL | PT-P | RC | RIH 7" LINER ON 5" DP STRING FROM 4380M TO 4763M. WHILE RIH, DRIFTED DRILL STRING STANDS WITH 2 5/8" DRIFT. FILLED AFTER 5 STANDS.
43902.6354 | 43902.7396 | 2.5 | DRL | PT-P | RW | OBSERVED COMPRESSION AT 4763M, ATTEMPTED TO CLEAR WITH RECIPROCATION, NO SUCCESS. REAMED DOWN FROM 4763M TO 4815M.
43902.7396 | 43902.8646 | 3 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43902.8646 | 43902.9479 | 2 | DRL | PT-P | RC | HELD PJSM. DROPPED 1.75" AL BALL. P/U & M/U CEMENT HEAD ALREADY LOADED WITH DP DART. CHASED THE BALL WITH 50 GPM & 550 PSI PRESSURE. OBSERVED INCREASE IN SPP. INCREASED SPP TO 2000 PSI; HELD FOR 5 MINUTES & THEN BLED OFF TO 1000 PSI. SLACKED OFF STRING WT. OBSERVED LINER HANGER SLIPS BITE & HOLDING. APPLIED LINER WEIGHT + 35 TON WEIGHT ON SLIPS TO ENSURE SLIPS ENGAGED. INCREASED SPP AGAIN TO 2000 PSI; HELD FOR 5 MINUTES & THEN BLED OFF TO 'ZERO'. P/U STRING 0.5M TO CHECK FREE; TOOL RELEASED. SLACKED OFF 15 TON WEIGHT & INCREASED SPP GRADUALLY, OBSERVED BALL SEAT SHEAR AT 2400 PSI. RESUMED CIRCULATION.
43902.9479 | 43903 | 1.25 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43903 | 43903.0938 | 2.25 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD. MEANWHILE PREPARED MIX FLUID FOR CEMENT JOB.
43903.0938 | 43903.1146 | 0.5 | DRL | PT-P | P/T | HELD PJSM. P/T CEMENT LINES AT 5000 PSI.
43903.1146 | 43903.2292 | 2.75 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE ADDED RETARDER IN MIX FLUID & WEIGHT UP CEMENT SLURRY.
43903.2292 | 43903.25 | 0.5 | DRL | PT-P | CMC | CEMENT JOB IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KUSSAK : SANDSTONE, CLAYSTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | CEMENT JOB IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED FOR 1.5 TIMES LINER VOLUME. RIH 7" LINER ON 5" DP STRING FROM 1421M TO 4763M & REAMED DOWN TO 4815M. CIRCULATED TO CLEAN HOLE. SET LINER HANGER AS PER PROCEDURE & CIRCULATED TO CONDITION MUD.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM CEMENT JOB & SET PACKER. POOH TO SURFACE. RIH WITH 8 1/2" PDC BIT FOR COC.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14