## DDR#316
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 316
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO/ HAMZA /MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4543 / 4306.68 METER | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 99.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4543 / 4306.68 METER | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-11-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 22 | 22 | 22RR1 | BHA No. |  |  | 49 | IN (M) |  | 4543 |  | OUT (M) |  |  | STRING (BBL) | 57.2
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4543 |  | SIZE (IN) |  | 6 | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 818.8
DEPTH, MD (M) | 4543 | 4543 | TVD @ 00:00HR (M) |  | 4306.68 |  | MANUFACTURER |  | SMITH | SMITH | SMITH | 6'' PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 692
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | MDSi613WBPX | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 REG |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1568
MW OUT (SG) | 1.7 | 1.7 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5339 | JN5339 | JN5339 | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.77 | 0.13175 |  | RESV. SYS (BBL) | 373
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  |  | 1X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.2 | 0.68478 |  | KILL MUD (BBL) | 1050
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 3 X 13 | 3 X 13 | 6 X 13 | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.91 | 0.14217 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 52 | 53 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4454 | 4454 | 4543 | 11 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 102.08 | 7.5981 |  | TOTAL | 2991
PV | 30 | 29 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 4543 |  |  | 3 X HWDP |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 28.36 | 1.0555 |  | DIESEL (LTR)
YIELD POINT | 20 | 21 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 89 |  |  | D.JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.18 | 0.34165 |  | RIG TANK | 102204
GEL ST. | 8/14 | 9/15 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 40-80 |  |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.78 | 6.3186 |  | CAMP TANK | 21939
WL (ml/30 min.) | 3 | 2.9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 120-200 | [13 empty] | CONSUMED | 5701
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 1-5 | [13 empty] | RECEIVED
ALK (MUD) | 0.9 | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 1.9386 | [13 empty] | TOTAL | 124143
ALK (FILT.) | 0.5 | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 45.91 | [13 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 165.22 | [13 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 380.32 | [13 empty] | CAMP STORAGE | 55000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 71.26 | [13 empty] | CONSUMED | 40000
KCl (mg/l) | 49574.2 | 52434.3 | JAR | 30.63 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 55.2 | [13 empty] | RECEIVED | 40000
CHLORIDES | 25500 | 26000 | 3 1/2" HWDPS | 30.63 | STAB - 2 |  | TFA (IN²) |  | 0.39 |  | 0.77 | [11 empty] | TOTAL | 455000
CALCIUM | 280 | 260 | 4 3/4" DCS | 30.63 | NMDC | 30.63 | HSI | [15 empty] | POB
OIL % |  |  | MUD MOTOR | 30.63 | SPSA | 30.63 | DULL CODE |  | I-O-D-L-B-G-O-R |  |  | TOTAL LENGTH (M) | [7 empty] | 323.55 |  |  | MPCL | 5
LUBE % | 2 | 2 | BHA ROT. HRS |  | 30.63 |  | BIT NO. 22 |  | 1-1-WT-A-X-I-NO-BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 17
SOLIDS % | 23.92 | 23.9 | ON BOTTOM HRS |  | 45.91 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 56.31 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 |  | 4475/4255.10 |  | 41.12 |  | 82.75 |  |  | 7.5 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 33684.025 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 |  | 4504/4277.05 |  | 40.54 |  | 83.94 |  |  | 1 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19536409.8545 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) |  | 4528/4295.03 |  | 42.38 |  | 82.15 |  |  | 2.74 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 108.2% | MUD CLEANER | 1 x 140 | 2 x 170 | [17 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" |  | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4538 |  | 880 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" |  | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4538 |  | 1190 |  | MURREE | 1445
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" |  | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4538 |  | 1730 |  | KULDANA | 3776 / 3738
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4353/4167.8
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | SAKESAR | 4423/4217.4
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4539/4303.64
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43405 | 43405.1562 | 3.75 | DRL | NPT-UP | CIR | CONT'D CIRCULATION TO CLEAN HOLE & HOMOGENIZED MUD. RECORDED MWD SURVEY.
43405.1562 | 43405.1667 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43405.1667 | 43405.1979 | 0.75 | DRL | NPT-UP | POOH | POOH FROM 4543M TO 4433M (INSIDE 7'' LINER).
43405.1979 | 43405.2188 | 0.5 | DRL | NPT-UP | P/T | HELD PJSM, H/UP DOWEL LINE, FLUSHED LINE WITH WATER, CLOSED VALVE, P/TESTED SAME AT 2500 PSI, OK.
43405.2188 | 43405.2604 | 1 | DRL | NPT-UP | FIT | CLOSED BOP & CONDUCTED FIT WITH 1.70 SG MUD & 600 PSI SURFACE PRESSURE (1.80 SG EMW).
43405.2604 | 43405.6562 | 9.5 | DRL | NPT-UP | POOH | POOH FROM 4433M TO 313M (TOP OF BHA).
43405.6562 | 43405.6667 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43405.6667 | 43405.75 | 2 | DRL | NPT-UP | BHA | POOH FROM 313M TO SURFACE. BROKE OUT BIT, DRAINED & L/D MUD MOTOR AND MWD TOOLS.
43405.75 | 43405.8333 | 2 | DRL | NPT-UP | BHA | M/U RR 6" BIT & RIH PACKED BHA FROM SURFACE TO 324M.
43405.8333 | 43406 | 4 | DRL | NPT-UP | RIH | RIH FROM 324M TO 1951M. FILLED UP STRING EVERY 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43406 | 43406.25 | 6 | DRL | NPT-UP | RIH | CONT'D RIH FROM 1951M TO 4443M. FILLED UP STRING EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / SHALE.
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TO HOMOGENIZE MUD. PERFORMED FIT AT 1.80 SG EMW, POOH TO SURFACE, B/OUT AND L/DOWN DIRECTIONAL TOOLS. M/U RR 6" BIT & RIH PACKED BHA FROM SURFACE TO 1951M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM & DRILL AHEAD 6" HOLE SECTION.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14