## DDR#316
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 316
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4815 | 4795.85 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 315.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4815 | 4795.85 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-03-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 62 |  | BHA NO. |  |  | 75 | IN (M) |  | 4815 |  | OUT (M) | 4815 |  | STRING (BBL) | 0
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 26 RR4 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 964.8
DEPTH, MD (M) | 4815 | 4815 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.15 |  | PITS (BBL) | 488
MW IN (SG) | 1.96 | 1.96 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | NOV |  | BIT SUB |  |  | 6.5 | 3.125 |  | 4 1/2 IF |  | 1.06 | 0.14202 |  | ACT. SYS (BBL) | 1452.8
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | SKFX616M |  | 6x 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 55.22 | 7.3983 |  | RESV. SYS (BBL) | 1129
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | E260746 |  | DRL. JAR |  |  | 6.375 | 2.75 |  | 4 1/2 IF |  | 9.8 | 1.313 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 30x 5"HWDP |  |  | 6.625 | 3 |  | 4 1/2 IF |  | 280.4 | 20.5788 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 53 | 56 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3x12 + 3x13 | [12 empty] | TOTAL | 2821.8
PV | 37 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4815 | [12 empty] | DIESEL (LTR)
YIELD POINT | 21 | 20 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4815 | [12 empty] | RIG TANK | 80203
GEL ST. | 9/15 | 9/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 15377
WL (ml/30 min) | 5.8 | 5.9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4879
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 95580
ALK (FILT.) | 0.2/1.0 | 0.2/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 642305
MAX SHIELD % | 1.5 | 1.5 | D & I SURVEY-(OFF BIT-M)Telescope |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 74000
KCl (%) | 3.8 | 3.8 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 66526
KCl (mg/l) | 34320.6 | 34320.6 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 109800
CHLORIDES (mg/l) | 80000 | 79500 | JAR | 46.68 | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 92800
HARDNESS (mg/l) | 380 | 380 | 5" HWDPS | 176.08 | STAB - 2 |  | TFA (IN²) |  |  | 0.7201 | [12 empty] | POB
PENETRAX % | 0 | 0 | 6.5" DCS | 176.08 | STAB - 3 |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 346.72 |  |  | MPCL | 3
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 16
SOLIDS % | 43.37 | 43.39 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 2.94 |  | BIT NO. 26 RR4 |  |  | 2-3-WT-A-X-1-SP/DL-TD |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 101
DAILY WELL COST (US$) |  | 30311.7 | SHAKER-2 | 2 x 200 + 1 x 170 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 22214193.1736 | SHAKER-3 | 2 x 140 + 1 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 111.6% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER (VM140HC, 32#, VT) |  |  |  | 4996 / 4496 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4814 / 3397 (TOL) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.96 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | PATALA | 4715/4703.61
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | HANGU | 4740/4726.58
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | DANDOT | 4753/4738.56
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | BAGHANWALA | 4773/4757
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-09 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 24 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | JUTANA | 4788/4770.97
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 14 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KUSSAK | 4813/4794.01
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43904 | 43904.1354 | 3.25 | DRL | PT-P | RIH | CONT'D RIH FROM 1957M TO 3312M. FILLED STRING EVERY 15 STANDS.
43904.1354 | 43904.1667 | 0.75 | DRL | PT-P | RW | WASHED DOWN FROM 3312M TO 3397M, TAGGED TOP OF LINER (TOL) AT 3397M WITH 5 TON.
43904.1667 | 43904.2604 | 2.25 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN.
43904.2604 | 43904.3333 | 1.75 | DRL | PT-P | POOH | POOH FROM 3397M TO 2474M.
43904.3333 | 43904.4792 | 3.5 | DRL | PT-P | DP | POOH FROM 2474M TO 1687M. WHILE POOH, L/D 82x 5" G-105 DP.
43904.4792 | 43904.5 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43904.5 | 43904.8021 | 7.25 | DRL | PT-P | DP | POOH FROM 1687M TO 346M (BHA TOP). WHILE POOH, L/D 140x 5" G-105 DP.
43904.8021 | 43904.9583 | 3.75 | DRL | PT-P | BHA | POOH BHA TO SURFACE. WHILE POOH BHA, L/D 30x 5" HWDP, JAR, 6x 6 1/2" DC, BIT SUB & BIT.
43904.9583 | 43905 | 1 | DRL | PT-P | DP | L/D 4x 3 1/2" G-105 (13.3PPF) DP STANDS ALREADY RACKED BACK IN DERRICK FOR INSPECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43905 | 43905.0521 | 1.25 | DRL | PT-P | DP | L/D 7x 3 1/2" G-105 (13.3PPF) DP STANDS ALREADY RACKED BACK IN DERRICK FOR INSPECTION.
43905.0521 | 43905.1042 | 1.25 | DRL | NPT-P | RS | SLIPPED & CUT 108 FT DRILL LINE. ADJUSTED CROWN-O-MATIC & RESET ACS.
43905.1042 | 43905.25 | 3.5 | DRL | PT-P | BHA | P/U & M/U RR 6" PDC BIT WITH SLIM BHA & RIH DOWN TO 287M & IS IN PROGRESS. WHILE RIH, P/U 18x 4 3/4" DC & 13x 3 1/2" HWDP. DRIFTED AND FLUSHED EACH SINGLE. FLUSHED DC STRING.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH RR 8 1/2" PDC BIT WITH SLICK BHA DOWN TO 3312M. WASHED DOWN & TAGGED TOP OF LINER AT 3397M. CIRCULATED & POOH TO SURFACE. WHILE POOH, L/D 222x 5" G-105 DP. L/D 4x 3 1/2" G-105 (13.3PPF) DP STANDS IN DERRICK FOR INSPECTION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 6" BIT WITH SLIM BHA & COC.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14