## DDR#317
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 317
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4815 | 4795.85 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 316.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4815 | 4795.85 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-03-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 63 |  | BHA NO. |  |  | 76 | IN (M) |  | 4815 |  | OUT (M) |  |  | STRING (BBL) | 34.3
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 20 RR2 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 899.3
DEPTH, MD (M) | 4815 | 4815 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.1 |  | PITS (BBL) | 438
MW IN (SG) | 1.96 | 1.96 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1371.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi613 |  | 18x 4 3/4" DC |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 164.09 | 12.2137 |  | RESV. SYS (BBL) | 1129
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP2216 |  | 18x 3 1/2" HWDP |  |  | 4.8125 | 2.25 |  | 3 1/2 IF |  | 169.92 | 6.3997 |  | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 55 | 56 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x 12 | [12 empty] | TOTAL | 2740.6
PV | 36 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4815 | [12 empty] | DIESEL (LTR)
YIELD POINT | 22 | 21 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 76848
GEL ST. | 9/15 | 9/17 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 14748
WL (ml/30 min) | 5.9 | 5.9 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3984
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 91596
ALK (FILT.) | 0.3/1.0 | 0.3/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 619568
MAX SHIELD % | 1.5 | 1.5 | D & I SURVEY-(OFF BIT-M)Telescope |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) | 3.8 | 3.8 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 53237
KCl (mg/l) | 34320.6 | 34320.6 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 76700
CHLORIDES (mg/l) | 79000 | 79000 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 92800
HARDNESS (mg/l) | 380 | 380 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) |  |  | 0.3313 | [12 empty] | POB
PENETRAX % | 0 | 0 | 4 3/4" DCS |  | STAB - 3 |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 335.28 |  |  | MPCL | 3
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 14
SOLIDS % | 43.41 | 43.41 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  |  |  | BIT NO. 20 RR2 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 100
DAILY WELL COST (US$) |  | 27361.3333 | SHAKER-2 | 2 x 200 + 1 x 170 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 22241554.507 | SHAKER-3 | 2 x 140 + 1 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 111.7% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER (VM140HC, 32#, VT) |  |  |  | 4996 / 4496 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4814 / 3397 (TOL) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.96 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | PATALA | 4715/4703.61
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | HANGU | 4740/4726.58
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | DANDOT | 4753/4738.56
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | BAGHANWALA | 4773/4757
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-09 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | JUTANA | 4788/4770.97
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KUSSAK | 4813/4794.01
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43905 | 43905.0521 | 1.25 | DRL | PT-P | DP | L/D 7x 3 1/2" G-105 (13.3PPF) DP STANDS ALREADY RACKED BACK IN DERRICK FOR INSPECTION.
43905.0521 | 43905.1042 | 1.25 | DRL | NPT-P | RS | SLIPPED & CUT 108 FT DRILL LINE. ADJUSTED CROWN-O-MATIC & RESET ACS.
43905.1042 | 43905.2917 | 4.5 | DRL | PT-P | BHA | P/U & M/U RR 6" PDC BIT WITH SLIM BHA & RIH DOWN TO 335M. WHILE RIH, P/U 18x 4 3/4" DC & 18x 3 1/2" HWDP. DRIFTED AND FLUSHED EACH SINGLE. FLUSHED DC & HWDP STRING.
43905.2917 | 43905.4583 | 4 | DRL | NPT-P | RS | CHANGED TDS IBOP & WASH PIPE. P/T WASH PIPE AT 3000 PSI.
43905.4583 | 43905.625 | 4 | DRL | NPT-UP | OTH | CONDUCTED CAT5 INSPECTION OF 3 1/2" G-105 (15.5PPF) DPS.
43905.625 | 43906 | 9 | DRL | PT-P | RIH / DP | RIH FROM 335M TO 1537M. WHILE RIH, P/U INSPECTED 126x 3 1/2" G-105 (15.5PPF) DP. DRIFTED AND FLUSHED EACH SINGLE. FLUSHED THE STRING EVERY 30 SINGLES.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43906 | 43906.0729 | 1.75 | DRL | PT-P | RIH / DP | CONT'D RIH FROM 1537M TO 1738M. WHILE RIH, P/U INSPECTED 21x 3 1/2" G-105 (15.5PPF) DP. DRIFTED AND FLUSHED EACH SINGLE. FLUSHED THE STRING.
43906.0729 | 43906.25 | 4.25 | DRL | PT-P | RIH | RIH FROM 1738M TO 3377M & WASHED DOWN TO 3435M ON 5" DP STRING. RIH IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | L/D 7x 3 1/2" G-105 (13.3PPF) DP STANDS IN DERRICK FOR INSPECTION. SLIPPED & CUT 108 FT DRILL LINE. RIH RR 6" PDC BIT WITH SLIM BHA DOWN TO 335M. CHANGED IBOP & WASHPIPE. CONDUCTED CAT5 INSPECTION OF 3 1/2" G-105 (15.5PPF) DPS. CONT'D RIH FROM 335M TO 1537M. WHILE RIH, P/U INSPECTED 126x 3 1/2" G-105 (15.5PPF) DP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 6" BIT WITH SLIM BHA, COC & POOH.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14